## Sheet1
Project Analysis
Customer | Alcoa Fastening System-Waco | Avani Projected Costs |  |  | Avani Quoted Costs |  |  | Projected Profit |  | Actual Costs | Actual Profit
Date | 2015-06-08
Status | Complete
Sales Rep | RK
SO# | 22283
Rev. # | 1
|  | Actual | Quantity | Total Cost | Quoted | Quantity | Total Quoted | Dollars | % | Dollars | Dollars | %
Product | A-Smoke 40 Basic | 13780 | 8 | 110240 | 21200 | 8 | 169600 | 59360 | 53.85% | 110240 | 59360 | 53.85%
Product | A-Smoke 40 Stands | 372 | 8 | 2976 | 880 | 8 | 7040 | 4064 | 136.6% | 2080 | 4960 | 238.5%
Product | 12" Jacobs Plenum Box | 125 | 8 | 1000 | 385 | 8 | 3080 | 2080 | 208% | 1000 | 2080 | 208%
Product | Poly Pad Pre-Filters | 125 | 8 | 1000 | 185 | 8 | 1480 | 480 | 48% | 1000 | 480 | 48%
Product | Jacobs Duct | 40000 | 1 | 40000 | 40000 | 1 | 40000 | 0 | 0% | 23834 | 16166 | 67.83%
Product |  |  |  | 0 |  |  | 0 | 0 |  |  | 0
Product |  |  |  | 0 |  |  | 0 | 0 |  |  | 0
Install |  |  |  | 0 |  |  | 0 | 0 |  |  | 0
Freight |  |  |  | 0 |  |  | 0 | 0
| Sub Total |  |  | 155216 |  |  | 221200 | 65984 | 42.51% | 138154 | 83046 | 60.11%
LTL Freight |  |  |  | 0
LTL Freight |  |  |  | 0
Ocean/Inland Freight |  |  |  | 0
| Total |  |  | 155216 |  |  | 221200 | 65984 | 42.51% | 138154 | 83046 | 60.11%