## Sheet1
Customer | Boilermakers 04 |  | Avani Projected Costs |  |  | Avani Quoted Costs |  | Projected Profit |  | Actual Costs | Actual Profit
Date | 2015-04-13
Sales Rep | MWH
Rev# | 1
|  | Actual | Quantity | Total Cost | Quoted | Quantity | Total Quoted | Dollars | % | Dollars | Dollars | %
Product | SDC-AT-4-96 | 77802 | 1 | 77802 | 88920 | 1 | 88920 | 11118 | 14.29%
Product | Back Draft Inserts | 3584 | 24 | 86016 | 3230 | 24 | 77520 | -8496 | -9.877%
Product | SDT-5 | 4756 | 2 | 9512 | 0 | 2 | 0 | -9512 | -100%
Product | Duct-US Duct Rolled Lip | 50410 | 1 | 50410 | 16530 | 1 | 16530 | -33880 | -67.21%
Product | Project Management-Install* | 24000 | 1 | 24000 | 24130 | 1 | 24130 | 130 | 0.5417%
Product | SDC-AT-4-48 | 46036 | 1 | 46036 | 42370 | 1 | 42370 | -3666 | -7.963%
| Totals |  |  | 293776 |  |  | 249470 | -44306 | -15.08%
Rev.1
*Project Management Estimated
project management changed to install
Duct order revised-moved collectors on outside pads