## Sheet1
Customer | Boilermakers 502 |  | Avani Projected Costs |  |  | Avani Quoted Costs |  | Projected Profit |  | Actual Costs | Actual Profit
Date | 2015-05-06
Status | Complete
Sales Rep | M Halbert
SO # | 21714
Rev# | 1
|  | Actual | Quantity | Total Cost | Quoted | Quantity | Total Quoted | Dollars | % | Dollars | Dollars | %
Product | SDC-AT-3-36 | 38992 | 1 | 38992 | 46944 | 1 | 46944 | 7952 | 20.3939 | 38992 | 7952 | 20.39%
Product | Custom BackDraft Panels | 2625 | 16 | 42000 | 3345 | 16 | 53520 | 11520 | 27.4286 | 34320 | 19200 | 55.94%
Product | US Duct | 7057 | 1 | 7057 | 14856 | 1 | 14856 | 7799 | 110.5144 | 7926 | 6930 | 8743%
Product | Project Management* | 5000 | 1 | 5000 | 6413 | 1 | 6413 | 1413 | 28.26 | 5000 | 1413 | 2826%
Product | SPC-2810 | 2955 | 1 | 2955 | 0 | 1 | 0 | -2955 | -100 | 2138 | -2138 | -100%
Product | Install Hardware | 1523 | 1 | 1523 | 0 |  | 0 | -1523 | -100 | 1523 | -1523 | -100%
| **Freight | 7597 | 1 | 7597 | 10500 | 1 | 10500 | 2903 | 38.2125 | 7597 | 2903 | 38.21%
| Ocean Freight | [8 empty] | 6562 | -6562 | -100%
| Totals |  |  | 105124 | 82058 |  | 132233 | 27109 | 25.7876 | 104058 | 34737 | 33.3823
*5 days at $1K/day
** US Duct $1037, ACT 4560, Taiwan Products inland $2000
Rev.1- Added install hardware