## Sheet1
Project Analysis
Customer | Butler-Rosedale,PA
Date | 2015-07-23
Status | Complete
Sales Rep | MTC
SO# | 22345
Rev. # | 1 | Avani Projected Costs |  |  | Avani Quoted Costs |  |  | Projected Profit |  | Actual Costs | Actual Profit
|  | Actual | Quantity | Total Cost | Quoted | Quantity | Total Quoted | Dollars | % | Dollars | Dollars | %
Product | SDC-AT-3-24 | 31808 | 1 | 31808 | 39145 | 1 | 39145 | 7337 | 23.07% | 31808 | 7337 | 23.07%
Product | WB-1055 (Merchant 1) | 1585 | 18 | 28530 | 1995 | 18 | 35910 | 7380 | 25.87% | 28530 | 7380 | 25.87%
Product | ARM 1620 (Stock) | 332 | 18 | 5976 | 725.8 | 18 | 13064.4 | 7088.4 | 118.6% | 5976 | 7088.4 | 118.6%
Product | Bracket BR-006 (Triangle) | 35 | 18 | 630 | 78.85 | 18 | 1419.3 | 789.3 | 125.3% | 630 | 789.3 | 125.3%
Product | SDT-180 (SM) | 700 | 3 | 2100 | 1374 | 3 | 4122 | 2022 | 96.29% | 2100 | 2022 | 96.29%
Product | Spiral Duct (US Duct) | 14484 | 1 | 14484 | 26876 | 1 | 26876 | 12392 | 85.56% | 14484 | 12392 | 85.56%
| Plenum (Triangle) | 2800 | 1 | 2800 | 0 | 1 | 0 | -2800 | -100% | 2800 | -2800 | -100%
Product | Hardware | 59 | 1 | 59 | 0 | 1 | 0 | -59 | -100% | 59 | -59 | -100%
Install | Avani* | 32400 | 1 | 32400 | 17400 | 1 | 17400 | -15000 | -46.3% | 32400 | -15000 | -46.3%
Freight |  |  |  | 0 |  |  | 0 | 0 | #DIV/0! | 9000 | -9000 | -100
| Sub Total |  |  | 118787 |  |  | 137936.7 | 19149.7 | 16.12% | 127787 | 10149.7 | 7.943%
LTL Freight |  |  |  | 0
Ocean/Inland Freight |  | 1930 | 1 | 1930 |  | 1 | 0 |  |  | 1930 | -1930 | -100%
| Total |  |  | 120717 |  |  | 137936.7 | 19149.7 | 15.86% | 129717 | 8219.7 | 6.337%
*Install took 18 days