## Sheet1
SO # | 22594
Customer | Centrix LLC-Kent, WA |  | Avani Projected Costs |  |  | Avani Quoted Costs |  | Projected Profit |  | Actual Costs | Actual Profit
Date | 2015-05-06
Sales Rep | MWH
SO # | 22594
Rev# | 2
|  | Actual | Quantity | Total Cost | Quoted | Quantity | Total Quoted | Dollars | % | Dollars | Dollars | %
Product | A Smoke 40 Standard | 17076 | 2 | 34152 | 23771 | 1 | 47542 | 13390 | 39.2071 | 34152 | 13390 | 39.2071
Product | A Smoke 40 Stand | 626 | 2 | 1252 | 895 | 90 | 1790 | 538 | 42.9712 | 875 | 915 | 104.5714
Product | A Smoke 40 Stand | 265 | 2 | 530 | 0 |  | 0 | -530 | -100 | 530 | -530 | -100
Product | Control Panel (Boss 24volt) | 7281 | 1 | 7281 | 10995 | 90 | 10995 | 3714 | 51.0095 | 7281 | 3714 | 51.0095
Product | Ducting (need layout drawing to verify duct order)Quoted by Evergreen | 7925 | 1 | 7925 | 16650 | 90 | 16650 | 8725 | 110.0946 | 7906 | 8744 | 110.5995
Product | Installation Contractor | 13910 | 1 | 13910 | 21450 | 90 | 21450 | 7540 | 54.2056 | 14239 | 7211 | 50.6426
Product | Install option 1 or 2 (??) | Not applicable per MWH 3-13-15 | [6 empty] | #DIV/0! | 0 | 0 | #DIV/0!
Product | Freight (pd by customer) | YES | [6 empty] | #DIV/0! | 0 | 0 | #DIV/0!
Product | SDT-7.5 | 5452 | 1 | 5452 | 0 | 1 | 0 | -5452 | -100 | 5452 | -5452 | -100
Product | SDT-7.5 Top Fabrication | 875 | 1 | 875 | 0 | 1 | 0 | -875 | -100 | 875 | -875 | -100
Product | Transition | 160 | 1 | 160 | 0 | 1 | 0 | -160 | -100 | 160 | -160 | -100
Misc | Dealer Cost (5% ?) | 4921 | 1 | 4921 | 0 | 1 | 0 | -4921 | -100 | 4921 | -4921 | -100
Missing | Air & Electrical labor for Boss Blast Gates |  | 1 | 0 | 0 |  | 0 | 0 | #DIV/0! | 7281 | -7281 | -100
| Totals |  |  | 76458 |  |  | 98427 | 21969 | 28.73% | 76391 | 22036 | 28.85%