## Sheet1
Project Analysis
Customer | Medtronic Spinal-Humacao,PR | Avani Projected Costs |  |  | Avani Quoted Costs |  |  | Projected Profit |  | Actual Costs | Actual Profit
Date | 2015-07-01
Sales Rep | Ed Sithes
SO# | 22714
Rev. # | 1
|  | Actual | Quantity | Total Cost | Quoted | Quantity | Total Quoted | Dollars | % | Dollars | Dollars | %
Product | A-Mist 80TF | 17155 | 3 | 51465 | 26393 | 3 | 79179 | 27714 | 53.85% | 51466 | 27713 | 53.85%
Product | A-Mist 40TF | 9004 | 2 | 18008 | 13197 | 2 | 26394 | 8386 | 46.57% | 18008 | 8386 | 46.57%
Product | Mist Pump |  | 3 | 0 | 945 | 3 | 2835 | 2835 | #DIV/0! | 2791 | 44 | 1.576%
Product | Fire Dampers w/ceramic release |  | 9 | 0 | 185 | 9 | 1665 | 1665 | #DIV/0! | 454 | 1211 | 266.7%
Product | Control panel (start/stop) | 150 | 3 | 450 | 655 | 3 | 1965 | 1515 | 336.7% |  | 1965 | #DIV/0!
Product | VFD |  | 3 | 0 | 1695 | 3 | 5085 | 5085 | #DIV/0! | 4041 | 1044 | 25.84%
Product | Misc Mechanical Materials* |  | 4 | 0 | 755 | 4 | 3020 |  |  | 3020 | 0 | 0%
Product | Duct-Jacobs | 40566 | 1 | 40566 | 21568 | 4 | 86272 | 45706 | 112.7% | 59381 | 26891 | 45.29%
Install | Avani Install* | 38000 | 1 | 38000 | 12657 | 4 | 50628 | 12628 | 33.23% | 50628 | 0 | 0%
Freight | Ship collect |  |  | 0 |  |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0!
| Sub Total |  |  | 148489 |  |  | 257043 | 108554 | 73.11% | 189789 | 67254 | 35.44%
LTL Freight |  |  |  | 0
LTL Freight |  |  |  | 0
Ocean/Inland Freight |  |  |  | 0
| Total |  |  | 148489 |  |  | 257043 | 105534 | 71.07%
*Estimated