## Sheet1
Project Analysis
Customer | PPL-Hazel Township,PA | Avani Projected Costs |  |  | Avani Quoted Costs |  |  | Projected Profit |  | Actual Costs | Actual Profit
Date | 2015-04-09
Sales Rep | M. Connors
Status | Complete
SO# | 22531
Rev. # | 1
|  | Actual | Quantity | Total Cost | Quoted | Quantity | Total Quoted | Dollars | % | Dollars | Dollars | %
Product | SDC-AT-3-12 | 17277 | 1 | 17277 | 20617 | 1 | 20617 | 3340 | 19.33% | 17277 | 3340 | 19.33%
Product | WB-10000 | 2850 | 1 | 2850 | 5116 | 1 | 5116 | 2266 | 79.51% | 7680 | -2564 | -33.39%
Product | STX-1000E | 500 | 1 | 500 | 1000 | 1 | 1000 | 500 | 100% | 1100 | -100 | -9.091%
Product | Duct** | 1000 | 1 | 1000 | 0 | 1 | 4881 | 3881 | 388.1% | 1173 | 3708 | 316.1%
Install | Avani-Duct/ Kistler-StatX* | 7100 | 1 | 7100 | 6059 | 1 | 11463 | 4363 | 61.45% | 7651 | 3812 | 49.82%
| Sub Total |  |  | 28727 |  |  | 43077 | 14350 | 49.95% | 34881 | 8196 | 23.5%
LTL Freight |  |  |  | 0
LTL Freight |  |  |  | 0
Ocean/Inland Freight |  |  |  | 1382 | [5 empty] | 1382
| Total |  |  | 30109 |  |  | 43077 | 14350 | 47.66% | 36263 | 6814 | 18.79%
Install Cost=Kistler$2251
Install Avani = $5400