## Sheet1
| Project Analysis | [6 empty] | 2015-08-19
Completed May 2015
Profit
| Customer | Sales Order # | Install/Drop Ship | Sales Rep | Sales Order Total | Total Costs | Margin | Comments
| Boilermakers 502 | 21714 | Install | MWH | 132233 | 105858 | 26% | Act collector, Project Management and Booth panels under margin
| Boilermakers 92 | 21709 | Install | MWH | 195602 | 198221 | 9% | Install over run of $24,000
| Machining Technology | 22412 | Drop Ship | MWH | 82902 | 59414 | 40%
| Cubic-Bristol, CA | 22482 | Install-Not Avani | MWH | 18105 | 9565 | 89%
| A Berger | 22639 | Drop Ship | BS | 111000 |  | 53%
| Sterling Springs | 21509 | Install-Not Avani | FJ | 208250 | 128454 | 53%
| Horizon | 22685 | Install-Not Avani | MWH | 24928 | 14586 | 38%
Completed June 2015
Profit
| Customer | Sales Order # | Install/Drop Ship | Sales Rep | Sales Order Total | Total Costs | Margin | Comments
| Alcoa-Waco,TX | 22283 | Drop Ship | RK | 221200 | 138154 | 60%
| Butler Gas-Rosedale Tech, PA | 22345 | Install | MTC | 137937 | 120717 | 14% | Install over run of $15,000
| South Louisiana Comm College, LA | 22578 | Install | MTC | 74420 | 60628 | 23% | Install and Welding Booths under margin
| College of Charleston, NC | 22401 | Drop Ship | MWE | 28048 | 16792 | 77%
| Praxair-United Brotherhood of Carpenters | 22518 | Drop Ship | MWH | 13941 | 10381 | 43%
| Watterson-Kodiak HS | 22608 | Drop Ship | KB | 64687 | 38573 | 68%
| Randolph Comm College, NC | 22699 | Drop Ship | ME | 10026 | 4500 | 123%
| Randolph Comm College, NC | 23030 | Install | ME | 15488 | 16260 | -5% | Filters (40) under margin
| JR Auto-Mexico | 21418 | Install | ES | 64778 | 61820 | 5% | Equipment under margin
| SL Cooke-Peening Technologies | 22597 | Drop Ship | MTC | 6909 | 5259 | 31%
| Southside Va CC | 22941 | Drop Ship | KB | 14900 | 7600 | 96%
| Thomson Linear | 23021 | Drop Ship | Fj | 3809 | 2081 | 83%
| Microbial Discovery Group | 23010 | Drop Ship | MTC | 4805 | 2872 | 87%
C | Genpak | 22935 | Drop Ship | MTC | 4903 | 2013 | 161%
| National Machinery, Ohio | 22927 | Drop Ship | ES | 40059 | 30954 | 29% | low margin on absolent (31%), extra custom paint due to damaged absolent
C | AP Wyoming-Natrona HS | 22479 | Drop Ship | MH | 77573 | 46115 | 68.2% | no invoice for outside contractor yet
[5 empty] | MTD SO Total | MTD Costs | MTD Profit $
[5 empty] | 783483 | 564719 | 218764
[6 empty] | MTD Margin | 38.74%
To Be Completed July 2015
Status IP/C | Customer | Sales Order # | Install/Drop Ship | Sales Rep | Sales Order Total | Total Costs | Profit Margin | Comments
IP | Medtronics | 22714 | Install | ES | 257043 | 189789 | 35.44%
IP | Schaeffler Mexico | 22954 | Install | ES | 117373 | 86838 | 35.16% | waiting on cost of install
IP | Little Elm HS | 23077 | Drop/Ship | KB | 11804 | 4421 | 167%
[5 empty] | MTD SO Total | MTD Costs | MTD Profit $
[5 empty] | 1001219 | 723433 | 277786
[6 empty] | MTD Margin | 38.4%
Completed July 2015
C | San Bernardino | 22684 | Install | MH | 114000 | 98629 | 15.58% | products under margin
C | Pearson | 22720 | Drop/Ship | FJ | 73440 | 47170 | 55.69%
C | Allegheny/ATI | 22839 | Install | MC | 38221 | 34652 | 10.3% | ACT Collector under margin and labor cost over-run
C | American Truetzschler | 23008 | Drop/Ship | ME | 28830 | 16411 | 75.67%
C | Metform-McClean | 22800 | Drop/Ship | FJ | 127040 | 76078 | 66.99%
C | Kadon | 23097 | Drop/Ship | FJ | 7123 | 4289 | 66.08%
C | East Penn/Wann | 23100 | Drop/Ship | ES | 19057 | 14474 | 31.66% | only made 30% on Absolent A-Smoke 40B list is 21,730 we sold for 18,471
C | TRW Fuji | 23070 | Drop/Ship | ME | 1050 | 300 | 250%
C | Baldor | 22983 | Drop/Ship | ME | 44289 | 29352.75 | 50.89%
C | Bristol-Truform | 22828 | Drop/Ship | FJ | 11234 | 8595 | 30.7% | only made 30% on Absolent A-Smoke 20 list is 11,993 we sold for 10,194
C | Hoffman & Hoffman | 23073 | Drop/Ship | ME | 1536 | 230.4 | 566.7%
C | McClain Tool | 23017 | Drop/Ship | ES | 13078 | 9616 | 36%
C | Thyssenkrupp | 23066 | Install | FJ | 28202 | 18861 | 49.53%
C | Thyssenkrupp | 23043 | Install | FJ | 2816 | 1409 | 99.86%
C | Airgas/PPL | 22531 | Install | MC | 43077 | 39112 | 10.14% | Act Collector and Taiwan Booth under margin
C | McCown Gordon | 22864 | Install | ES | 123396 | 71884 | 71.66% | Install not complete 7/31/15, may incurr additional install costs
C | Plumbers and Pipefitters | 22152 | Install | MTC | 366183 | 273500 | 33.89% | Install not complete 7/31/15, may incurr additional install costs
C | Ecolo Tech | 23148 | Drop/Ship | FJ | 12896 | 8627 | 49.48%
C | The Timken Company | 23139 | Drop/Ship | ME | 8262 | 4828 | 71.13%
[5 empty] | MTD SO Total | MTD Costs | MTD Profit $
[5 empty] | 1063730 | 758018.15 | 305711.85
[6 empty] | MTD Margin | 40.33%
To Be Completed August 2015
IP | Boilermakers 242 | 21711 | Install | MH | 77077.3 | 80874 | -4.695% | estimated
IP | Boilermakers 04 | 21712 | Install | MH | 249470 | 339239 | -26.46% | estimated
IP | Spartanburg | 23074 | Install | ME | 86859.25 | 60334 | 43.96%
IP | Groathouse | 21517 | Install | KB | 94203 | 65923 | 42.9%
IP | 3m/ Airgas | 22932 | Drop/Ship | RK | 13100 | 7285 | 79.82%
IP | Construction Gely | 22955 | Drop/Ship | KB | 10252 | 7642 | 34.15%
IP | Centrix | 23197 | Install | MH | 21733.96 | 14421 | 50.71%
IP | Duke | 23078 | Install | ME | 4536 | 2896 | 56.63%
IP | Thyssen Krupp | 23167 | Install | FJ | 9995 | 7141 | 39.97%
[5 empty] | MTD SO Total | MTD Costs | MTD Profit $
[5 empty] | 567226.51 | 585755 | -18528.49
[6 empty] | MTD Margin | -3.163%
Completed August 2015
C | General Dist. Helena, MT | 20799 | Install | MC | 55958 | 68864 | -18.74%
C | Boilermakers 92 | 21709 | Install | MH | 207602 | 198221 | 4.733%
C | Boilermakers 502 | 21714 | Install | MH | 132233 | 104058 | 27.08%
C | Georgia Power/RCN | 22984 | Drop/Ship | KB | $28,171.00 | 20835 | 35.2%
C | Little Elm HS | 23077 | Drop/Ship | KB | 11804 | 4421 | 167%
C | Doosan | 21920 | Install | ES | 232099 | 178684.43 | 29.89%
C | Hennessy | 23195 | Drop/Ship | CS | 244.8 | 146.88 | 66.67%
C | Petron | 23136 | Drop/Ship | ES | 2437.71 | 1377 | 77.03%
C | Dubose | 23196 | Drop/Ship | ME | 4167.65 | 1611 | 158.7%
C | Thyssen Krupp | 23115 | Install | FJ | 16000 | 11077 | 44.44%
C | Thyssen Krupp | 23119 | Drop/Ship | FJ | 27456.5 | 18700.5 | 46.82%
C | Triangle Engineering | 23086 | Drop/Ship | MC | 895 | 529 | 69.19%
C | Boilermakers Local 37, LA | 22959 | Drop/Ship | CS | 3396 | 1260 | 169.5%
C | Custom Mechanical Alaska | 22934 | Drop/Ship | KB | 12638 | 6902 | 83.11%
C | Stackpole International | 22974 | Drop/Ship | BS | 22480 | 14125 | 59.15%
C | Delaware CC | 23022 | Install | KB | 43335 | 33360 | 29.9%
C | Pure Power | 23202 | Drop/Ship | ME | 74.82 | 75.78 | -1.267%
C | McClain Tool | 23221 | Drop/Ship | FJ | 297.5 | 60 | 395.8%
C | Cal City | 22916 | Install | MH | 293616 | 244927 | 19.88% | Underquoted the Taiwan booths-Landed cost
C | Barnes | 23166 | Drop/Ship | FJ | 12860 | 7712 | 66.75%
C | Kennemetal PA | 23246 | Drop/Ship | MC | 6959 | 4040 | 72.25%
C | Erwin Junker | 23208 | Install | ES | 30450 | 34040 | -10.55%
[5 empty] | MTD SO Total | MTD Costs | MTD Profit $
[5 empty] | 1117003.98 | 955026.59 | 161977.39
[6 empty] | MTD Margin | 16.96%
To Be Completed September 2015
IP | LEE college | 22601 | Install | RK | 367382 | 277374 | 32.45%