## Installs
Order Date | Reps | SO # | SO Total | Customer | Contact | NET TMS/DEP | Scope | Rqustd Ins Date | Confirmed Delivery Date | Scheduled Install Date | Pending
2013-06-21 | MC | 20072 | 74210 | SW Texas JC TX |  | YES | Fan, Concete Pad, 38 arms, brackets |  |  | 2/9/15 Eric to call to clarify duct work 2/19 short brackets and stands. 2/23 richard king is getting a quote for shortages.Cust. DISPUTING LOSS! 2-23-15. 3/2 eric is meeting with pontus. | 3/9 eric submitted loss,3/18 customer quoted. Still have not paid ($25k). RK to call 4/23
2013-10-24 | FJ | 20550 | 39425.2 | Truform- McClean Fog, IL |  | yes | AB-Smoke 40, jacobs duct, control panel | Not Avani | 2014-01-31 | Engineer on site wants to change layout, Bob Zill to Install | 4/17 A moke 40 units. per hal /daniel Fred will be gettng back to him
2013-12-26 | MC | 20799 | Invoiced | General Distributing, MT |  |  | SDC-30-16MD,duct,arms,silencer | pend pad | 2/24/14 collector | all collectors, arms,on site(need revised duct order after dwg approval) | 3/9 Waitng for pourig on concrete pad and then daniel duct order needs to be modified on concrete pad.ground is frozen will be a while. Mike emailed regarding misunderstanding on who is paying for union install
2014-04-30 |  | 21379 | 63869 | H B Construction/ Bernalillo H S NM | MikeH@hbconstruction.com cell (505) 377-3731 | NET 30 | SDC-AT-5-20/ Duct/ WB-1044(9), ARM-1620(9) | 2015-11-01 |  | 2015-11-01 | cust needs in Nov of 2015, need duct sketch
2014-06-10 | KB | 21517 | 92830 | Groathouse-Roosevelt High, WY | wkitchen@groathouse.com | no | Grinding Booth W/doors & rear mount collector (2) WB-1055 (18) 1620 Arms (18) | 9/2015 contract install | construct booths and install arms only | Sept. 2015 sheet metal specialties, 3/30 new contact is Wayne Kitchen | Groathouse contracted SM specialties for instal and duct. We are not paying for install labor or duct. Only send crew to construct booths and install arms.2 Custom GB with “front doors” and “rear mount collector” The submittal with the rear mount collector had 1 front door (sliding).4/6 still working on drawings. 4/9 per Chaz July delivery for the booths
2014-07-25 | MH | 21709 | 195608.8 | Boilermakers Bloomington CA Local 92 | Mark Thomas mstbm92@gmail.com | yes | SDC-AT-5-20, 16 booths, duct, collector stand | 2014-12-01 | PM only | ACT shipped 2nd dust collector 3/4 | Pending stand PE stamp. 4/17 install 4-23-4-30, 4/24 all duct delivered
2014-07-25 |  | 21711 | 77077.3 | Boilermakers Spokan WA Local 242 | Mark Keffeler bm242@aol.com | yes | local 242 | 2014-12-01 | not our install manage only | Waiting on Drawing approval before ordering duct. Connect to the existing square duct! 2/23/15 | system in port 11/20 ACT ship before 10/31. 4/17 KB quote done we need to order
2014-07-25 | MH | 21712 | 249470 | Boilermakers Page, AZ Local 04 | Casey Tibbs, utahcasey79@hotmail.com | yes | local 4 | 2014-12-01 | Customer wants full install | need to adjust duct order | 3/9 eric will meet with Ed pontus on 15000.00 price increase. Daniel and bill working on drawing
2014-09-19 | ME | 21946 | 12645 | GTTC Gilford tech 2014-2015 | ssaunders@gtcc.eduPH# 336-334-4822 ext 59020 | yes | 4 installs annually | 2015-05-04 |  | 1/23 issued 2 po's. | installation will be April
2014-05-13 | ES | 21986 21418 | 52847.94 | JR Automation |  | yes | SDC-20-16MD, RM6000N,duct, silencer | install in Mexico |  | 1st week of JUNE Bill, Jason, Don. 3 days Wilmington 10/2, duct and transitions ship from MI 5/8/2015 | Bill completed drawing and sent to Darren(PM) 3/17 Per Darren reschuedule duct del until 1st week in June Should be closing in june. 5/6 need to resolve issue of roll media before shipping. cust wants updat of refund for roll media
2014-10-17 | ES | 22050 | 6084.05 | Spanda Indust Development Sacramento CA |  | 1st/ 2nd dep | Welding booth 5 gas/ air lines, 15 Curtains, 5 mting brackets,5 collector SDC 10-6, 1 silencer, 1 duct | 2014-12-29 |  | act delivered 4/9 | Collector due on Site 4/6 change requires more duct. Daniel to produce duct quote. Installation sched for 4/16
2014-11-10 | MC | 22152 | 366183 | Plumber and Pipefitters Landover MD | Tim Haley plumber.school@verizon.net | yes | Act collector, customer welding booths( 1) Premier Welding booths (20)Welding Booth w/hood (2)duct SDT 3(4) | 2015-07-03 |  | FIRST PAYMT MADE , 2ND DEPOSIT MUST BE PAID BEFORE SHIPMENT.2/19-May want custom only have several here. | 2/9 MADE IN THE USA 3/26 pending 10X12 booth drawing from tia 4/8 eta from taiwan mid july. installed the first week in June.
2014-12-02 | MH | 22233 | 126064 | Chevron-Richmond, CA |  | yes | (8) WB 1066, (1) SDC-at-3-12, (8) 1020 arms, (8) custom hoods spiral duct | 4/9/2015 Pend potential strike | No deposit required |  | 3/16 all on site except curtain rods. Install pending next order.3/31 ed willl give us update. 4/17 mention of seismic, install date pending customer
2015-02-03 | MH | 22482 | 18104.84 | Cubic Machinery / Bristol | melanie.antunes@cubicmachinery.com | YES | AB-A Mist,duct | 2/18 rcvd 1st dep |  | Cubic doing install | Contract installer req higher elevation for latteral connections 4/6 client wants renovations. Layout is changing per customer will be ECO
2014-09-12 | ES | 21920 | 1374419.13 | Doosan- Intl. Mexico |  | yes | Absolents, Ed to PM | 2015-03-30 |  | Shipments eom Jan/April/July/Oct | Order placed 3/11, received another order for 5/2015 del 4/8 more deliveries going out. Customer changing layout. No more legs. Pend duct and Bill to redraw
2014-12-30 | MC | 22345 | 39145 | Butler- Rosedale pittsburg PA |  | yes | SDC-AT-3-24, (18) WB-1055, WB to made in US, (18) arm 1620 | complete by 4/1 | 2/20 SO changed from drop ship to install. | per candi merchant 1. PO 10408 pick up DELAYED TO 3/19/15 | 3/9 drawing done. 3/9 drawing approved3/16 daniel adding 28" sleeve 3/17 picking up 8 more booths. Duct del 3/17- 3/30 more duct del.4/17 tables and light kits.4/17 per chaz The tables are estimated to arrive here the first week of June.
2015-02-20 | ES | 22545 | 87000 | Erwein Junker/Feurer Powertrain | info@junker-usa.com 847-488-0406 | NO | Month long duct install | 2015-04-09 |  | waiting on duct drawing from jacobs/ they will get with us | april 7 install date 3/2. Daniel to provide grippl pictures/directions 4/17 per Eric order has been revised don’t do anything with this yet.
2015-02-12 | MC | 22531 | 32791.5 | PPL/Airgas | Ron.downing@airgas.com, arthur.crochetiere | NET 30 | SDC-AT-3-12, WB10000, AE-1000 statX, contract statX install |  | StatX contract install ONLY | 3/17 It was scheduled to ship 3/20 but it looks like now it will be ready on 3/18. per CB | 3/24 per connors "We have some issues that need to be resolved with the location…I will keep you informed." 4/8 mike conners needs to update us.4/17 hal will udat us next week
2015-02-24 | KB | 22578 | 74420 | South Louisianna Comm Coll | 337-521-8898 | NET 30 | (40 WB, (40) curtains | ? | 2015-05-13 | states “30 opening”, “Primer red powder coat”, “11gauge panels”, “1/2” thick 14”DX40”WX36”H table”, “weld positioner”, and “2 rod holders”. | Appr eta for draft table/booths may 2015. 3/30 Per Eric location of the weld positioner, table, and rod holders is not defined. 5/4 40 booths will ship 5/8 new contact nicole.manuel@solacc.edu also Lisa Dupois 337-521-8905
2015-03-03 | RK | 22601 | 352442 | Lee College | mboyd@bartlettcocke.com, willie.smith@solacc.edu | NO | (90)WB-1056, (90)SPC-2807,(90) Curtains, arms (90) arms, (90) light kits,(1) SDC-AT-4-48, (1) Dust Collector, install | 2015-06-15 | 6/15 in port | 3/19 hold pending deposit,4/2/15 WO done for SPC-2807 | for 90 custom WB-1056 but the customization isnt clearly defined. I discover a spec for an 18”D fixed rear shelf. We need to follow up with the customer to nail down custom specs custom booth submittal sent to RK 3/26. 4/8/ per eric requested del date is ~6/15 but booths won’t be ready for container until 6/4
2015-03-04 | MH | 22594 | 99900 | Centrix LLC | tia.gilberts@centrix-llc.com | YES 1st and 2nd | AB-A Mist,duct, BOSS control panel, stand,SDT-7.5 installation | 3/19 dep rcvd | 3/30 per Chaz order a | 3/23 Drawings sent for approval. 3/27 absolent will ship 5/20. 3/30 per chaz we are ordering the SDT-P-10 and taking out the SDT-7.5. | 4/6 per chaz email I do need the fan outlet flange dimensions as we need to duct the exhaust out the building. We closed the job based on the mist unit being in stock. 4/17 table top from robbie will be next week
2015-03-18 | mh | 22685 | 19390 | Horizon MFG Industries | john@horizonman.com | yes | Mist 40TF,duct control panel CP-SS-10, installation |  |  |  | 4/22 AB mist will ship 5/18, duct shipping 4/28
2015-04-02 | ES | 22748 |  | Johnson Controls |  | no |  |  |  |  | 4/2/15 incomplete order per cheryl waiting for all the correrct info. Items ordered from tiawan 4/2
2015-04-01 | es | 21247 | 0 | National Machinery-Tiffin, OH |  | N/A | AB-smoke,duct | demo |  | 4/1 Per Ed no charge, eric got email that cust is supplying duct?
2015-04-14 | ES | 22714 | 257042 | Medtronic PR | edwin.marrero.nievs@medtronic.com | net 60 | ab mist 80tf,(3)ab mist 40tf(2),mist stop(3)fire dampers(9) control panel(3) vfd frequency(3)drive, duct(4) |  |  | 4/29 rcvd adapters and VFS15 | 4/17 daniel doing re-drawing
2015-05-01 |  | 22884 | 2924 | Rosedale Technical/Butler gas |  | no | Air Diverters (2)
Total |  |  | 3713892.76
2014-05-01 |  | 21360 | Invoiced | CareFusion |  |  | Training in Mexico-Bill

## Drop ships
Order Date | SO # | REP. | Total | Company Name | Contact | NET TERMS /DEP | Scope | Requested | Ship Date | Pending
2013-04-24 | 19838 | MH | 0 | Watterson-WA KODIAC HS | Shawn Morgan smorgan@wccak.com | YES | (18) booths, arms, led lights | On site June 1 2015 | 3/2 chaz ordered for drop ship.booths changing from 1054 10 45 ask chaz for date. 3/31 questions on arm lights | 4/17 per shawn cust still wants booths on site by June 1st. 4/23 booths on container. Customer to pick up container from port? What port? Invoice upon shipment? 4/23 sent chaz all shipping info
2014-06-10 | 21509 | FJ | 208250 | Sterling Springs IL |  | YES | install b. zill/ fan ordered 7/16 dust collector 7/25/2014 | not our install multiple installs |  | we have installed and piped 12 of the 16 grinders. The customer expects to have the remaining grinders in the plant by 4/30/15
2014-10-23 | 21849 | BS | 28954 | RB&W Canada second order frm Sept |  | YES |  | customizing 575 vlts | not our install Tin knockers duct del 1/21 2/10 rcevd liability and quote | 4/16 more duct del 4/17. 4/16 candi ordering a 2- 24 volt for motors being airshipped from sweden. 4/29 2-24v will ship 5/4
2014-12-10 | 22283 | RK | 221040 | Alcoa-Waco TX |  | YES | A Smoke 40B (8) Stands, Plenums, poly pad filters, duct | 2 del 1/14, 6 del 12/29 |  | 4/14 spoke with RK 5/1 Hal doing drawings
2014-12-19 | 22317 | ES | 111313 | McCownGordon Construction- Kansas City, MO |  | NO | (6) WB5087 (1) wb5088 (1) GB5088 (2) SDT-3 Installation-Outside Contractor |  | PEND DEPOSIT | 4/17 cust still reviewing drawings and still no dep. Booths are appr. Eric will get with pontus
2015-01-16 | 22401 | ME | 28048 | Coll of Charleston-Charleston,SC |  | NET 30 | SPC-800 (2) 1020P (4)SDT-2 Customized (3) |  | 5/1 filters for booths here tagged | 3/2 been app kirk about table tops and del date in april. 4/6 San Moa ordered 3/5/15. 4/17 jo let customer know about May del.
2015-02-03 | 22479 | BS | 71223 | AP Wyoming | 30-426-4242 jhaass@a-p.com David Jaeger <davidjaeger@a-p.com | no | Grinding booth TMC ,WB-1055,Arm 1620,Br006, XA Weldng curtin |  | 4/17 no 1st dep | Why no duct? Contract install 3/30 eric emailed AP Wyo asking if they are ordering GB with no collector, and standard WB’s.submitted new booth drawings 3/31. kirkwill discuss lead times
2015-02-09 | 22518 | ENG | 11876 | Praxair | tim_sinderson@praxair.com | yes | WB-1055C, curtain,2 arm1620 ,duct, ECO2000 |  | w/o done for ECO2000,W/O done for arm,bracket,filter Duct drawing approved 3/16 3/9 waiting for dep. | 4/29 rcvd dep
2015-01-19 | 22412 | MH | 114815.3 | Machine Technology-Auburn, WA |  | YES | A Mist 40TF (2) A SMoke40 (2) paint Duct, Install outside contractor |  | 2/9 dep received, pend duct approval, 3/31 absolents ship 4/14 at the earliest | Absolents sched to ship 4/14 Stands shipped 4/14. 4/21 k&b will deliver 4/29
2015-03-02 | 22598 | mc | 6909 | SL Cook CO |  | NET 30 | SDC-3D-1,HEPA FM3-1 |  |  | taiwan order was plced 3/3 will del june. 4/21 left message with cust about ship date.
2015-03-09 | 22639 | BS | 111000 | A. Berger Precision | matthew.cheung@aberger.com | YES | AB-smoke,duct, 5 stands | invoiced 3/9 | 2015-05-11 | 3/13 per Lotta will ship 5/11. 3/19 rcvd first deposit per eric stands will be 5/11
2015-03-20 | 22696 | MC | 14000 | Regency Sales | Ray Roman 216-901-9202 | NET 30 | Robo-40 | 2015-03-27 |  | unit painted, need 1 tray with traps, pulse valave are being relocated strap will be airshipped from taiwan due at AVANI 4/29
2015-04-22 | 22845 | MC | 13129 | Regency Sales/John /Bean Tech | Regencysales@ameritech.net | net 30 | SDC-5-4,Eco 3000, crate |  |  | 4/29 per eric will order hood
3/20/22015 | 22684 | MH | 114000 | San Bernardino | Ed Sanker 909-384-4400 esanker@valleycollege.edu | NO | WB-6066 (6), curtains (6),Top mount Dust collector (6), Eco-300 (1) |  | NEED 1ST DEP. | 3/20 per MH taiwan lead time ok, Demos are part of package, pend duct sketch 4/6, 4/17 eric reminded mh
2015-03-27 | 22720 | FJ | 88950 | Pearson Construction/prison | Jwing@pearsonconstruction.com | yes | WB-DL-6066.54, custom,ship (loc-tite 272) | 2015-05-05 |  | 4/21 taiwan will ship WB 6/11
2015-03-16 | 22669 | KB | 10025.9 | Randolph Comm College | Sharon Reynolds 336-633-0234 | NET 30 | SDT-3, upgraded to SDT-5-FT with 6" arm and casters |  | 2015-04-30 | 3/23 bill quoted filters, drawing approved, casters ordered on different sales order, eta for SDT-5FT mid June
2015-03-31 | 22737 | ME | 271.34 | Randolph Comm College | jrallen@randolph.edu | NET 30 | caster set for custom SDT 5 table (set of 4) | 2015-06-15 |  | 3/31 This goes with SO 22669 Taiwan order 14 wks 3/17 per chaz taiwan to ship out Mid May for install early June.
2015-03-31 | 22742 | MC | 6213 | Adena Corp | Gguttenberg@adenacorporation.com | yes | WB-1043.5 (3) curtains (3) |  | 2015-05-06 | 4/6 Booth drawing appr. 4/14 WB will ship 5/6
2015-04-13 | 22797 | ES | 7991 | Gosiger | jill.duff@gosiger.com | net 30 |  |  |  | 5/5 candi is getting tracking for me then close
2015-04-14 | 22800 | FJ | 108880 | Maclean Fogg |  | NO | AB smoke(4),Stands (4), duct (4) |  |  | 4/17 hal/daniel working on drawings. Absolent ordered. 4/17 per eric 6 week lead time for stands
2015-04-15 | 22803 | FJ | 7420.93 | Security Locknut | sln01@securitylocknut.com | net 30 | AB-Smoke, arm,duct |  |  | 4/16 daniel working on drawing.4/17 absolents ordered.4/30 fume arm del.
2015-04-17 | 22828 | fj | 11234 | Truform Equipment/Bristol | jschanks@truformequipment.com | no | AB-A Smoke 20, control panel |  |  | 5/4 per Ed/Eric release absolent. Candi to release today
2013-04-21 | 22832 | MH | 16816.75 | Senior Aerospace | tclark@seniorssp.com | no | SDT-5,silencer,FM-20235,fm-s-30242, customised sdt-5
2015-04-23 | 22851 | FJ | 1560 | Barnes |  | net 45 | duct
2015-05-01 | 22885 | MC | 600 | Clark Air Systems |  | net 30 | fire dampers (4) |  |  | 5/4 Jon will have done by the 5/8
2015-05-04 | 22890 | ME | 10773 | Airgas/Gala Industries | 770-590-6200 | net 30 | SDT-7.5, FM-s-20100
Total |  |  | 1325293.22
2015-02-05 | 22510 | FJ | 0 | Ecolo- Tech | 248-541-1100 ecolotechinc@yahoo.com | demo | 90 day demo unit |  | 2015-02-18 | delivered 2/25 revisit May 25th
2015-01-19 | 22417 | FJ |  | MacLean Fogg-Savanna, IL |  | demo | Amist 6C,24 prefltrs w/frames,1 set flanges | closed 3/27 |  | 3/23 closed. Item delivered 3/5 60 day demo send invoice 5/5/15

## CASES
open internal case # | REP | Open Date | CASE # | SO # | Product | Serial # | Stopped production | Company Name | Issue | Warr | Status | Pending | Root cause | Short term resolution | Long term resolution | closed | Hours | Freight | Flight | Hotel | Outside contractor costs | parts
|  | Currently 11 open warranty cases | Currently 4 pending cases |  |  | Currently 30 closed warranty cases |  |  | 35 total warranty cases for 2015
10 | RK | 2015-03-03 | 1532 | 22056 |  |  |  | Airgas Torcsill | duct shortage (1) 8" 54, (4) 8" pipe, (2) 8" slip, 8" clamps | yes | Items staged in Engineering cube. Ship with next order per RK | 3/5 per eric items that need to ship will go with new PO for an arm and hood when submitted. 3/23 eric holding order
26 | BS | 2015-04-07 | 1554 | 21948 |  |  |  | RB&W | Motor Is correct voltage (575) but display controller is 460/240V | Yes | 4/29 24 v will ship 5/4
27 | mc | 2015-04-07 | 1555 | 22345 | ARM-1620 |  |  | Rosedale/butler gas | 3 arms have wrong/weak flex hose and no avani decals | Yes | pend CS order from Taiwan to ship with Rosedale SDT180s | 4/20 Chaz ordering hose for 3 arms will be here from taiwan with SDT180. also need decals
30 | mc | 2015-04-16 | 1561 | 22445 | wb,tables |  |  | Veritas | scratches on WB, shorted shipment 2 tables | yes | Cust. To quote repaint. Tables to ship 4/22, M1 to supply paint also | 4/23 waiting on quote from veritas to subtract the amount of money to repair booths.5/4 per eric/CB waiting on paint for booths | Vendors mistakes
31 | BS | 2015-04-16 | 1565 | 20806 | control panel |  | no | Toshiba/honda | trouble with control program | yes | per Chaz Problem with control panel may be under COMPLETE AUTOMATION RESOUCES WARRANTY. will now more 4/24/15 | Don and Brian Rode to visit 4/23. 5/6 per Don do not close yet.
32 |  | 2015-04-17 | 1556 | 22364 | SPCmini | 150619 |  | Step PLUS | Brushes & commutator burned | yes | Don asked San Mao to send replacement brushes, customer wants new motors. | We have just installed a sanyo laser lithium march of 2015. 5/4 don checking w/taiwan for shipping info
33 | MC | 2015-04-27 | 1597 | 22531 | WB10000 |  |  | PPL | Paint booth | yes | We ordered/sent the wrong booth. PPL will use the booth they have now until we get new booth from taiwan, at which time we will also install.
34 | ES | 2015-04-27 | 1596 | 22759 | jacobs duct order | NA |  | National machinery | Duct painted wrong color, pant RAL 7035 per SO | yes |  |  | wrong RAL on SO | issue credit | [7 empty] | 218.68
35 | AV | 2015-04-28 | 1598 | 22853 | filter order |  | no | Commercial metals | wrong filters sent, being returned sending new ones | yes | [6 empty] | 1 | 12 |  |  |  | 395.25
36 | DM | 2015-04-30 | 1606 | 22314 | switch |  | no | napotnik welding | broke in shipping | yes | shipping out the same day. This was stocked |  | shipping |  |  |  | 1 | 15 |  |  |  | 175
37 |  | 2015-05-01 | 1608 | 22066 | hepa fliters |  | no | vegas fastensers | warning lights on filters lit | yes | 5/1 shipping next week | [10 empty] | 610
| PENDING | CASES | [5 empty] | PENDING
|  | 2015-03-24 | [5 empty] | JR Auto | return/refund cell 1 & 2 roll media |  | emailed Ed
|  | 2015-02-19 | pend |  |  |  |  | Johnson controls | install of 6 roll media (pending ed meeting with TY) in michigan, different transitions, from tiawan, change gears on prototype Customer claims 6 roll media, not 3 | YES | do not open case for 15 weeks | 2/19 Drawings from Taiwan, approval, 12-15 weeks lead,3/2 per eric wll need to be installed (6) RM6000 in battle creek michigan
| FJ | 2015-03-19 | Pend |  | Scientific collector |  |  | Sterling Spring | MANY Pulse valves stuck Working valves= 1,2,3,4,5,6,7,8,9,10, 11,12, 13,14,16,18,19,22,23. Valves not pulsing= 15,17,20,21,24,25,26,27,28,29,30,31,32 (some pulse a small amount, 3 or 4) | 7-2014 begun service | F. Johnson emailed mgerardi@scientificdust.com | 4/7 sent MC email for update
|  | 2015-02-25 | [5 empty] | Ventaire | SPC750 wont run continuously | NO |  | 3/2 eric contacting
| Done | Done | Done | Done |  |  |  | Done | Done | Done | Done | Done |  |  |  | Done
|  |  | n/a | 22344 |  |  |  | Clayton |  | not a case |  | We made a bagde. 2/18 don is taking care of |  |  |  | closed | 1
2 | ES | 2015-02-11 | 1514 | 21442 |  |  |  | CMC Alamo | SDC-15-16 no pulse control | yes | Ordered control from taiwan | 3/3 per chaz will ship 3/6 air. 3/9 shipping |  |  |  | Closed | 1 | 10.04 |  |  |  | 175
3 | MC | 2015-02-19 | n/a | 21468 |  |  |  | PA rail car | Master duct too small | yes | Closed | 3/6 delivered 9"flex 10' long close |  |  |  | Closed | 2
4 | MC | 2015-02-24 | 1518 | 21004 |  |  |  | Norfolk Southern | SPC- 1000 making a loud noise | yes | Where is the SPC? | delivered fed ex track#342823429-4 |  |  |  | Closed | 1
5 |  | 2015-02-25 | 1520 | 22527 |  |  |  | Welding alloys | RL Flange adapters hole pattern doesn't match his SBU-3 | Yes |  | 3/19 sent email to adam to see if he was sending back to us? Per adam took of issue in house |  | Re-drill holes |  | closed | 1
7 | MC | 2015-02-18 | 1516 | 22192 |  |  |  | Brennan Environ/sig sauer | Worn brushes | Yes |  | shipped 3/3 |  |  |  | closed | 2
8 | MC | 2015-02-19 | 1517 | 22170 |  |  |  | SIFCO ASC | needs replacement telescoping arm spring | yes |  | 2/5 don submitted packing list for spring. 2/25 don shipped sprng |  |  |  | closed | 1
9 | bill b | 2015-03-04 | 1531 | 3 s/o's |  |  |  | Barnes | transitions not welded that barnes fixed |  |  | gave to brittany to issue credit. |  |  |  | Closed
|  | 2015-02-26 | 1521 | 22319 |  |  |  | National Machinery | 2 sets of decals | yes |  | ups tracking 1Z82A9630492866250 |  |  |  | closed | 4
13 | MH | 2015-03-09 | n/a |  |  |  |  | Neumeier | Broken light on side wall of booth | Yes | Only the tube, sending picture. |  |  | Pulled light tube from salvage and cut to fit | Keep inventory of 1 4' light tube | closed | 1
19 | KH | 2015-03-03 | 1527 | 22196 |  |  |  | Hagemeyer | cust. Rcvd 2 right booths from stock in our warehouse | Yes | [5 empty] | Closed | 1
20 | ES | 2015-03-02 | 1528 | 22066 |  |  |  | Vegas Fasteners | Short SPC2k, ARM1630P, 2 manual starters, return duct Filter light on | yes | SPC-2000 del 3/10 | 3/10 ducts inc approved, given greenlight |  |  |  | Closed | 2 | n/a |  |  |  | 1800
21 | KB | 2015-02-05 | n/a | 22033 |  |  |  | Southern career institute | Control buttons damaged in shipping | yes | [5 empty] | closed | 5 | 11.85
22 | ES | 2015-02-12 | 1515 | 22319 |  |  |  | National Machinery | Damaged in shipping | Yes |  | 2/25 tom em painting himself |  |  |  | closed | 4 | 9.4 |  |  |  | 30
17 | AV | 2015-03-19 | 1543 | 22628 | FM-S116N1 |  | no | Harger Lightning and Grounding | Filter was sent without frame | yes | 3/19 Allana ordered wrong filter new one shipped | 3/23 filter will del 3/24 fedex 773174357658 |  |  |  | 2015-03-25 | 1 | 29 |  |  |  | 80
18 | MC | 2015-03-23 | 1544 | 21468 | ECO-2000 | 114506 | no | PA Rail car | ECO-2000 no gauge, eco 3ooos want gauges relocated | yes | eric got them to relocate gauges | 3/23 need to ship gauges and panels this week | 2 year old product shipped to customer without being updated to current | install gauge |  | 2015-03-26 | 1 | 10.92
11 |  | 2015-03-06 | 1534 | 22078 |  |  |  | Freeport Mcmoran | VFD tripping OVER HEAT, Jacobs duct leaking, Absolent gauge pegged | yes/not our case | Complete AR sent new VFD, contractor to fix duct. To be completed 3/23, need absolent serial # to issue warranty PO for new monitor | 3/23 Repair for leak done. 3/30 email for tracking on controller from absolent. No cost to us |  |  |  | 2015-03-31 | 1 | n/a |  |  | 1230.07
8 |  | 2015-03-03 | 1529 | 22316 |  |  |  | ELG Utica Alloys monroe NC | No spark trap on collector, shot blaster port left open. | yes | Quoting dampers and traps | closed 3/31 |  |  |  | 2015-03-31 | 3 | n/a |  | 4/6 candi checking for rental rates | 252
n/a |  | 2015-02-11 | 1511 | 20894 |  |  | no | alcoa | hepa filter | yes | [5 empty] | 2015-04-01 | 4 | 711 |  |  |  | 2000
6 |  | 2015-03-04 | 1522 | 21930 |  |  |  | Airgas great lakes White Wave Food | customer claims item sent is wrong rec plenum vs round. | yes | plenum box del 3/16 track#773092693113 | 3/16 per Eric- daniel can contact cust to explain how this works.3/18 daniel call 2x cust did not call back |  |  |  | 2015-04-02 | 2 | 9.39 |  |  | 305 | 135
24 | AV | 2015-03-31 | 1549 | 22663 | FM-20252 |  | no | PCB Piezotronics NC | Return Damaged folter and send new one | yes |  | 3/31 packing list done |  |  |  | 2015-04-06 |  | 18.08 |  |  |  | 250
25 | MC | 2015-03-31 | 1551 | 22598 | 6" hood |  | no | Regency Sales | Hood damaged in shipping per chaz send another we pay for shipping | yes | [5 empty] | 2015-04-06 |  | 17.18 |  |  |  | 189
30 | BS | 2015-04-13 | 1559 | 22267 | lateral |  |  | honda of canada | wrong size | yes | [5 empty] | 2015-04-14 |  | 107.63 |  |  |  | 256
28 | BS | 2015-04-13 | 1558 | 19057 | starter |  |  | airgas | bad starter | Yes/demo | per don need case, shipping 4/13 |  |  |  |  | 2015-04-14 |  | 11.82 |  |  |  | 120
1 | ES | 2015-02-10 | 1512 | 18625 |  |  |  | JCC | Silencer leaking | yes | Robbie to modify, daniel to install Tuesday | silencer needs to br rework daniel will go 4/7 |  |  |  | 2015-04-22 | 6 |  |  |  |  | 60
23 | MH | 2015-03-30 | 1548 | Cata- logue | SPC-1000 |  |  | Fatigue | return 2 SPC-1000s for partial credit | NO | These were actually SPC-180s? not 1000s. | Not to arrive until Thursday 4/9 Fed Ex #3131661676
30 | CS | 2015-03-04 | 1556 | 22596 | A mist 40TF |  |  | Caldwell Sheanne | 2 filters had no frame | yes | delivered 4/10 |  |  |  |  | 2015-04-10 |  | 11.82 |  |  |  | 168
16 | ME | 2/18/12015 | 1542 | 20454 | SDC-30-16MDF | 134602 | no | Comfort systems TN Tech/Bristol | Vibration issues | Yes | Need replacement motor ? Going to try impeller only | Mike to install impeller 4/15 | Impeller imbalance | Replace Impeller |  | 2015-04-20 | 10 | 189 | 9 hours |  |  | 1443
14 | MC | 2015-02-11 | 1540 | 21683 |  |  |  | GE Grove city |  | no | getting outside contract for elec to be done |  |  |  |  | 2015-04-22 | [5 empty] | 2530
12 | MC | 2015-03-09 | 1537 | 20735 |  |  |  | Wolf-tec |  | yes | Taiwan recommends a earth leakage breaker, elec contractor determined transformer is leaking. Bonding center tap did not resolve. Recommends supplying house 120V | Local contractor to quote sub panel install.4/20 candi sending over quote to cust. 4/22 have quote for $5966.00. will be charged back to Taiwan |  | replace transformers with house main supplied sub panel |  | 2015-04-28 | 12 |  | 1 flight | 2 nights | 5846.68
29 | CS | 2015-04-13 | 1557 | 22142 | paint booths |  |  | airgas/portersville | naill sticking out of filters/hazard | yes | 4/13 I contact CB for insight4/14 Merchant 1 to replace nails with revised filter holder | Merch 1 to replace with revised filter holder. 4/22 Packing list done for filter holders |  |  |  | 2015-04-28 | [5 empty] | 1000
Total
[18 empty] | 1174.13 |  |  | 7633.75 | 11634.93 | 20442.81

## Custom
Customer |  | Model # | Part # | Last rev | Change description |  |  | Deficiencies | pend
IOWA HS |  | SDT180-X |  |  | 8" outlet, 14" center to ground
J&J JCI |  |  |  |  | New Roll Media | Ty Flick | Ty.R.Flick@jci.com
McCown Gordon |  |  |  |  | add air pipe to booths, remove wheel from g booth, SDT5X with no motor/filt | Steve |  |  | Drawing sent to steve
Sr. Aerospace | DEMO | SDT3 |  | A | Add working lights, kill switch, air kill solenoid |  |  | only 1 air valve
Chevron |  | pipe stand
all | Change to all | ECO collectors
San bern val coll
PPL | warranty