## Project Install Checklist
Project Install Checklist
| Yes | No | N/A
Sales Order (Document)
Customer PO (Document)
Sales Quote (Document)
Equipment Quote(s)Document
Internal Quote (Form)
Duct Layout Quote (Drawing)
Duct Quote Order (Form)
Sales Order Review (Form)
Sales Order Review Reply (Document)
Site Visit
Duct Layout Submitted to customer (Drawing)
1st Deposit
Equipment PO's (Document)
Duct Layout Approved (Document)
Duct Order (Form)
Order Reviewed by 2nd party (Form)
Duct Order Revised (Form)
2nd Deposit
Duct Order PO (Document)
Fabrication PO's (Document)
Work Order Issued (Form)
Packing List Issued (Form)
Order Confirmation (Document)
Shipping Confirmation (Documents)
Project Install Review (Form)
Project Install Quote (Document)
Project Install Folder (Documents)
Does delivery of products coincide with scheduled install date

## Sales Order Review Checklist
Sales Order Review
This review is conducted by the Project Manager when the sales order and purchase order are submitted to Engineering
Does the sales order reflect the same information as on the purchase order
Is the delivery date achievable based on standard lead times
Is the voltage/phase specified
Are shipping instructions specified
Are there quotes in place from the vendors
Are more details required on any aspect of the sales order?
Is this a standard product? If no is the customized portion clear and defined?
Are products and services clearly defined and match both the quote and customer PO?

## Order Review
Order Review
The following review is to be done at the time that the duct order is generated by the engineer.
Item | Ordered & Ordered Correctly
| Yes | No | Need to Order | Need to Order | Need to Order | Need to Order
Duct type-
tubes
slip tubes
sleeves
elbows
branches
clamps
gaskets
o rings
throttle valves
butterfly valves
blast gates
fire dampers
reducers/cones
angle flange adaptors
plenum boxes
Fan inlet flange
Fan outlet flange
Fan outlet duct (90/45/bird screen)
Rect-Rounds
Return air duct
machine adaptors
Hose adaptors
Flex Hose
Arm Stands
Mounting Brackets
Duct Stands
Silencers
Mist stop
Plenum Box-mist stop
end caps
vibration isolator
Equipment Order
collectors
fans
fume arms
booms
Installation Items
gripples
bolts
nuts
washers
thread cutting screws
unistrut
threaded rod
work order issued
revised duct order required
revised order completed
final duct order signed off
Packing list issued
PO(s) request issued
po request attached
copies of all placed on server
duct review form placed on server

## Project Schedule Install Review
Project Install Review
| Yes | No | N/A | Need to Complete
Have all orders been received by the customer (PO's & Packing Lists)
Are there remaing products/duct at Avani to deliver to customer (work Order(s))
Has the duct review been completed and signed off
Has additional duct/parts been ordered and delivered
Install Contractor Schedule Confirmed
Customer Notified of Install date
Customer approved install date(s)
Installers selected and advised
Airline Reservations
Hotel Reservations
Rental Car Reservations
Lift Rentals
Project Folder completed
Project review form placed on server

## Server Layout
Project Install Folder Layout-Server
Customer Name - Location
Sales Order Number
Sales Order
Purchase Order(s) | Folder
Sales Quote
Equipment Quotes | Folder
Internal Quote Form
Quote Duct Layout Drawing
Final Duct Layout Drawing
Customer approved drawing document
Duct Order Form
Packing Lists | Folder
Work Orders | Folder
Order Confirmation
Shipping Confirmation (s) | Folder
Duct Order Review Form
Project Install Review Form

## Flow Chart
Engineering Process Flow Chart
Internal Quote Requested
duct layout received
duct drawing completed
duct order form completed
internal quote form completed
project folder received by project manager
project folder reviewed by Project Manager |  |  |  | Sales Order Review Checklist
sales review form submitted to salesman yes-no
yes |  |  |  | No
sales review form returned complete
yes |  |  |  | No
folder delivered to engineer
verify internal quote form in place on server
yes |  | no
verify that duct order for quoting purpose has been completed
yes |  | no
verify that duct layout drawing has been completed
yes |  | no
review duct drawing and modify as required for submittal to customer
duct drawing completed
duct drawing submitted to customer for approval
approval received | yes-no
yes |  |  | no
do modifications require more duct/labor than documented on internal quote form
no |  |  |  | yes
has first deposit been received or waived |  |  |  | salesman advised that change order required
yes
project engineer conducts duct order review
requires modification?
yes |  | no
request po for duct, equipment and misc fabrication
order confirmations received
project coordination reviews ship dates versus required installation dates
salesman notified of feasibility of meeting required installation date
project enginner review for installation using installation review checklist
are additional purchase orders required?
yes |  | no