## Installs
[5 empty] | INSTALLATIONS |  |  | 2014-03-03
[5 empty] | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | SO | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
Total
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets |  |  |  | 38 hose arms, arm stands at Avani,need to change fan to 208 volt,order duct
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10 |  | at broker | Abraham or John -Solo | everything shipped to Tuscon 2/21,take p-trap
2013-10-10 | 20674 | 12596 | Magna Power, MI | AB-Mist -20 |  | Duct ship 2/4/14 | 3/10-3/13 Jason | duct shipping 2/4/14, plenum & mist pump shipped,P Trap
2013-10-14 | 20513 | 43684 | Schaeffler Mexico | AB-Mist-20 | customer to advise | duct delivery 2/4/14 | 2/25-3/2 Bill&John | shipped (1)plenum,(11)fire dampers,gripples&hardware, Take 8" Plenum
| 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40 |  | 2014-01-31 | matt to check with Fred | Fred is working with customer on intall date, duct needs to be ordered waiting on install date
2013-11-22 | 20654 | 18299 | Schaeffler SC | AB-Mist-21 | duct on site | absolent on site | 3/5/14 Daniel & Mike | Branch On order, return trip necessary, Mark to get additional PO
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20 |  | (3) absolents on site | Barb to confirm duct delivery | magna has not released remaining duct from Jacobs,shipped 3 plenum boxes,mist pump boxes 3
2013-12-11 | 20735 | 156500 | Wolf Tech-NY | grinding booth | 2/28/14 customer |  |  | taiwan has drawing confirmation, need paint color confirm from customer
2013-12-12 | 20744 | 39629 | Meigs Local School | Down Draft Table |  | SDCAT416 1/13/14 | matt to contact mc re changes | downdraft table po to robbie2/26 , light kit here,portable filtration here/ duct ordered 2/26
2013-12-16 | 20754 | 41076 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200 | multiple phases to project | continuing into 2015 | ran duct to 3 of 5 machines 2/18/14 | delivered VFD
2013-12-20 | 20786 | 37462.95 | Truform-Rightaway, IL | AB-A Smoke 40 | 2/1/14 per Fred |  |  | Drawing Approved by customer,duct ordererd 3/4
2013-12-26 | 20799 | 55957 | General Distributing | SDC-30-16MD,duct,arms,silencer |  | 2/24/14 collector |  | need duct layout from MC,silencer,collector shipped 2/24 in Wilmgton 4/9
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan | 7/31/14 -customer |  | drug tests required | absolent ordered 1/16/14, fan, wiring,duct layout issues
2014-01-17 | 20894 | 44105 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum | 2/28/14 not confirmed |  |  | Matt is working onduct layout with ED System to be in LAX 3/31
2014-01-23 | 20903 | 11202 | Wolf Tech-NY | Paint Booths |  |  |  | electrical panels on order
2014-01-23 | 20904 | see above | Wolf Tech-NY | Paint Booths |  |  |  | Paint "custom" sample mailed to cust. 3/4/14
2014-02-11 | 20998 | 102178 | Curtis Niagara | A Smoke 40 Duct F. Dampers valves |  |  | Daniel 3/26?? | A Smoke shipping from Tx 3/12/14, duct, plenum/ connection/ F. dampers ordered 2/26 Duct to ship 3/26
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel | by mid April |  |  | System to ship 3/31, panel ordered 2/24, duct needs ordering,drawing sent approval
2014-02-24 | 21059 | 6252 | Performance Contractors LA | 2030 arms, brackets, duct, install |  |  | link with trip to Weatherford | order bleed in branches, Matt 3/4/14
N/A | 20675 | 57487 | US Steel-PA | Baghouse | ASAP | Baghouse Installed | Need Hoods | 2 hoods on order Taiwan-deliver to customer arrive in Wilmington 3/19
Follow-Up | 19979 | 224863 | Weatherford-LA | welding booths | ASAP |  | 2/24-2/27 Daniel & Jason | ordered control panel to arrive on 2/19 , ordered silencers customer to provide ship carrier , shorten arms,new controls Welding Curtain ship 2/27 Gr Push Lights ordered 2/11/14
Follow-Up | 19854 | 248508 | LATTC | modify grinding table | ASAP |  |  | shorter arms delivered to customer, (3) grinding tables need modified
Follow-Up | 20274 | 41772 | Sirchie | Lexan tops,Filter Bag | ASAP |  |  | lexan tops at Avani, Ordered filter bags from Peidmont, Matt to order duct
Maintenance |  |  | Guilford Tech-Jamestown,NC | Filter change out | 2014-03-05 | school shut 3/3 perfect time to install | Jason & Josh 3/5 | Ordered filters
2014-02-24 | 21044 | 9640 | Herbalife Winston-Salem | Booth, blower, hood , arm, duct | 2014-03-17 |  |  | 2/26 ordered booth from Muhammad , arm and blower work order 2/26 sent, duct needed
2014-04-25 | 21320 | 148236.7 | Truform/Parker Fasteners | Absolents(4) Arms (28) Duct | June Install | NOT OUR INSTALL |  | Absolents orderred by Cheryl 4/25

## Drop Ship Bill
[5 empty] | Drop-Bill-Ship |  |  | 2014-03-03
|  | SO |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Total | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct |  |  | Fred&Matt | order Duct & Plenum Box
2013-04-24 | 19838 | 25884 | Watterson-WA | WB1055-Arm-Light Kit | Must arrive before 5/28/14 |  |  | on order from Taiwan
2013-10-30 | 20563 | 1434 | Fireaway - TRW Fuji Valve, TN | magnets & hoffman Box | Bill or Matt to go train-Ken to get PO for training |  |  | parts at Avani, customer wants training
2013-11-26 | 20325 | 19715 | Nucraft Metal - MI | Contactor-Relay |  |  |  | Fred to advise
2013-12-26 | 20802 | 3348 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2) |  | MC to advise | Customer does not want for 1 year | Mike wants to sell customer doesn’t' want until 6/2015
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains | Ken?? customer wants to hold for 60 days |  | cust wants no earlier than May | system & curtains in warehouse-
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055 | Ken?? | at Avani 1/7/14 |  | Shipped Close
2014-01-07 | 20720 | 21948 | GE | WB-6057G & TMC5-2 | Charles to confirm delivery |  |  | CS ordered
2014-01-08 | 20840 | 25912 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump | 3/9/2014(MC advised not going to meet date) |  | ab ships 3/10 | absolent on order, mist pump to build(voltage?)
2014-02-03 | 20956 | 8680 | Mid-America | (8) silencers |  |  |  | Silencer shipped 2/24 in Wilmg 4/9
2014-02-04 | 20965 | 9029 | General Dist. MT | Dust Collector & Booths | 2014-03-05 |  |  | shipped 2/24 be in Wilmington 4/9
| 19668 | 5440 | Sundisc | Lexan Top, exchange SDT-3 For SDT-1.5 |  |  |  | lexan top & SDT-1.5 at Avani
2014-02-04 | 20954 | 8830 | Thomas Linear | Use Mist duct, plenum, dampers | ( duct shipping 2/25) |  | customer to revise po | dampers/plenum to ship 2/20 duct ship 2/25 system moved per sam 2/20 Filters to shipping 2/21
2014-02-07 | 20987 | 916 | Forge Shop | spark elminator | 02/17/2014 and not before |  |  | on order
2014-02-06 | 20990 | 5872 | Paramount Die Co. MD | ODF 1000,1620 arm, stand | 2014-02-07 |  |  | Barb ordered ab, need dimensions on stand mc
2014-02-14 | 21023 | 4391 | ACR Dayton Ohio | Duct Jacobs | earliest they can ship 3/6 |  | 2014-03-06 | ordered 2/17
2014-02-18 | 21034 | 5110.21 | Jernberg Il | Duct Jacobs | 2/20 recevd folder 12/18 afternoon |  |  | b/o 27 rest shipped out Thurs 2/20 rest to shi0 this week
2014-02-21 | 20999 | 23946 | Hawkins | Wet Scrubber/ silencer/ duct | 2014-04-01 |  |  | Drawing sent by Fred to cust 3/4 for confirmation
2014-02-25 | 21065 | 250 | Granite City VT | Manual Starter & Overload |  |  |  | ordered 2/24
2014-02-25 | 21066 | 483.86 | Stanadyne | Duct K & B | 2014-02-24 |  |  | shipped 2/28/14 closed
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm |  |  |  | ordered all 2/26/14
2014-05-14 | 21418 | 52847.94 | J.R Automation | collector/ sliencer/ roll media/duct |  |  |  | collector ordered 5/14
2014-04-30 | 21357 | 8350 | Regency Crown Battery | arm SBU 30830 | 2014-06-30 |  |  | in port 6/23

## Open Orders12-31-13
Open Orders as of 12/31/13
Order Date | SO # | Customer | Scope
Installations
2013-09-16 | 20387 | NMCT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke
2013-12-20 | 20550 | Truform-Rightaway, IL | AB-A Smoke 40
2013-11-29 | 20675 | US Steel-PA | Baghouse
2013-05-29 | 19979 | Weatherford-LA | welding booths
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
| 19854 | LATTC | replace 26 mother boards install flex on sdt1400s
| 20851 | Curtis Screw | Run Duct to new machine
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
2013-12-19 | 20781 | CMS-Waco TX | Duct
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-11-06 | 20587 | NSK-Mexico | Jacobs Duct
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2013-10-02 | 19858 | Bernard Mechanical Contractors | Curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Case | 18869 | SunRight Disc | Lexan Top, exchange SDT-3 For SDT-1.5
Case | 20612 | Praxair Nipoma Hg School | left side welding booth damaged
Case | 20843 | Mustang | WB 1055
New | 20751 | US Engine-SC | Branch
New | 20720 | GE | WB-6057G & TMC5-2
2013-07-13 | 20131 | North Central Technical College | welding curtains

## Open Orders 1-31-13
Open Orders as of 1/31/13
Order Date | SO # | Customer | Scope
Installations
2013-06-21 | 20072 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | NCMT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200
2013-12-20 | 20786 | Truform-Rightaway, IL | AB-A Smoke 40
2013-12-26 | 20799 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-15 | 20880 | Stanadyne | Filters
2014-01-17 | 20894 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-01-23 | 20903 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | Wolf Tech-NY | Paint Booths
N/A | 20675 | US Steel-PA | Baghouse
Follow-Up | 19979 | Weatherford-LA | welding booths
Follow-Up | 19854 | LATTC | modify grinding table
Follow-Up | 20274 | Sirchie | Lexan tops,Filter Bag
Maintenance |  | Guilford Tech-Jamestown,NC | Filter change out
New |  | Altec | Filter change out
Courtesy Call |  | Accellent | Balance Absolents
| 20629 | Peterson | Welding Booths
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-19 | 20781 | CMS-Waco TX | Duct
| 20587 | NSK-Mexico | Jacobs Duct | closed 2/3
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | To ship per Sam Week of 2/3 designated truck
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Warranty | 18869 | SunRright Disc | Lexan Top, exchange SDT-3 For SDT-1.5
2014-01-07 | 20720 | GE | WB-6057G & TMC5-2
2014-01-08 | 20840 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump
2014-01-08 | 20837 | Wann Air Systems | Asmoke,Motor,Filters
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct | closed shipped 1/31
2014-01-13 | 20865 | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers | statx here 1/31 bill to work on next week
2014-01-23 | 20909 | Proveedora | US Duct | closed 2/4
2014-01-23 | 20910 | Proveedora | US Duct | closed 2/4
2014-01-27 | 20931 | Templeton | silencer, clamps, extension
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets | 1/28/14 shipped closed
2014-01-29 | 20563 | Fireaway - TRW Fuji Valve | wire & resistors
| 20738 | Curtis Screw | Absolent Filters (3)

## Open Orders2-28-14
Open Orders as of 2/28/13
Order Date | SO # | SO | Customer | Scope
Total
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10
2013-10-10 | 20674 | 12596 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | 43684 | Schaeffler Mexico | AB-Mist-20
| 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40
2013-11-22 | 20654 | 18299 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | 156500 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | 39629 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | 41076 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200
2013-12-20 | 20786 | 37462.95 | Truform-Rightaway, IL | AB-A Smoke 40
2013-12-26 | 20799 | 55957 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-17 | 20894 | 44105 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-01-23 | 20903 | 11202 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | see above | Wolf Tech-NY | Paint Booths
2014-02-11 | 20998 | 102178 | Curtis Niagara | A Smoke 40 Duct F. Dampers valves
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel
2014-02-24 | 21059 | 6252 | Performance Contractors LA | 2030 arms, brackets, duct, install
N/A | 20675 | 57487 | US Steel-PA | Baghouse
Follow-Up | 19979 | 224863 | Weatherford-LA | welding booths
Follow-Up | 19854 | 248508 | LATTC | modify grinding table
Follow-Up | 20274 | 41772 | Sirchie | Lexan tops,Filter Bag
Maintenance |  |  | Guilford Tech-Jamestown,NC | Filter change out
2014-02-24 | 21044 | 9640 | Herbalife Winston-Salem | Booth, blower, hood , arm, duct
SO
Order Date | SO # | Total | Customer | Scope
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct
2013-04-24 | 19838 | 25884 | Watterson-WA | WB1055-Arm-Light Kit
2013-10-30 | 20563 | 1434 | Fireaway - TRW Fuji Valve, TN | magnets & hoffman Box
2013-11-26 | 20325 | 19715 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | 3348 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055
2014-01-07 | 20720 | 21948 | GE | WB-6057G & TMC5-2
2014-01-08 | 20840 | 25912 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump
2014-02-03 | 20956 | 8680 | Mid-America | (8) silencers
2014-02-04 | 20965 | 9029 | General Dist. MT | Dust Collector & Booths
| 19668 | 5440 | Sundisc | Lexan Top, exchange SDT-3 For SDT-1.5
2014-02-04 | 20954 | 8830 | Thomas Linear | Use Mist duct, plenum, dampers
2014-02-07 | 20987 | 916 | Forge Shop | spark elminator
2014-02-06 | 20990 | 5872 | Paramount Die Co. MD | ODF 1000,1620 arm, stand
2014-02-14 | 21023 | 4391 | ACR Dayton Ohio | Duct Jacobs
2014-02-18 | 21034 | 5110.21 | Jernberg Il | Duct Jacobs
2014-02-21 | 20999 | 23946 | Hawkins | Wet Scrubber/ silencer/ duct
2014-02-25 | 21065 | 250 | Granite City VT | Manual Starter & Overload
2014-02-25 | 21066 | 483.86 | Stanadyne | Duct K & B
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm

## Jan-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
Verbal-ED | 20851 | Curtis Screw | Run Duct to new machine | ASAP |  | 1/23-1/26 Dan & Abe | duct to ship 1/16/14-Daniel to install,Duct &gaskets at Avani to go
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-11-02 | 20621 | Oracle Winston Salem NC
2014-01-15 | 20880 | Stanadyne-NC | Stat-X Install | Drop-Ship-Bill |  |  | 2014-01-24
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
Case | 20843 | Mustang | WB 1055
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2014-01-09 | 20829 | Charter | K& B Duct |  |  | 2014-01-23
2014-01-06 | 20815 | Jernberg - IL | K&B Duct |  |  | 2014-01-23
| 20879 | Stanadyne
| 20587 | NSK-Mexico | Jacobs Duct |  |  | shipped 1/17/14 | Broker crossed over boarder 1/31/14 closed
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct |  |  | 1/30/2014 & 2/6/14 | closed shipped on 1/31/14
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets |  |  |  | shipped 1/28/14 closed

## Feb.-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500 |  |  | 1/26 - 2/3 Both Crews | completed 2/2/14
2013-12-18 | 20738 | Curtis Screw | Absolent Filters (3) |  |  | 2014-01-31 | shipped 2/6/14
| 20880 | Stanadyne | Filters |  |  |  | recd. 1/31/14
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10 |  | absolent on site | 2/9-2/13 Jason&Mike | completed 2/11/14
2013-07-03 | 20131 | North Central Tech College | welding curtains |  |  | 2014-02-05 | shipped 2/4/14
2014-01-27 | 20931 | Templeton | silencer, clamps, extension | asap |  |  | completed 2/4/14
2014-01-23 | 20909 | Proveedora | US Duct | ASAP |  | 2014-01-30 | completed 2/4/14
2014-01-23 | 20910 | Proveedora | US Duct | ASAP |  | 2014-01-30 | completed 2/4/14
2014-02-05 | 20855 | Proveedora De Seguriad | duct | missed pieces |  |  | shipped 2/5/14 close
2014-01-03 | 20824 | Hydromat St. Louise | Mist 20 s and Mist Pump |  |  |  | all shipped, and received closed 2/5
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | 2014-02-10 |  | shipping 1/31/14 | shipped out 2/7/14
New |  | Altec | Filter change out | 2014-02-08 |  | 2/8/14 Dan/Abraham/Josh
2014-02-05 | 20971 | Jernberg | 16" gaskets | overnight |  |  | ordered 2/5/14
2014-02-06 | 20975 | Muntz- Mundelein, IL | Damper, reducers , flg adaptors |  |  |  | ship damper 2/10 duct shipping 2/13
2014-01-22 | 20907 | Stanadyne | duct | 1/31/14 recd. Folder 2/3 |  | duct ships 2/11 | duct shipped 2/11 spark arrestor to shipping 2/10/14
2014-02-07 | 20993 | 1137 | Teel Plastics, WI | 1020 arm, bracket & duct |  |  |  | SHIPPED CLOSE
2014-02-11 | 21000 |  | Honda Canada Mfg | F.Damper ( fusable) Filter 6 | 2/11 recvd folder 2/11 |  |  | SHIPPED CLOSE
2014-01-13 | 20865 |  | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers |  | asmoke&fd delivered |  | SHIPPED CLOSE
Case | 1298 |  | Praxair Nipomo High School | panel PO sent in 2/5/14 |  |  |  | TO SHIPPING 2/19
2014-02-24 | 21038 | 235.6 | Howell Metal VA | 14"Elbow & Clamp |  |  |  | duct shipped 2/26 close
2014-01-08 | 20837 | 18352 | Wann Air Systems | Asmoke,Motor,Filters | 2014-01-31 |  |  | closed 2/27/14
2014-02-21 | 21052 | 250 | OZ Lifting Products MN | Manual Starter & Overload |  |  |  | shipped 2/25/14
2013-12-19 | 20781 | 36379 | CMS-Waco TX | Stainless KB Duct |  |  |  | shipped 2/26
2014-02-26 | 21069 | 900 | TRW Fuji | Fire Dampers 6 K&B |  |  |  | SHIPPED CLOSE
2013-11-15 | 20629 | Peterson | Welding Booths | CANCELLED ORDER |  |  | CUSTOMER CANCELLED VERBALLY PER ED 2/11/14
Courtesy Call |  |  | Accellent | Balance Absolents | 2/18 9AM |  | 2/18/2014 Bill