## Installs
INSTALLATIONS
[6 empty] | Requested | Confirmed | Quoted | Scheduled | 2015-01-20
| Order Date | SO # | SO | Customer | Scope | Install Date | Delivery Date | Inst. Hrs | Install Date | Pending
|  |  | Total | [6 empty] | Comments
x | 2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets |  |  |  | flex shipped, duct ordered, duct in oct | need rec to round for fan
| 2013-10-24 | 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40 | Not Avani | 2014-01-31 |  | Engineer on site wants to change layout, Bob Zill to Install | Fred is working with customer on intall date, duct is on order waiting on install date
| 2013-12-26 | 20799 | Invoiced | General Distributing, MT | SDC-30-16MD,duct,arms,silencer |  | 2/24/14 collector |  | all collectors, arms,on site(need revised duct order after dwg approval) | drawing sent for approval for modification, waiting on concrete pad
| 2014-04-30 | 21379 | 63869 | H B Construction/ Bernalillo H S NM | Dust Collector/ Duct/ Welding Booth | 2015 |  |  | 2015-11-01 | Call customer in 3/2015 before ordering to see if on track
| 2014-05-01 | 21360 | Invoiced | CareFusion | Training in Mexico-Bill
| 2014-06-10 | 21517 | 92830 | Groathouse-Roosevelt High, WY | Grinding Booth (2) Wp-1055 (18) 1620 Arms (18) |  |  | 30 | Sept. 2015
| 2014-07-25 | 21709 | 195608.8 | Boilermakers Bloomington CA |  | 2014-12-01 | not our install manage only |  |  | act collectors ordered 8/22, curtains shipping 10/24, Free SPC 2810 ordered 9/25, Welding booths arms booms ordered 9/2,In port 11/5
| 2014-07-25 | 21711 | 77077.3 | Boilermakers Spokan WA |  | 2014-12-01 | not our install manage only |  |  | system in port 11/20 / ACT ship before 10/31
| 2014-07-25 | 21712 | 249470 | Boilermakers Page, AZ |  | 2014-12-01 | not our install manage only |  |  | act collectors ordered 8/22/14
| 2014-07-25 | 21713 | 87108.35 | Boilermakers Portland, Or |  | 2014-12-01 | not our install manage only |  |  | act collectors ordered 8/22/14
| 2014-07-25 | 21714 | 121732.05 | Boilermakers Puyallup, WA |  | 2014-12-01 | not our install manage only |  |  | systems in port 11/20/ ACT shipping before 10/31
| 2014-08-05 | 21755 | 22885 | Bonney Forge Corp Mt. Union PA | ASMoke 20, Duct, | 2014-12-22 | transition piece? |  | pushed back to 2/2 MC | duct ordered, system ordered
x | 2014-09-10 | 21910 | 39900 | Neumeier Engineering | Grinding Booth,Wet Collector,Duct | 2014-12-08 | contractor to install |  | install 1/8/15 outside contractor | argos to install after all is on site, dave setera contacted 1/2/15
| 2014-09-19 | 21946 | 12645 | GTTC 2014-2015 | 4 installs annually |  |  |  |  | order filters and schedule install
xx |  | 21977 | 98471.88 | Joes Racing/ Constance Machines Everett WA | A Mist 80 TF 3 contrl panel filter duct |  | waiting on dwg approval duct inc and need to order transition |  | (Evergreen)issued po Advised they can install week of 1/19 | Duct arrives 1/19, Evergreen advised
xx | 2014-05-13 | 21418 | 52847.94 | JR Automation | SDC-20-16MD, RM6000N,duct, silencer | install in Mexico |  |  | Wilmington 10/2, duct and transitions ship from MI | Bill completed drawing and sent to Darren
xx | 2014-10-20 | 22056 | 100367 | Airgas Torcsill Foundation Pasadena TX | arms 2030 2040/ brackets 8/ collector/ duct/ Robotic hood | 2014-11-06 | PO issued to contractor |  | emailed contractor (week of 19th?) | Duct shipped hoods shipped ACT collector delivery this week-confirm
|  | 22050 | 6084.05 | Spanda Indust Development Sacramento CA | Welding booth ( 5) gas/ air lines (15) Curtains ( 5) mting brackets ( 5) collector SDC 10-6 (1) silencer (1) duct | 2014-12-29 | need drawing from Alcoa for Silencer |  | have booths been orderd? | collecter needs to be shipped from Alcoa, dwg sent to ed for approval
| 2014-11-10 | 22152 | 366183 | Plummer and Pipefitters Landover MD | Act collector, customer welding booths( 1) Premier Welding booths (20) Welding Booth w/hood (2) duct SDT 3 (4) | 2015-02-05 |  |  | FIRST PAYMT MADE | layout of booths have been approved, duct layout over booths needs to be done
|  | 22180 | 20200 | Schaffler-Cheraw, SC | A Smoke 20 |  | No deposit required |  | duct ordered 1/14/15 | NO control panel System ordered 11/26
| 2014-11-24 | 22220 | 15550 | Schaffler-Cheraw, SC | A Smoke 20 |  | No deposit required |  | need layout from mark | NO control panel A Smoke ordered 11/26 need layout from mark
| 2014-12-02 | 22233 | 126064 | Chevron-Richmond, CA | (8) WB 1066, (1) SDC-at-3-12, (8) 1020 arms, (8) custom hoods , spiral duct | on site 12/31/14 | No deposit required |  | wtg on dwg approval, need curtain rods from muhammed, c clamps to be fabricated | dwg sent to customer 12/12
| 2014-12-08 | 22268 | 29642 | Schaffler-Cheraw, SC | A Mist20(2), Duct & Cradle |  |  |  | Duct ships 1/23/15 | Absolent ordered `12/8 ships 12/23
| 2014-12-16 | 22300 | 5749 | Borg Warner-Arden, NC | Jacobs duct and install |  |  |  | duct ordered-Jacobs 1/14/15 | dwg is approved
| 2014-12-19 | 22316 | 107897.8 | ELG Utica Alloys - Monroe, NC | (1) SDC-AT-3-12 (1) SDC-AT-3-24 Duct & Install | 2015-01-19 |  |  |  | hal is working on dwg
| 2014-12-15 | 22291 | 32669 | Haun/Derrick Corp. Cheektowaga, NY | (1) Robo 40 Duct & Install | 2014-12-31 |  |  |  | duct dwg to be done, need approval on hood & dwg
| 2014-12-23 | 22329 | 332720 | Bonney Forge Corp Mt. Union PA | (1) SDC-7-6 (1) SDC-5D-6 (1) 2040 (1) 8"Bracket K&B Duct |  |  |  | awaiting parts from Taiwan for collectors | need hoods
|  |  |  | Vegas Fasteneners | (11) new hoods, re-duct job |  | Need PO |  | Travel 1/20, Install 1/20-1/22 | Hoods shipped 1/12, duct ships 1/14, Absolent needs to ship,2/5 US Duct eta 2/6
| 2015-12-29 | 22356 | 11750 | Cutler Hammer - Arden, NC | special filters, duct, install |  |  |  | Install 1/22/15 | flters, duct and return air box & louvers ordered
| 2015-01-12 | 22378 | 14939 | Leuco Precision Tooling | AB-A Mist 20, Jacobs Duct, 2-1/2" Loc-Line vacuum hose, install
| 2015-02-03 | 22482 | 18104.84 | Cubic Machinery | melanie.antunes@cubicmachinery.com | AB-A Mist,duct
| Total |  | 1175232.58

## Drop Ship Bill
|  |  |  | Drop/Ship/Bill |  |  |  |  | 2015-01-20
|  |  | SO |  |  | Requested | Confirmed | Scheduled | Pending
| Order Date | SO # | Total | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
| 2013-04-24 | 19838 | 25884 | Watterson-WA | (18) booths, arms, led lights | On site June 1 2015 | Review order in Jan 2015 |  | Need to supply details for order already sent to Taiwan
| 2013-12-26 | 20802 | Invoiced in Full | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2) | 2015-06-01 | MC to advise | Customer does not want for 1 year | Customer wants to store here until 6/2015, sent email to salesman re: options to sell etc
| 2014-06-10 | 21509 | 208250 | Sterling Springs IL | install b. zill/ fan ordered 7/16/ dust collector | 2014-07-25 | not our install multiple installs |  | first installed billed 7/16, waiting on Fred to bill the next one
x | 2014-08-26 | 21849 | 13780 | R B & W Canada | A Smoke 40/ P Trap/ Duct | 2014-12-01 | not our install | bill strouth said to hold duct order | system shipped 12/23 need duct ,emailed for update 1/20
x | 2014-08-28 | 21701 | 5238 | Holman Jacksonville, Fl | Welding Booth and Curtain 1 | sometime in 2015 cust. has been asked to give 12-14 week lead time minimal | 12/12 approved drawing | ordered from Taiwan 12/5/14 | booth ordered drawing approved 12/10, need to order curtain
| 2014-09-12 | 21920 |  | Doosan-Pena Intl. |  |  |  |  | Shipments eom Jan/April/July/Oct
x | 2014-10-13 | 22033 | 12000 | Southern Career Inst Harlingen, Tx | welding booths, robos, duct | 2014-12-01 | Need transitions from Triangle | ship units in whse when duct ships 1/22/15 | welding booths, robos in whse,ship when duct ships ordered duct 1/20 (4)transitions, (2) robo plenums
x | 2014-10-23 | 21948 | 28954 | RB&W Canada second order frm Sept |  | 12/2014 install | customizing 575 vlts |  | system ship 12/23 Duct ships 1/21/15
x | 2014-11-04 | 22140 | 6986.65 | Hydromat Maryland Hght MO | A Mist 20 ( 1) Mist pump ( 1) | 2015-02-20 | System to ship prior to 2/16 Mist pump |  | system to ship in 2/2015, need to order and build mist pump
| 2014-10-24 | 22079 | 16405 | Horn Equipment Moore Oklahoma | Ext Boom ( 2) Arm 2040(2) duct | 2014-12-30 | no deposit | not our install | Hytech installing Feb 3 & 4 2105
x | 2014-11-13 | 22178 | 14136.2 | Pasadena ISD - Houston, TX
x | 2014-12-03 | 22243 | 10074 | United Grinding-Miamisburg,OH | 8" K&B PB, A Mist 10, water can | 2015-02-01 |  | absolent ships 2/25 | need to issue packing list for (2) plenums 2/16/15
x | 2014-12-08 | 22267 | 25065 | Honda of Canada | (3) A Mist20, Duct, |  |  | need ductlayout -Bill strouth | absolents ordered 12/8, need duct, (2)transitions, (1) plenum
x | 2014-12-10 | 22283 | 221040 | Alcoa-Waco TX | A Smoke 40B (8) Stands, Plenums, poly pad filters, duct | 2 ship 1/14 6 ship 12/29 |  | need duct layout from Richard King | need packing list for stands, plenums and poly pad frame s and filters (8)
x | 2014-12-10 | 22281 | 5037 | United Grinding-Miamisburg,OH | A Mist 10, water can, 8" plenum | due April 2015 |  |  | nothing ordered see due date
x | 2014-12-16 | 22297 | 2443 | Hastings- Hastings, PA | duct |  |  |  | MT submitted duct for review
x | 2014-12-17 | 22307 | 9698 | Fatigue Technology -Seattle WA | (1) SPC-3000 (1) Hepa Cage, Duct |  |  |  | Hal working on dwg
x | 2014-12-19 | 22317 | 111313 | McCownGordon Construction -Kansas City, MO | (6) WB5087 (1) wb5088 (1) GB5088 (2) SDT-3 Installation-Outside Contractor |  |  |  | ordered 12/23 sent email for tracking 1/20
x | 2014-12-19 | 22319 | 22280 | National Machinery-Tiffin, OH | (2) A Smoke 20- Custom Paint | Deliver to Avani for Paint | waiting for SW paint sample | scott cook to paint | At avani awaiting paint
x | 2014-12-30 | 22344 | 5559.6 | Clayton Associates - Lakewood, NJ | SPC-1000 with class 1 div 1 motor, 230 volt, carbon filter,plenum box to hold two arms |  |  |  | motor&carbon filter ordered, spc-1000 in house, impeller ordered,starter & enclosure ordered
x | 2014-12-30 | 22345 | 39145 | Butler-Pittsburgh, PA | SDC-AT-3-24, (18) WB-1055, |  |  |  | collector ordered 12/30 PO 10161
| 2015-01-05 | 22352 | 7914 | Norco- Gillette, WI | fan with silencer, 8"x 5' boom, 2040 arm
| 2015-01-06 | 22349 | 3352 | Honda of Canada | duct only K & B |  |  | old dominion est. del 1/20 | duct ships 1/21/15
| 2015-01-09 | 22373 | 425 | Anderson Quality Spring-Canby, OR | pressure gauge, impeller |  |  |  | impeller ordered fromTaiwan 1/13/15, pressure gauge S-2000 in stock
x | 2015-01-12 | 22381 | 111.36 | Alotech - Goldston, NC | Goyen solenoid valve |  |  |  | c sithes to order 1/13/15
| 2015-01-13 | 22385 | 327.94 | Kennemetal-Wldon, NC | Jacobs Duct |  |  | 1/20 being delivered today | requested order 1/13/15
| 2015-01-13 | 22382 | 12126 | Cheever Construction-Utica, NE | (4) WB-1055, (4) Curtains, (4) 1620 arms, (4) 6" fume arm brackets
| 2015-01-13 | 22178 | 14136.2 | Airgas Pasadena ISD | (26) side shelves and back shelves, c clamp stands |  |  |  | ordered 1/7/15, Muhammed quoting c clamp stands
| 2015-01-16 | 22407 | 552.9 | Kennametal - Weldon, NC | (30) ceiling hanger brackets |  |  | 1/20 email-Shipping on 1/21 | ordered 1/16/15
| 2015-01-16 | 22401 | 28048 | College of Charleston-Charleston,SC | SPC-800 (2) 1020P (4)SDT-2 Customized (3)
| 2015-01-19 | 22415 | 6517 | Baldor Dodge-Rogersville, TN | A Mist10, Special pre-filter, Control Panel |  |  |  | ordered 1/20/15
| 2015-01-19 | 22412 | 114815.3 | Machine Technology-Auburn, WA | A Mist 40TF (2) A SMoke40 (2) Duct, Install outside contractor
| 2015-01-20 | 22421 | 263.68 | Schaeffler Group USA Inc | duct | 1/20 ship ups 2nd day X723W4 |  |  | 1/20 ordered PO #10261
| 2015-02-05 | 22510 | 0 | Ecolo- Tech | 248-541-1100 ecolotechinc@yahoo.com | demo unit
| 2015-02-05 | 22511 | 311.76 | Honda of Canada | MRO_AP@hcm.honda.com | duct
| 2015-02-05 | 22412 | 114815.3 | Machine Technology | Sherri@machtech.biz | AB-Mist, AB smoke, duct, |  |  | 2/5/15 no 1st dep
| Total |  | 971877.83

## Install-Dates
INSTALLATIONS
2014-09-05 | 21883 | 9540 | Borg Warner-Arden, NC | (3) Absolent Filters-Jacobs Duct | 2014-09-27 |  |  | 1/6-1/7/2014 | 3 filters in warehouse duct ships arrived 12/9
2014-08-05 | 21760 | 11387.81 | Morris South Charlotte, NC | Collector, Duct | 2014-11-10 | Duct,plenum and connections to be ordered, |  | 2014-01-08 | systemon per mark ship 11/19 cust wants mid Dec duct ships 12/23 (1) day install
| 21977 | 98471.88 | Joes Racing/ Constance Machines Everett WA | A Mist 80 TF 3 contrl panel filter duct |  | waiting on dwg approval duct inc and need to order transition |  | (Evergreen)issued po to contractor need to confirm date with MH | System ( 2) shipping 10/17/ panels here need duct and customized items
2014-10-20 | 22056 | 100367 | Torcsill Foundation Pasadena TX | arms 2030 2040/ brackets 8/ collector/ duct/ Robotic hood | 2014-11-06 | Schedule Install |  | 1st dep rec 11/7 | Matt T sent questions to R King Duct shipped 11/26 Collector ordered 11/12 duct shipped 11/26 Hood ordered 11/18 K&B ship 12/12 ACT collector not delivered yet
2014-06-17 | 21554 | 121283.66 | Sunnyvale Dist. (Bloom)Center-Sunnyvale, CA | Grinding Booth,SDT-1.5, |  |  | 50 | 2015-01-12 | Act shipping by 10/27/ duct to arrive 11/10 customer informed
2014-09-10 | 21910 | 39900 | Neumeier Engineering | Grinding Booth,Wet Collector,Duct | 2014-12-08 | contractor to install |  | duct ordered 11/26 to ship 12/3 system in port 12/10 ,ordered buck booster | Gbooth in port 12/9 Wet Collector to ship , duct is on site
2014-08-05 | 21755 | 22885 | Bonney Forge Corp Mt. Union PA | ASMoke 20, Duct, | 2014-12-22 | transition piece? |  | 2014-01-26 | duct ordered, system ordered
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets |  |  |  | flex shipped, duct ordered, duct in october | need rec to round for fan
2013-10-24 | 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40 | Not Avani | 2014-01-31 |  | Engineer on site wants to change layout, Bob Zill to Install | Fred is working with customer on intall date, duct is on order waiting on install date
2013-12-26 | 20799 | Invoiced | General Distributing, MT | SDC-30-16MD,duct,arms,silencer |  | 2/24/14 collector |  |  | drawing sent for approval for modification
2014-04-30 | 21379 | 63869 | H B Construction/ Bernalillo H S NM | Dust Collector/ Duct/ Welding Booth | 2015 |  |  | 2015-11-01 | Call customer in 3/2015 before ordering to see if on track
2014-05-01 | 21360 | Invoiced | CareFusion | Training in Mexico-Bill
2014-06-10 | 21517 | 92830 | Groathouse-Roosevelt High, WY | Grinding Booth (2) Wp-1055 (18) 1620 Arms (18) |  |  | 30 | Sept. 2015
2014-07-25 | 21709 | 195608.8 | Boilermakers Bloomington CA |  | 2014-12-01 | not our install manage only |  |  | act collectors ordered 8/22, curtains shipping 10/24, Free SPC 2810 ordered 9/25, Welding booths arms booms ordered 9/2,In port 11/5
2014-07-25 | 21711 | 77077.3 | Boilermakers Spokan WA |  | 2014-12-01 | not our install manage only |  |  | system in port 11/20 / ACT ship before 10/31
2014-07-25 | 21712 | 249470 | Boilermakers Page, AZ |  | 2014-12-01 | not our install manage only |  |  | act collectors ordered 8/22/14
2014-07-25 | 21713 | 87108.35 | Boilermakers Portland, Or |  | 2014-12-01 | not our install manage only |  |  | act collectors ordered 8/22/14
2014-07-25 | 21714 | 121732.05 | Boilermakers Puyallup, WA |  | 2014-12-01 | not our install manage only |  |  | systems in port 11/20/ ACT shipping before 10/31
2014-09-19 | 21946 | 12645 | GTTC 2014-2015 | 4 installs annually
2014-05-13 | 21418 | 52847.94 | JR Automation | SDC-20-16MD, RM6000N,duct, silencer | install in Mexico |  |  | Wilmington 10/2, duct and transitions ship from MI | must be installed-complete by 10/20
| 22050 | 6084.05 | Spanda Indust Development Sacramento CA | Welding booth ( 5) gas/ air lines (15) Curtains ( 5) mting brackets ( 5) collector SDC 10-6 (1) silencer (1) duct | 2014-12-29 | need drawing from Alcoa for Silencer |  | need deposit | welding booths to be fabricated by?
2014-11-10 | 22152 | 366183 | Plummer and Pipefitters Landover MD | Act collector, customer welding booths( 1) Premier Welding booths (20) Welding Booth w/hood (2) duct SDT 3 (4) | 2015-02-05 |  |  | FIRST PAYMT MADE | need to do drawings MT
| 22180 | 20200 | Schaffler-Cheraw, SC | A Smoke 20 |  | No deposit required |  |  | NO control panel System ordered 11/26 duct to be ordered
2014-11-24 | 22220 | 15550 | Schaffler-Cheraw, SC | A Smoke 20 |  | No deposit required |  |  | NO control panel A Smoke ordered 11/26 duct to be ordered
2014-12-02 | 22233 | 126064 | Chevron-Richmond, CA | (8) WB 1066, (1) SDC-at-3-12, (8) 1020 arms, (8) custom hoods , spiral duct | on site 12/31/14 | No deposit required |  |  | booths being made, need specs on hood and c clamp arm, collector ordered, need duct drawing
2014-12-08 | 22268 | 29642 | Schaffler-Cheraw, SC | A Mist20(2), Duct & Cradle |  |  |  | Duct Drawing sent to customer for approval | Absolent ordered `12/8 ships 12/23
2014-12-16 | 22300 | 5749 | Borg Warner-Arden, NC | Jacobs duct and install |  |  |  | need duct layout
2014-12-17 | 22301 | 10888 | Curtis Niagara | Jacobs duct and install |  |  |  | need duct layout
2014-12-19 | 22316 | 107897.8 | ELG Utica Alloys - Monroe, NC | (1) SDC-AT-3-12 (1) SDC-AT-3-24 Duct & Install | 2015-01-19
2014-12-15 | 22291 | 32669 | Haun/Derrick Corp. Cheektowaga, NY | (1) Robo 40 Duct & Install | 2014-12-31
2014-12-23 | 22327 | 1560 | Sirchie- Youngsville, NC | Hose, Duct, Install | 2015-01-20 |  |  |  | requested Chaz to order 12/23/14
2014-12-23 | 22329 | 332720 | Bonney Forge Corp Mt. Union PA | (1) SDC-7-6 (1) SDC-5D-6 (1) 2040 (1) 8"Bracket K&B Duct

## Jan-Completed (hidden)
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Verbal-ED | 20851 | Curtis Screw | Run Duct to new machine | ASAP |  | 1/23-1/26 Dan & Abe | duct to ship 1/16/14-Daniel to install,Duct &gaskets at Avani to go
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-11-02 | 20621 | Oracle Winston Salem NC
2014-01-15 | 20880 | Stanadyne-NC | Stat-X Install | Drop-Ship-Bill |  |  | 2014-01-24
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
Case | 20843 | Mustang | WB 1055
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2014-01-09 | 20829 | Charter | K& B Duct |  |  | 2014-01-23
2014-01-06 | 20815 | Jernberg - IL | K&B Duct |  |  | 2014-01-23
| 20879 | Stanadyne
| 20587 | NSK-Mexico | Jacobs Duct |  |  | shipped 1/17/14 | Broker crossed over boarder 1/31/14 closed
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct |  |  | 1/30/2014 & 2/6/14 | closed shipped on 1/31/14
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets |  |  |  | shipped 1/28/14 closed

## Feb.-Completed (hidden)
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500 |  |  | 1/26 - 2/3 Both Crews | completed 2/2/14
2013-12-18 | 20738 | Curtis Screw | Absolent Filters (3) |  |  | 2014-01-31 | shipped 2/6/14
| 20880 | Stanadyne | Filters |  |  |  | recd. 1/31/14
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10 |  | absolent on site | 2/9-2/13 Jason&Mike | completed 2/11/14
2013-07-03 | 20131 | North Central Tech College | welding curtains |  |  | 2014-02-05 |  | shipped 2/4/14
2014-01-27 | 20931 | Templeton | silencer, clamps, extension | asap |  |  |  | completed 2/4/14
2014-01-23 | 20909 | Proveedora | US Duct | ASAP |  | 2014-01-30 |  | completed 2/4/14
2014-01-23 | 20910 | Proveedora | US Duct | ASAP |  | 2014-01-30 |  | completed 2/4/14
2014-02-05 | 20855 | Proveedora De Seguriad | duct | missed pieces |  |  |  | shipped 2/5/14 close
2014-01-03 | 20824 | Hydromat St. Louise | Mist 20 s and Mist Pump |  |  |  |  | all shipped closed 2/5
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | 2014-02-10 |  | shipping 1/31/14 | shipped out 2/7/14
New |  | Altec | Filter change out | 2014-02-08 |  | 2/8/14 Dan/Abraham/Josh
2014-02-05 | 20971 | Jernberg | 16" gaskets | overnight |  |  | ordered 2/5/14
2014-02-06 | 20975 | Muntz- Mundelein, IL | Damper, reducers , flg adaptors |  |  |  | ship damper 2/10 duct shipping 2/13
2014-01-22 | 20907 | Stanadyne | duct | 1/31/14 recd. Folder 2/3 |  | duct ships 2/11 | duct shipped 2/11 spark arrestor to shipping 2/10/14
2014-02-07 | 20993 | 1137 | Teel Plastics, WI | 1020 arm, bracket & duct |  |  |  | SHIPPED CLOSE
2014-02-11 | 21000 |  | Honda Canada Mfg | F.Damper ( fusable) Filter 6 | 2/1 recvd folder |  |  | SHIPPED CLOSE
2014-01-13 | 20865 |  | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers |  | asmoke&fd delivered |  | SHIPPED CLOSE
Case | 1298 |  | Praxair Nipomo High School | panel PO sent in 2/5/14 |  |  |  | TO SHIPPING 2/19
2014-02-24 | 21038 | 235.6 | Howell Metal VA | 14"Elbow & Clamp |  |  |  | shipped 2/26 close
2014-01-08 | 20837 | 18352 | Wann Air Systems | Asmoke,Motor,Filters | 2014-01-31 |  |  | closed 2/27/14
2014-02-21 | 21052 | 250 | OZ Lifting Products MN | Manual Starter & Overload |  |  |  | shipped 2/25/14
2013-12-19 | 20781 | 36379 | CMS-Waco TX | Stainless KB Duct |  |  |  | shipped 2/26
2014-02-26 | 21069 | 900 | TRW Fuji | Fire Dampers 6 K&B |  |  |  | SHIPPED CLOSE
2013-11-15 | 20629 | Peterson | Welding Booths | CANCELLED ORDER |  |  | CUST CANCELLED VERBALLY PER ED 2/11/14
Courtesy Call |  |  | Accellent | Balance Absolents | 2/18 9AM |  | 2/18/2014 Bill

## Mar-Completed (hidden)
2013-10-14 | 20513 | 43684 | Schaeffler Mexico | AB-Mist-20 | customer to advise | duct delivery 2/4/14 |  | completed 3/1/14
2013-11-22 | 20654 | 18299 | Schaeffler SC | AB-Mist-21 | duct on site | absolent on site | 3/5/14 Daniel & Mike | closed 3/5/14Mark to get additional PO
2013-12-20 | 20786 | 37462.95 | Truform-Rightway, IL | AB-A Smoke 40 | 2/1/14 per Fred | Duct ships 3/11 | 64.125 | completed 3/19/14 | 12" jacobs plenum&(4) 6"fire dampers take from Avani gripples ordered 3/10, install of 3/18
2013-10-10 | 20674 | 12596 | Magna Power, MI | AB-Mist -20 |  | Duct ship 2/4/14 | 41.25 | 3/20 Daniel Jason Mike | duct shipping 2/4/14, plenum & mist pump shipped,P Trap, install 3/21 to be confirmed by customer
2013-12-12 | 20744 | 39629 | Meigs Local School | Down Draft Table |  | SDCAT416 1/13/14 |  | Daniel Jason Mike 3/24 | downdraft table po to robbie2/26 , light kit here,portable filtration here/ duct revised 3/6, install 3/24 to be confirmed by customer
2014-03-05 | 21089 | 5153.13 | Starcon ( weldstar) | booth welding table top |  |  |  | install included with this | Estimated completion, ready to ship 3/26
2014-03-05 | 21090 | 3600 | Starcon ( weldstar) | Installation welding table top |  | Install 3/28/14 |  | John & Mike 3/27-3/29 | Fred to confirm install date, sometime after after 3/26
2014-03-14 | 21175 | 6785 | Eaton Roxboro-NC |  |  |  |  | Bill to be involved in install,confirm 3/28,Daniel & Jason | K&B received 3/21 , pulling from stock K&B, Fire dampers to warehouse 3/21,need ccover plates asap Matt to order
2014-02-25 | 21066 | 483.86 | Stanadyne | Duct K & B | 2014-02-24 |  |  | shipped 2/28/14 closed
2014-02-18 | 21034 | 5110.21 | Jernberg Il | Duct Jacobs | 2/20 recevd folder 12/18 afternoon |  |  | shipped in full no back order closed March2014
Maintenance |  |  | Guilford Tech-Jamestown,NC | Filter change out | 2014-03-05 | school shut 3/3 perfect time to install |  | completed 3/5/14
2014-02-14 | 21023 | 4391 | ACR Dayton Ohio | Duct Jacobs |  |  |  | closed 3/10/14
2014-03-03 | 21101 |  | Alcoa | filters/ track | 2014-03-03 | shipped 3/6 closed
2014-03-05 | 21117 | 416.88 | Munntz | 6 elbows K&B | 2014-03-07 | closed 3/7/14 |  | ordered to ship 3/6
2013-11-26 | 20325 | 19715 | Nucraft Metal - MI | Contactor-Relay |  |  |  | close per Fred 3/10/14
2014-02-25 | 21065 | 250 | Granite City VT | Manual Starter & Overload |  |  |  | closed 3/11/14
2014-02-06 | 20990 | 5872 | Paramount Die Co. MD | ODF 1000,1620 arm, stand | 2014-02-07 |  |  | closed 3/11/14
| 19668 | 5440 | Sundisc | Lexan Top, exchange SDT-3 For SDT-1.5 |  | work order issued to shipping 3/3 |  | Shipped 3/10/14-Closed
2014-03-12 | 21149 | 593.52 | Deutsche | Fire Dampers 3 |  |  |  | shipped 3/12 CLOSE
2014-02-04 | 20954 | 8830 | Thomas Linear | Use Mist duct, plenum, dampers | ( duct shipping 2/25) |  | customer to revise po | dampers/plenum to ship 2/20 duct ship 2/25 system moved per sam 2/20 Filters to shipping 2/21 final parts shipped 3/5 Closed
2014-03-17 | 21178 | 1014.2 | Proveedora | K & B Duct duplicate | CANCELLED ORDER | CANCELLED ORDER |  | CANCELLED ORDER 3/18/14
2014-03-20 | 21198 | 4213.6 | CMS | duct | 2014-03-20 |  |  | shipped 3/24 close
2014-03-24 | 21201 | 463.44 | US Engine Valve | Fire Damper/ Flange adaptors / clamps | 2014-03-20 |  |  | shipped 3/24 close
2014-03-18 | 21184 | 370.33 | Proveedora | K & B Duct clamps | 2014-03-18 |  |  | shipped 3/24 close
2014-03-11 | 21137 | 3601.03 | McClain Tool and Technology | Duct Jacobs | rush |  |  | shipping 3/18
2013-10-30 | 20563 | 1434 | Fireaway - TRW Fuji Valve, TN | magnets & hoffman Box | Bill or Matt to go train-Ken to get PO for training |  |  | parts at Avani, customer wants training
2014-03-25 | 21203 | 5932 | Alco Fastening System | Filters/ track/ Filters A Smoke 40 | 2014-03-20 |  |  | shipped 3/28
2014-03-06 | 21126 | 7028 | Alcoa Waco Tx | Filters/ duct mist stop | 2014-04-05 |  |  | Shipping 3/28/14 Close
2014-03-26 | 21219 | 1356 | P K / Swedish Match | dust/ reducer/ clamp | 2014-03-28 |  |  | duct shipped - system req to ship 3/26
2014-03-18 | 21182 | 1417 | Muntz IL | K&B duct/ Fire Damper | 2014-03-18 |  | Closed 3/31 | fire damper ship 3/18 K&B ship 3/26

## April-Completed (hidden)
Follow-Up | 19979 | 224863 | Weatherford-LA | welding booths | ASAP |  |  | closed 4/1 | curtains ship3/24 To Weatherford, silencer at customers,vacuum branch recd 3/21 need 2 LED lights from taiwan
2014-02-24 | 21059 | 6252 | Performance Contractors LA | 2030 arms, brackets, duct, install |  |  |  | 4/2-4/3 Jason Mike | Matt 3/4/14 Sprial ordered 3/6/14 ship 3/17
Follow-Up | 20274 | 41772 | Sirchie | Lexan tops,Filter Bag | ASAP |  |  |  | installed lexan and duct
2014-02-24 | 21044 | 9640 | Herbalife Winston-Salem | Booth, blower, hood , arm, duct | 2014-03-17 |  | 20 | 4/14 Jason & Mike must be on site by 7:15 am | boothdelivered 4/4 , arm and blower ship out 3/7, duct needed , K&B ordered ship 3/17, warehouse req for stock submitted 3/11
2014-02-11 | 20998 | 102178 | Curtis Niagara | A Smoke 40 Duct F. Dampers valves |  | 1st stop | 131.11 | 4/22-4/27 Daniel - Duct arrives 4/22 | A Smoke shipping from Tx 3/12/14, duct, plenum receivd 3 14/ connection/ F. dampers ordered 2/26 Duct to ship4/10 & 4/16 Fire Dampers complete 3/14
N/A | 20675 | 57487 | US Steel-PA | Baghouse | Pickup ASMOKE 40 | 4th stop |  | 5/1-5/2 Daniel-Pickup Unit on Return from Curtis Screw-ODR 3000 | Mike Connors delivered hoods
| 21179 | 17290 | Global Precision Products-Rush NY | Mist 20 DEF 2000 | 2017-03-31 | 2nd stop |  | 4/27-4/28 Daniel | U S duct 3/26 and pulled shipped , fabricate Throttle valves, bleed in box, fire dampers done, and hepa filters 3/20, plenum ordered 3/24
2014-03-27 | 21229 | 2319 | QP Manufacturing-Ohio | Mist Stop, duct install |  | 3rd stop |  | 4/30-5/1 | Duct on order duct in warehouse, Deliver Mist Stop Unit. Run flex hose, install duct
2014-04-03 | 21246 | 2400 | Amsted Rail | Stat X First Re. Canisters | 03/31/14 got folder 4/3/14 |  |  | all shipped 4/7 CLOSE
2014-03-28 | 21236 | 8418 | Baldor | A mist 20/ p trap/ panel/ filter | 2014-03-28 |  | closed 4/10/14 | 3/31 P Trap shipped , system shipped 4/4, panel shipped 4/8
2014-04-11 | 21299 | 4700 | DSSI (Johnson Controls) | Stat X | 2014-04-11 |  |  | shipped over night 4/17 CLOSE
2014-03-18 | 21183 | 2995 | Sonic / GE Hitachi | Downdraft Tables | 2014-03-18 |  |  | SHIPPED 4/14/14
2014-02-03 | 20956 | 8680 | Mid-America | (8) silencers |  | Trial silencer |  | shipped 4/17 returning 1
2014-04-11 | 21301 | 862.11 | Delta | Duct K/B or US DUCT | 2014-04-11 |  |  | duct shipped 4/17 close
2014-04-22 | 20962 | 15084 | General Distributing | TMC-3-2 WB-6055 |  |  |  | shipped 4/22/14
2014-02-04 | 20965 | 9029 | General Dist. MT | Dust Collector & Booths | 2014-03-05 |  |  | Shipped designated truck 4/21- close
2014-04-16 | 21314 | 6273 | Honda of Canada | Fire Damper/ Filter | 2014-04-16 |  |  | Shipped 4/22 Close
2014-01-08 | 20840 | 25912 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump | 3/9/2014(MC advised not going to meet date) | color & texture critical | ab ships 3/10 | closed 4/24/14
2014-04-11 | 21296 | 97178.8 | Industrial Air Devices | A Smoke 3000 Statx | 2014-04-11 |  |  | all has shipped - close
2014-02-21 | 20999 | 23946 | Hawkins | Wet Scrubber/ silencer/ duct | 2014-04-01 |  |  | shipped 4/24
| 21310 |  | Stanadyne | Filter/ "Stat X/ Hepa | 2014-04-15 |  |  | stat x shipped 4/17/Hepa ordered/ Nano shipped 4/17
| 20921 | 2100 | Regency Sales | Hoods 6 |  |  |  | shipped 4/25/14

## May-Completed (hidden)
Order Date | SO # | SO | Customer | Scope | Install Date | Delivery Date | Inst. Hrs | Install Date | Comments
Total
2014-01-17 | 20894 | 44105 | (Magnum Engin)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum | 2/28/14 not confirmed |  | 72.16 | closed 5/1/14 | booths/ table shipping from LAX 4/8/ vacuum delivered 3/27
2014-03-21 | 19857 | Replacement | Johnson Controls | RM-6000 |  |  |  | Daniel & CJ leave 5/12 Install 5/13-5/14 | Bill Need to order duct
2014-03-26 | 21222 | 37947 | Schaeffler Group FT. Mill SC | 2 A Mist 40 Duct | 2014-03-31 |  |  | Jason -Mike 5/14-5/16 | Ordered (2) A Mist 3/27/14 to arrive 5/13 5p.m., US Duct ordered 5/6, plenum 5/6, work order 5/6 for inventory
2014-04-22 | 21285 | 8275 | Petron | Duct/ plenum inlet/ fire dampers inline | 2014-04-08 |  | need packing list for gripples 1 bag, | plenum bx 4/22 shipped / duct to pull from inventory 4/24/ fire dampers 4/24/ to ship , jacobs shipped 5/8/ CLOSE
2014-04-11 | 21232 | 42687 | Lakeshore Fittings-Grand Haven, MI | Duct & Install |  |  |  | Ecolo-Tech did the duct and install
| 18566 |  | Trenholm, AL |  |  | Duct to ship 5/6, all other supplies at location |  | closed 5/27/14 | phase 2 SO was closed, Bill to review original order, Ken to view materials on site/ duct ordered 4/15
Annual Maint. |  |  | Guilford | Filter Change | May 5 or 12 |  |  | Jason-Mike 5/12/2014
2014-05-05 | 21375 | 6511 | Truform | A Mist 20 , Panel | 2014-05-19 |  |  | All shipped CLOSE
2014-05-09 | 21401 | 125 | Winco | duct |  |  |  | shipped 5/13 CLOSE
2014-04-23 | 21156 | 11479 | Hi Cone | After Filter Housing |  |  | Scientific | shipped 5/15 CLOSE
| 21229 | 48.75 | Q P | Nema Housing |  |  |  | ordered 5/2/14
2014-04-03 | 21251 | 540 | Altec | 60 + 8 Filters | 2014-04-03 |  |  | John-Mark-David 5/17 | Filters ordered to ship to Avani est ship 4/16
2014-04-11 | 21297 | 6419 | Jarden | Duct Order-Diverter Valve | before 6/1/14 |  |  | all shipped- CLOSE
2014-04-04 | 21200 | 28028 | ELG Utica | Dust Collector |  |  | shipping 5/27 | shipped to customer 5/22
2014-05-13 | 21411 | 14950 | MarbleFall High School | 10 booths no tables hardware/ curtain rods |  |  |  | closed 5/23
2014-01-07 | 20720 | 21948 | GE-Greenville SC | WB-6057G & TMC5-2 | Charles to confirm delivery |  |  | closed 5/22
2014-05-22 | 21448 | 220.62 | Winco MFG | 2 Y branches/ 1 reducer |  |  |  | ordered pcs 5/22 to ship 5/28
2014-04-11 | 21295 | 4668 | Airex | SPC 2000 Arm 2030 Expl proof motor | 2014-04-11 |  | motor ship 5/19 | All Shipped 5/28 CLOSE
2014-05-09 | 21399 | 8453 | Thomson Linear LLC | A Mist 20 / Duct | 8453 | send plenum then close |  | All shipped 5/27 CLOSE
2014-05-19 | 21431 | 1684.34 | Ashland Chemical | Steel Duct |  |  |  | shipped 5/22 close
2014-05-23 | 21450 | 11177 | Salem Tools | Mist 20 ctrl panel, stat x | 2014-05-27 |  |  | all shipped 5/30 close

## June-Completed (hidden)
2014-05-29 | 21458 | 4000 | GE Greenville, SC | Added install to drop ship order |  | 2014-06-09
2014-05-09 | 21391 | 63498 | Schaeffler SC | Absolent Mist 80 (2) |  | 6/10-6/11
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10 |  | 6/11-6/12
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20 |  | 6/9-6/11 Jason
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055
2014-06-05 | 21498 | 3287.4 | Absolent Install Graco In SD | K&B | 2014-06-23 | Bill Boisvert 6/23 | duct ordered, airline , car, hotel scheduled duct shipping 6/13
2014-04-30 | 21348 | 34417 | Curtis Niagara,NY | Absolent/ duct/ |  | Daniel Mike install 6/24 | Install complete CLOSE
2014-06-23 | 21580 | 942 | Altec Industries Inc | Duct work | 2014-06-23 | Jason 6/28/14 Noon | install complete close
2014-05-30 | 21460 | 13637 | DENSO manufacturing | A Smoke 20 Control Panel P Trap |  | ALL SHIPPED CLOSE
2014-05-30 | 21470 | 3000 | Pekin Community School | (6) welding Booths
2013-03-13 | 21166 | 6331.65 | Hydromat Maryland | A Mist 20 and Mist Pump |  | all shipped CLOSE
2014-06-03 | 21487 | 2632.95 | Zeus Aiken SC | Duct Master and K&B |  | All Shipped 6/411 and 6/12 CLOSE
2014-05-20 | 21439 | 3313.5 | Honda-Alliston, ON | Duct |  | shipped 6/13 CLOSE
2014-05-20 | 21440 | 6422.24 | Honda-Alliston, ON | Duct |  | shipped 6/13 CLOSE
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm |  | shipped 6/12 and 6/16 CLOSE
2014-06-12 | 21521 | 4665.14 | US Engine Valve SC | Duct | 2014-06-15 | shipped 6/24 CLOSE

## July-Completed (hidden)
Follow-Up | 19854 | 248508 | LATTC | modify grinding table | ASAP |  |  |  | shorter arms delivered to customer, (3) grinding tables need modified
2014-05-09 | 21394 | 39900 | Airgas/ T H Harris Campus | 40 red welding booths | 2014-06-30 |  |  | Shipped 6/27 close
2014-06-16 | 21548 | 6013 | LakeShore Fittings Michigan | A Smoke 5 leg supports | 2014-06-30 |  |  | shipped 6/26 CLOSE
2014-06-25 | 21590 | 3689 | The Timken Company | Filters b- valve- clamps | 2014-07-07 |  |  | shipped 7/3 close
2014-05-01 | 21360 | 12225 | CareFusion | Abs. Mist 20/ filters/ training | 2014-05-14 |  |  | filters shipped 5/21, syst shipped 5/19 training In Mx by Bill
2014-06-30 | 20676 | 57928 | RBW of Canada | duct K & B | 2014-07-07 | not our install |  | duct shipped 7/9 close
2014-07-04 | 21629 | 1440 | Eaton Roxboro-NC |  |  |  |  | Bill & Daniel & Matt C 7/21 | completed 7/11/14
2014-07-08 |  | repair | Schaeffler - Cheraw |  |  |  |  | CJ 7/10 between 11-12
2014-07-09 | 21641 | 370.33 | Proveedora De Seguridad | clamps | 2014-07-09 |  |  | shipped on 7/10 close
2014-04-30 | 21357 | 8350 | Crown Battery/ Regency | Arms/ floor stand/ |  |  | LAX 6-23-14 | shipped 7/8 close
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct |  |  | Fred&Matt | Closed
2014-07-08 | 21628 | 1000 | ThyssenKrupp Presta | Duct with customized pcs | 2014-07-20 |  |  | shipped 7/16 Close
2014-07-14 | 21642 | 74 | Proveedora De Seguridad | fire dampers | 2014-07-09 |  |  | Shipped 7/16 close
2014-07-08 | 21633 | 1070 | Standayne | Stat X AV1000 |  |  |  | shipped 7/14 close
2014-04-10 | 21288 | 7991 | Gosiger/ Tect Aerospace | AB A Mist 20/ Duct | 2014-05-30 |  |  | system shipped 5/22, duct shipped 7/17 close
2014-06-04 | 21491 | 21200 | Ecolotech / US Manufacturing | A Smoke 40 B , Contrl Panel, P-Trap, Stand |  |  |  | ordered system, ordered panel, shipped P Trap & Mounting stand
2014-07-03 | 21501 | 4601.94 | Norris Building | control panels 2 customed |  |  |  | shipping 7/21
2014-07-08 |  | repair | Stanadyne | Wire Stat-X, return motor, deliver filters | install when filters arrive - see cheryl |  |  | Bill 7/24 at 2:00
2014-04-01 | 20557 | Maintenance | Guilford Tech GTTC | Filter change out |  |  |  | 2014-07-28 | Last filter required shipped 7/23 all others pulled frm warehouse
2014-07-08 | 21636 | 14869.69 | Sterling Springs IL | panel |  |  |  | shipped on 7/24 close
2014-07-28 | 21723 | 181 | Stanadyne | Statx wire | 2014-08-01 |  |  | wired ordered and shipped 7/30 close
2014-07-30 | 21736 | 395.68 | Deutsche Precision | Fire dampers 2 | 2014-08-01 |  |  | work order and packing slip to warehouse 7/30
2014-06-17 | 21553 | 6748 | RSS Grinders and Automation Inc | AB A Mist 6 C (2) stands ( 2) | 2014-08-04 |  |  | shipped 7/31 close

## August-Completed (hidden)
2014-04-21 | 21320 | 148236.7 | Truform Parker Fasteners, AZ | A Smoke 40, (28) 1220 Arms |  |  |  | NO AVANI INSTALL | Completed Close
2014-05-07 | 21385 | 152351 | Airgas Masscon, Westmoreland , PA | SDC-AT-4-48, 22 arms, Duct |  |  |  | Jason-Mike 7/28/14
2014-07-21 | 21686 | 1675.38 | Kennametal Weldon NC | Jacobs duct | 2014-07-29 |  |  | shipped all 7/31 close
2014-06-26 | 21595 | 330 | Shepard Air Force Base | (2) Welding Booth Light Switches |  |  |  | on order from Taiwan asked to be air frieghted
2014-07-15 | 21669 | Warranty | GE Greenville, SC | vacuum system |  |  |  | Daniel & CJ 8/5 | duct shipping 7/22 plenum ordered 7/15/
2014-06-17 | 21556 | 5037 | United Grinding | ODF 1000 collector, plenum, P Trap | syst ships 8/8, p trap and plenum ship 8/1 |  |  | request to ship out 8/1 to warehouse
2014-05-22 | 21437 | 22392 | Haun/ Northern Catskills | 16 welding booths | 2014-07-16 |  | must call customer before releasing | truck in 8/8 packing slip to shipping 8/8
2014-07-28 | none | 2396.73 | Constrata | duct | 2014-08-01 |  |  | ordered as stock per Ed, bring to Avani and customer will pick up and pay duct ships 8/1
2014-01-23 | 20903 | 11202 | Wolf Tech-Kingston, NY | Electrical Panel |  |  |  | 8/25 Daniel CJ | Duct ships 7/17
2014-01-23 | 20904 | Warranty | Wolf Tech-Kingston, NY | Paint |  |  |  |  | electrical panels on order
Modification | 21377 | Warranty | Gaithersburg VA | Replace Fan(s) |  |  |  | Jason & Mike 8/11 | all in port wilmington 7/31
2014-05-30 | 21478 | 26384.65 | Keller Tech/ Great Lakes Mach-Tonawanda, NY | A Smoke 40, duct | 2014-06-30 | customer asgreed to 8/11 & 8/12 |  | Daniel-CJ 8/10/14 (stop #1) | All shipped from Avani 7/10/2014, duct shipped from K&B 7/21
2014-03-19 | 21133 | 31729 | Granite Co Sch. Brockbank Jr. Hg,UT | Baghouse/ Shaker | 2014-06-03 | shipped to customer |  | 8/11/14 NO AVANI INSTALL | notify Absl and Jacobs when to ship,connect flange, plenum/ control panel here
2014-03-19 | 21134 | 31729 | Granite Co.Sch Kearns Hg Office,UT | Baghouse/ Shaker | 2014-06-03 | " |  | 8/11/14 NO AVANI INSTALL | all in port 7/31 wilmington
2014-03-19 | 21136 | 29510 | Granite Co Sch Kearns Jr. Hg,UT | Baghouse/ Shaker/ Duct | 2014-06-03 | " |  | 8/11/14 NO AVANI INSTALL | all in port 7/31 wilmington
2014-08-05 | 21762 | 1899 | Truform Equipment Posen IL | SPC 1000 Arm 1620p duct | 2014-08-05 |  |  | shipped 8/14 close
2014-08-05 | 21737 | 3798 | Jacobson Mg Media Ohio | SPC 1000 Arm 1620p duct | asap some already shipped by cheryl 7/31 |  |  | shipped 8/14 close
2014-08-07 | 21766 | 900 | Proveedora | (6) 6" Fire Dampers
2014-08-07
2014-08-14 | 21793 | 6938.9 | The Timken SC | Mist 20 / K& B /plenum bx | 2014-08-22 |  |  | all shipped by 8/21 close
2014-05-28 | 21397 | 25000 | Tennessee Rand | Wet dust collector |  |  |  | shipped on 8/15 close
2014-06-30 | 21603 | 2962 | Centurion Tools LLC, VA | duct and install 1 day |  |  |  | Daniel - CJ 8/21/14 | emailed customer about installation date 8/4 again
2014-05-21 | 21443 | 21233 | Defense Fin and / Accounting | Booth/ down draft table/ portable | tble in port 7/30/ warehouse to dismantle booth needs to ship mid august |  |  | shipped 8/22 close
2014-08-15 | 21806 | 943 | Honda of Canada | duct K&B | 2014-09-12 |  |  | Shipped 8/25 close
2014-06-05 | 21497 | 31775 | Kiffer Industeries/ CMC -Hope AK | SDC-15-16, duct, | 2014-08-01 |  |  | Duct Inc 8/18/2014 (in port 7/30) (lax7/30-clear customs8/6) | ordered Asmoke 40 6/2/14, duct ready to ship 7/3
2014-08-14 | 21793 | 6938.9 | Timken Co Union SC | Amist 20/ Duct K&B Plenum | 2014-08-22 |  |  | shipped 8/26 Close | absolent 8/26 delivery
2014-08-22 | 21830 | 655 | Parker Hannifin Corp | Mist Pump | 2014-08-29
2014-05-21 | 21442 | 31050 | Kiffer Industeries/ CMC Taylors, SC | SDC-15-6/ duct | 2014-06-20 |  | 15 | Daniel-CJ 8/25/2014 (in port 7/30) (lax7/30-clear customs8/6)/ duct shipping 8/13

## Sept-Completed (hidden)
2014-08-26 | 21847 | 329.13 | Alotech Sandford, NC | Gauge, Pilot Valve Hose & clampa | 2014-08-26 |  |  | all delivered close 9/2/14
2014-06-25 | 21587 | 388 | United Grinding | Plenum 8 " P Trap 1 | 2014-12-01 |  |  | shipped 9/3 close
2014-09-03 | 21875 | 1846.78 | 1st Hope Fire Ext Oxford, NC | stat-x canister linear heat cable | 2014-09-10 |  |  | shipped 9/5/2014 close
2014-07-08 | 21635 | 58469 | Coastal Welding Supply | 20 SDT 180 1 fan 60 hp cust duct | no later 8/31/2014 | fan & duct arrives 8/26 |  | All completed close 9/3
2014-09-02 | 21861 | 5870.66 | Stackpole International Ancaster Canada | Mist 6 C Duct motor 575 hp |  |  |  | shipped 9/09 close
| 21907 | 786.61 | Honda of Canada Ontario | duct | 2014-09-10 |  |  | Duct ordered and shipped 9/10 close
2014-09-09 | 21901 | 200 | Duer Carolina Coil Greer, SC | Fusible Fire Damper Links 20 |  |  |  | Shipped 9/10 close
2014-09-04 | 21874 | 779.8 | Zeus Industrial Products | K & B duct pieces |  |  |  | shipped 9/10 close
2014-09-11 | 21912 | 2174.05 | Kennametal Asheboro, NC | duct | 2014-09-13 |  |  | Shipping on 9/12 over night close
2014-08-26 | 21852 | 3368.36 | Stanadyne Jacksonville, NC | filter statx 1000 venturi | 2014-09-08 |  |  | all has shipped close
2014-09-03 | 21868 | 8725.22 | Alcoa Fastening System Waco TX | duct | 2014-09-12 |  |  | all shipped close
2014-09-12 | 21918 | 868.76 | US Engine Valve Westminister | duct | 2014-09-12 |  |  | all shipped close
2014-08-15 | 21803 | 2818.36 | Jarden Columbia, SC | diverter valve | 2015-08-14 | need flanges from Jacobs |  | all shipped close
2014-09-03 | 21874 | 779.8 | Zeus Industrial Gaston SC | duct K & B | 2014-09-12 |  |  | shipped 9-10 close
2014-09-10 | 21898 | 361.99 | The Timken Honea Path, SC | Duct and hose | 2014-09-23 |  |  | all shipped close
2014-09-10 | 21908 | 1366.65 | Jernberg Indust Bolingbrook Il | duct | 2014-09-24 |  |  | shipped 9/22 close
2014-07-24 | 21640 | 9995 | Caterpillar Engine System | A Mist 20S Duct F Dampers Pleneum | 2014-09-30 | dj | ask fred approval of drawing | all has shipped 9/22 close
2014-09-19 | 21956 | 750 | R A Zweig Glenview IL | Duct | 2014-10-02 |  |  | shipped 9/23 close
2014-09-19 | 21940 | 4521.5 | Ventarie Burnsville | Customized SPC 3810 |  |  |  | shipped 9/30 close
2014-07-01 | 21616 | 18258 | Kennametal Inc, NC | A smoke 20 Fire Trace installation | Need to advise Customer of date for install |  |  | Bill 9/25/14 | A Smoke ships 9/16/ fire trace ship by 8/29

## Oct-Completed (hidden)
2014-09-12 | 21851 | 1735 | Advanced Engineering Apex Diver | spark trap | 2014-08-28 |  |  | shipped 10/1 close
2014-07-28 | 21718 | 11482.25 | Bristol Industries Truform | A Smoke 20 Panel VDF Plenum | bring to Avani |  |  | all received and shipped 10/2 close
2014-08-08 | 21771 | 6976 | Tennessee Rand | duct | 2014-09-02 |  | more duct to order | all shipped by 10/2 close
2014-08-28 | 21851 | 1735 | Advance Engineering | Flange InLet |  |  |  | shipped 10/1 close
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel |  | Ed wanted Jason/ Bill to install
2014-10-02 | 21987 | 1597 | Amsted Rail PA | control box / starter |  |  |  | shipped 10/6/2014
2014-10-08 | 22014 | 385.52 | Kennametal Inc | jacobs duct |  |  |  | delivered 10/8/14
2014-10-06 | 22001 | 544.8 | Zeus Indust Prod Gaston, SC | duct 20 pcs |  |  |  | shipped 10-8 close
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains | Ken?? customer wants to hold for 60 days | 5 booths |  | shipped 10/9/14 closed
2014-08-27 | 21853 | 36222 | Dyad Construction | (26) eco-1066 & (26) curtains | 2014-11-11 |  |  | all shipped close
2014-10-13 | 22034 | 112.7 | Kennametal Weldon,N C | flanges | 2014-10-16 |  |  | shipped 10/14 close
2014-09-26 | 20535 | 10800 | Cooper & Company | Install (10) 5055 Booths |  |  |  | 10/13 Daniel & Mike | install done 10/15 close
2014-08-11 | 21775 | 30121.15 | Mt. Olive University Mt. Olive NC | Fan, Arm, Duct | 2014-09-19 |  |  | Jason, CJ | Install complete close
2014-10-07 | 22012 | 165.6 | Caldwell AL | prefilter poypad with track | 2014-10-13 |  |  | frame ordererd 10/14 work order in folder
2014-04-30 | 21355 | 152966 | Amstead Rail-Camp Hill, PA | ABH-192-10 Baghouse,Fan, BM8005 Boom,Arm | 2014-07-31 | Install Gauge |  | Daniel-Mike 10/24 | Close Out
2014-07-10 | 21650 | 3397.09 | Altec Industries | duct and install 1 day | 2014-07-11 | matt to ask customer
2014-09-04 | 21798 | 11420 | National Machinery Tiffin Ohio | A Smoke w/ cust paint/ cap off and move inlet | shipping to avani |  |  | shipped 10/20 close
2014-05-08 | 21391 | 63498 | Schaeffler SC | Install second duct |  |  |  |  | Duct to ship 10/13
2014-10-15 | 22043 | 3111.56 | Stanadyne | Statx 1000 Filters |  |  |  | all shipped close
2014-10-13 | 22035 | 3767 | Tennessee "Tech Center | K & B duct/ winter/summer gates | 2014-10-24 |  |  | duct shipped 10/21 close
2014-10-23 | 22063 | 1000 | Stanadyne | Stat X 1000 E |  |  |  | shipped 10/23 close
2014-10-09 | 22016 | 5355 | Barnes International Rockford | Jacobs Duct/ Rect aRound | 2014-10-16 |  |  | All shipped Close
2014-09-24 | 21970 | 23644 | NSK Bearing Man. | A smoke 5 duct | 2014-10-03 | order 6" flex, hose clamps, 5-6 reducer, raw connector 6" |  | all crossed border shipped close
2013-12-16 | 20754 | 41076 | Eaton Roxboro-NC / multiple installs | A Smoke40 & Asmoke 1200 |  | continuing into 2015 |  | multi stage project invoice after each stage | need to balance system
2014-06-30 | 21615 | 5786.93 | Eaton Roxboro-NC | duct and install |  |  |  |  | install done close
2014-07-15 | 21629 | 1440 | Eaton Roxboro-NC | install only |  |  |  |  | install done close
2014-08-13 | 21782 | 4892 | Freeport McMoran El Paso, TX | project management | 2014-09-30 |  |  | closed

## Nov Complete (hidden)
2014-10-27 | 22086 | 1310 | Hydromat Inc Maryland, MO | Mist 400 Mist Pump ( 2) | 2014-10-30 |  |  | shipped 11/3 close
2014-10-27 | 22090 | 1003 | Cianflone Scientific Pittsburg PA | SPC mini Used custom Hose | 2014-11-27 | not our installation |  | shipped close
| 22109 | 586.8 | Brennan Kamatics Corp Bloomfield Ct | Arm 0710p Mting Brackets 3" light kit duct work | 2014-10-29 |  |  | shipped 11/4 close
2014-09-30 | 21984 | 3982 | Lakeview Public Schools St Clair MI | welding booths curtains brackets arms |  |  |  | shipped 11/3 close
2014-07-08 | 21632 | 40847 | Magna P. T Canada | AB A Smoke 20 ( 2) AB A Mist 10 (3) | motor different | one unit here to ship waiting on door | Cheryl ordered on 7/8 | Last system shipped 11/3 close
2014-11-05 | 22075 | 1519.62 | amstead Rail | silencer
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan |  |  | 309.53
2014-10-30 | 22112 | 135 | Tennessee Rand Chattanooga | duct stand customize | 2014-10-29 |  |  | shipped close
2014-09-24 | 21960 | 5053 | Mid Atlantic Boiler Lenoir NC | Fan |  |  |  | shipped close
2014-10-27 | 22081 | 4865 | Barnes Rockford IL | Duct | 2014-11-09 | no deposit per Ed |  | shipped close
2014-11-05 | 22148 |  | The Timken Co Union SC | 6" pipe/ 6" clamps/ adjust nipple 6" |  |  |  | shipped 11/11/14
2014-08-26 | 21846 | 77683 | Boilermakers Local 69 | Silencer/ duct/fan/ arm 2020 | 2014-10-30 | not our install |  | Ken-installer also doing duct | Install complete close
2014-09-15 | 21920 | 74141.28 | Doosan Intra. / Pea International | A Mist 10 5/ leg ext / duct | 10/31/14 1/10/15 3/2015 | robbie to make leg extensions |  | duct ships 10/7 to avani spiral one day ship for m. duct get there by 10/27 NEED Legs
2014-11-10 | 22163 | 894.46 | McClain Tool | Jacobs Duct | 2014-11-24 |  |  | all shipped 11/13 close
2014-11-13 | 22177 | 146.25 | ThyssenKrupp | 8" clamps |  |  |  | shipped 11/18 close
2014-11-04 | 22127 | 1320 | TRW Fuji Valve | fire dampers 6" ( 8) | 2015-11-10 |  |  | shipped / close
2014-11-06 | 22144 | 5037 | United Grinding Miamisburg OH | A Mist 10 ( 1) Pleneum (1) Water Seal Can |  |  |  | all shipped closed
2014-09-25 | 21971 | 10584 | Kaliburn Inc Ladson SC | install 28 filters, clean machines | 2014-10-17 |  |  | completed close | filters in warehouse , clean units, install filters, haul off old filters
2014-07-07 | 21627 | 21627 | Cummins Inc No. Charleston, SC | A Mist 60 A mis 40TF Duct | 2014-09-30 |  |  | waiting on aproval of drawings,return air | Install complete close
2014-04-01 | 20557 | Maintenance | Guilford Tech GTTC | Filter change out |  |  |  |  | FINAL 2014 IN NOVEMBER LARGEST CHANGE OUT
2014-08-29 | 21869 | 2040 | Masterbrand Cabinets, Kinston NC | filter change | Need Po & Date from customer | one day (7) people |  | Jason, CJ, Sam, John, Mark ,Mike, Daniel (need 7)collectors 640 bags

## Dec Complete (hidden)
2014-11-24 | 22218 | 1003 | Cianflone | spc mini & flex hose |  |  |  | shipped 12/1 close
2014-11-03 | 21238 | 27775 | DYNA MIG Mfg Stratford ON | A Smoke 40/ Stand/ Duct | not our installation | duct ship 11/10 system ship 10/22 WHERE IS STAND? |  | All shipped 12/1 close
2014-10-24 | 22066 | 79527 | Vegas Fasteners Nevada | Amist 40 (3) arms2030p (1) Mist 10C (1) Mist stop prefilters (3) Portable filtration (1) Duct mist pumps(3) Stands (3) | 2014-11-20 | duct order pending |  | 12/1 duct inc | system shipping 12/15
2014-09-30 | 21976 | 46345 | Medtronic Puerto Rico | A Smoke 40 duct fire dampers |  |  |  |  | system and avani shipmt on site/ duct to arrive 11/10
2014-10-06 | 22006 | 29897.68 | Ecolo Tech/ Dana Light Indiana | A Mist 80 Arms 3 brackets control panel filter | 2014-10-06 | system ship 12/5 control panel adapter and p trap ship 11/12 |  | all shipped close
2014-12-04 | 22247 | 388 | United Grinding-Miamisburg,OH | 8" plenum water can | over night |  |  | all shipped over night close
2014-09-30 | 21958 | 32148 | Laredo Comm College Laredo TX | welding booths / |  |  | lax 11/17 | cust still issuing customs docs vendors ask quest
2015-11-03 | 22110 | 395.68 | Deutsche Precision MO | fire dampers 2 jacobs | 2015-11-07 |  |  | packing slip to warehouse 11/3
2014-11-05 | 22151 | 16787.28 | Kennametal Weldon NC | A Mist 10 ( 3) fire dampers/ duct | 2014-11-17 |  |  | duct ship 11/13 dampers ship 11/14/ systems ship 12/1
2014-11-20 | 22205 | 787.6 | Kennametal Weldon NC | y branches and clamps | 11/19/2014 over nighted | need information about sizes
2014-08-19 | 21808 | 13199 | Airgas P.A Rail Car Co Mercer, PA | add to slide rail | Dust Collector Duct | 2014-09-05 |  |  | last install completed 12/11 close
2015-08-05 | 21757 | 47931 | GE Electric Grove City, PA | Air return to building Need rect 90 | 2014-10-01 |  |  | 2014-12-09 | last install completed 12/09 close
2014-02-02 | 22238 | 350.7 | Tennesse Rand | Jacob Duct |  |  |  | to shipped 12/10 close
2014-08-04 | 21747 | 17641 | Lynar Corporation Allentown, PA | A Mist 40 TF Duct ( jacobs) | 2014-08-04 | duct order | watch back ordered | System shipping 8/8, duct ships 12/11
2014-12-02 | 22237 | 4046 | Elgin Community College | motor SDC 25 M from Taiwan | 2014-12-16 | 2014-12-04 |  | shipped 12/12
2014-05-30 | 21468 | 32518 | Airgas/ Pa Rail Co. Mercer, PA |  |  |  |  | 2014-12-10
2013-12-11 | 20735 | 156500 | Wolf Tech-Kingston, NY | Install Hinges |  |  |  | 12/11-12/12
2014-12-11 | 22285 | 1181.64 | Alotecch- Sanford, NC | Misc Duct
2014-12-15 | 22293 | 658.85 | Kennametal Inc. | Jacobs duct pieces
2014-08-19 | 21809 | 29070 | Airgas Laredo Job Crop Center Laredo, TX | Arm (6) ECO-3000 Drums in stock Cust. Duct | 2014-09-17 |  |  | Scheduling install but advised by Richard 12/9 that layout is going to change | All has shipped by 9/18 install needs to be done, LAX shipment
2014-12-17 | 22295 | 4950 | Altec- Creedmoor, NC | K & B Duct Install |  |  |  | 12/20-12/21
2014-12-17 | 22296 | 4950 | Altec- Creedmoor, NC | K & B Duct Install |  |  |  | 12/20-12/21
2014-10-24 | 22078 | 136567 | Freeport McMoran El Paso TX | A Smoke 40 VFD Control Panel, Floor Stand , Ext Booms, Arm 2030 , Customized Fume Arm Hood, Duct, Pleneum Prefilter | 2014-12-15 |  |  | 12/.15 Jason & duct inc to do the install | plenum/ stands ordered 10/30 duct to ship 12/2
2014-12-19 | 22315 | 489 | Lake Region Medical Center- Orchard Park, NY | (2) 6" fire dampers & US Duct order
2014-08-08 | 21773 | 13801 | PCB Piezotronics of NC | Collector . Duct | 2014-11-28 | 2014-12-23 |  | return with new hood, damper and clamps | collector in Wil 11/13 Duct at Avani 11/3/ hose ordered
2014-12-10 | 22280 | 1848.13 | Machine Laboratory | US Duct Order |  |  |  | duct ordered 12/11 shipping 12/19
2014-11-11 | 22167 |  | Barnes | Jacobs Duct | 11/1414 |  | complete
2014-12-02 | 22239 | 5355 | Barnes | Jacobs Duct |  |  | complete | duct shipping 12/11 from vendor
2014-10-29 | 22094 | 1497 | Barnes | duct plenum flex hose | 2014-11-07 |  | complete
2014-12-16 | 22298 | 135 | Tennessee Rand | duct stand |  |  |  | close 12/23/14
2014-11-18 | 22196 | 3384 | CSX Transportation | (1) ECO Welding Booth, SBU-1.5 with 1620 | 2014-12-16 | ASAP |  | shipped 12/16/14
2014-11-13 | 22179 | 42475 | DM Squared - King, NC | A Smoke 20 (2), Jacobs Duct | 2014-12-13 | No deposit required |  | Install 12/29 | duct ships 12/18, absolents on site, plenums and fire dampers ordered
2014-11-05 | 22149 | 18426 | East Penn Mfg Co ( Wann Air) | (1) A Smoke 40B/ metal filter kit/ motor starter |  |  | ship 12/26 | absolents to ship 11/11 req tracking 11/7
2014-11-05 | 22150 | 37132 | East Penn Mfg Co ( Wann Air) | A Smoke 40 (2) filters (80) Man. Motor 2 |  |  | ship 12/26 | absolents to ship 11/11 req tracking 11/7
2014-12-19 | 22318 | 1928.58 | Delta Faucet - Jackson, TN | K & B Duct |  | ships 12/30 |  | requested c sithes to order 12/22/14

## Jan 2015 Complete
2014-06-17 | 21554 | 121283.66 | Sunnyvale Dist. (Bloom)Center-Sunnyvale, CA | Grinding Booth,SDT-1.5, |  |  | 50 | 2015-01-12 | Act shipping by 10/27/ duct to arrive 11/10 customer informed
2014-10-17 | 22048 | 29559.58 | Sunnyvale 2 Bloom | SDT 7.5 Chute Grinding Booth Scales | 2014-12-26 | customizing |  | grinding booth downdraft table being delivered 1/5/15
2014-12-23 | 22230 | 925 | Honda of Canada | K & B Duct & 8" K&B Fire Damper | need by 1/10/15 |  |  | K&B ships 1/6/15, FD ships 12/30/15
2014-08-05 | 21760 | 11387.81 | Morris South Charlotte, NC | Collector, Duct | 2014-11-10 | Duct,plenum/connections to be ordered |  | 2014-01-08 | systemon per mark ship 11/19 cust wants mid Dec.duct ships 12/23 (1) day inst.
2014-09-05 | 21883 | 9540 | Borg Warner-Arden, NC | (3) Absolent Filters-Jacobs Duct | 2014-09-27 |  |  | 1/6-1/7/2014 | 3 filters in whs. duct ships arr.12/9
2014-12-19 | 22321 | 1070 | Stanadyne- Jacksonville, NC | stat-x 100E |  |  | close 1/10/15 | request c sithes to order 12/22/14
2014-12-17 | 22301 | 10888 | Curtis Niagara | Jacobs duct and install |  | order cancelled |  | need duct layout | MC and DT to visit week of 2/5/15
2015-01-15 | 22393 | 186.24 | Delta Faucet-Jackson, TN |  |  |  |  | shipped 1/13/15
| 2014-11-04 | 22142 | 10070 | Portersville Valve - Airgas- Portersville, PA | (1) paint booth
| 2014-12-23 | 22327 | 1560 | Sirchie- Youngsville, NC | Hose, Duct, Install | 2015-01-20 |  |  | waiting on arrival of flex from Masterduct | requested Chaz to order 12/23/14