## Installs
|  |  |  | INSTALLATIONS |  |  | 2014-01-31
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-06-21 | 20072 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets |  |  |  | arms, arm stands at Avani
2013-09-16 | 20387 | NCMT Mexico | A-Mist 10 |  | at broker | Abraham or John -Solo | everything needed is at brokers,take p-trap
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500 |  |  | 1/26 - 2/3 Both Crews | us duct order going out 24th, leave early am,
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20 |  | Duct ship 2/4/14 | date | duct shipping 2/4/14, plenum & mist pump shipped,P Trap
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20 | customer to advise | duct delivery 1/30/14 |  | shipped (1)plenus,(11)fire dampers,gripples&hardware, Take P-Trap
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40 |  | 2014-01-31 | matt to check with Fred | Fred is working with customer on intall date
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10 |  | absolent on site | 2/9-2/13 Jason&Mike | duct on site,shipped plenum, cyclone,ptrap,gripples
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21 |  | absolent on site | 2/17-2/19 Dan & Abe | stand and cradle at Avani, P-Trap
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20 |  | absolent on site |  | magna has not released remaining duct from Jacobs,shipped 3 plenum boxes,mist pump boxes 3
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth | 2/28/14 customer |  |  | taiwan needs drawing confirmation,waiting for customer approval
2013-12-12 | 20744 | Meigs Local School | Down Draft Table |  | SDCAT416 1/13/14 |  | awaiting duct layout from MC,downdraft table here, light kit here,portable filtration here
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200 | 2014-02-15 | AB- 1/20/2014 |  | Duct ship 2/13, Build12" Dampers& 12" Plenum Boxes
2013-12-20 | 20786 | Truform-Rightaway, IL | AB-A Smoke 40 | 2/1/14 per Fred |  |  | Duct and internal frame required waiting approval from customer
2013-12-26 | 20799 | General Distributing | SDC-30-16MD,duct,arms,silencer |  | 2/24/14 collector |  | need duct layout from MC,silencer
2013-12-27 | 20806 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan | 7/31/14 -customer |  |  | absolent ordered 1/16/14, fan, wiring
2014-01-15 | 20880 | Stanadyne | Filters |  |  | 2014-01-27 | shipped to Stanadyne to be received 1/30
2014-01-17 | 20894 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum | 2/28/14 not confirmed
2014-01-23 | 20903 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | Wolf Tech-NY | Paint Booths
N/A | 20675 | US Steel-PA | Baghouse | ASAP | baghouse ships1/31/2014 | 2/4/14 Bill | duct ships1/17-transition shipped from avani,2 hoods on order
Follow-Up | 19979 | Weatherford-LA | welding booths | ASAP |  |  | ordered control panel, ordered one silencer,shorten arms,move on/off?
Follow-Up | 19854 | LATTC | modify grinding table | ASAP |  |  | shorter arms on order, (3) ginding tables need modified
Follow-Up | 20274 | Sirchie | Lexan tops,Filter Bag | ASAP |  |  | lexan ordered, matt to order filter bag
Maintenance |  | Guilford Tech-Jamestown,NC | Filter change out | 2014-03-01 |  |  | Barb to order filters
New |  | Altec | Filter change out
Courtesy Call |  | Accellent | Balance Absolents | 2/4 9AM |  | 2/11/2014 Bill
| 20629 | Peterson | Welding Booths |  |  |  | Production Stopped-Ed

## Drop Bill Ship
|  |  |  | Drop-Ship-Bill |  |  | 2014-01-31
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2013-12-19 | 20781 | CMS-Waco TX | Duct |  |  |  | Bryan to advise
| 20587 | NSK-Mexico | Jacobs Duct |  |  | shipped 1/17/14 | avani shipping is handling
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | 2014-02-10 |  | shipping 1/31/14 | Muhammed to dleiver 1/30 ship 1/31
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit | Must arrive before 5/28/14
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay |  |  |  | Fred to advise
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2) |  |  |  | (2) being modified in warehouse
2013-10-02 | 19858 | Bernard Mechanical Contractors | system&curtains | customer wants to hold for 60 days |  |  | system & curtains in warehouse-
2013-12-02 | 20535 | Cooper & Company | WB-5055 | none | at Avani 1/7/14 |  | Ken contacted for delivery
Warranty | 18869 | SunRright Disc | Lexan Top, exchange SDT-3 For SDT-1.5 |  |  |  | lexan ordered
2014-01-07 | 20720 | GE | WB-6057G & TMC5-2 |  |  |  | CS ordered
2014-01-08 | 20840 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump | 3/9/2014(MC advised not going to meet date) |  | ab ships 3/10 | absolent on order, mist pump to build
2014-01-08 | 20837 | Wann Air Systems | Asmoke,Motor,Filters | 2014-01-31 |  |  | absolent ship2/20,motor recd 1/13,filters
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct |  |  | 1/30/2014 & 2/6/14
2014-01-13 | 20865 | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers
2014-01-23 | 20909 | Proveedora | US Duct | ASAP |  | 2014-01-30
2014-01-23 | 20910 | Proveedora | US Duct | ASAP |  | 2014-01-30
2014-01-27 | 20931 | Templeton | silencer, clamps, extension | asap |  |  | all ordered
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets
2014-01-29 | 20563 | Fireaway - TRW Fuji Valve | wire & resistors
| 20738 | Curtis Screw | Absolent Filters (3) |  |  | 2014-01-31

## Open Orders12-31-13
Open Orders as of 12/31/13
Order Date | SO # | Customer | Scope
Installations
2013-09-16 | 20387 | NMCT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke
2013-12-20 | 20550 | Truform-Rightaway, IL | AB-A Smoke 40
2013-11-29 | 20675 | US Steel-PA | Baghouse
2013-05-29 | 19979 | Weatherford-LA | welding booths
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
| 19854 | LATTC | replace 26 mother boards install flex on sdt1400s
| 20851 | Curtis Screw | Run Duct to new machine
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
2013-12-19 | 20781 | CMS-Waco TX | Duct
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-11-06 | 20587 | NSK-Mexico | Jacobs Duct
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2013-10-02 | 19858 | Bernard Mechanical Contractors | Curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Case | 18869 | SunRight Disc | Lexan Top, exchange SDT-3 For SDT-1.5
Case | 20843 | Mustang | WB 1055
New | 20751 | US Engine-SC | Branch
New | 20720 | GE | WB-6057G & TMC5-2
2013-07-13 | 20131 | North Central Technical College | welding curtains

## Open Orders 1-31-13
Open Orders as of 1/31/14
Order Date | SO # | Customer | Scope
Installations
2013-06-21 | 20072 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | NCMT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200
2013-12-20 | 20786 | Truform-Rightaway, IL | AB-A Smoke 40
2013-12-26 | 20799 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-15 | 20880 | Stanadyne | Filters
2014-01-17 | 20894 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-01-23 | 20903 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | Wolf Tech-NY | Paint Booths
N/A | 20675 | US Steel-PA | Baghouse
Follow-Up | 19979 | Weatherford-LA | welding booths
Follow-Up | 19854 | LATTC | modify grinding table
Follow-Up | 20274 | Sirchie | Lexan tops,Filter Bag
Maintenance |  | Guilford Tech-Jamestown,NC | Filter change out
New |  | Altec | Filter change out
Courtesy Call |  | Accellent | Balance Absolents
| 20629 | Peterson | Welding Booths
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-19 | 20781 | CMS-Waco TX | Duct
| 20587 | NSK-Mexico | Jacobs Duct
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Warranty | 18869 | SunRright Disc | Lexan Top, exchange SDT-3 For SDT-1.5
2014-01-07 | 20720 | GE | WB-6057G & TMC5-2
2014-01-08 | 20840 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump
2014-01-08 | 20837 | Wann Air Systems | Asmoke,Motor,Filters
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct
2014-01-13 | 20865 | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers
2014-01-23 | 20909 | Proveedora | US Duct
2014-01-23 | 20910 | Proveedora | US Duct
2014-01-27 | 20931 | Templeton | silencer, clamps, extension
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets
2014-01-29 | 20563 | Fireaway - TRW Fuji Valve | wire & resistors
| 20738 | Curtis Screw | Absolent Filters (3)

## Jan-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Verbal-ED | 20851 | Curtis Screw | Run Duct to new machine | ASAP |  | 1/23-1/26 Dan & Abe | duct to ship 1/16/14-Daniel to install,Duct &gaskets at Avani to go
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-11-02 | 20621 | Oracle Winston Salem NC
2014-01-15 | 20880 | Stanadyne-NC | Stat-X Install | Drop-Ship-Bill |  |  | 2014-01-24
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
Case | 20843 | Mustang | WB 1055
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2014-01-09 | 20829 | Charter | K& B Duct |  |  | 2014-01-23
2014-01-06 | 20815 | Jernberg - IL | K&B Duct |  |  | 2014-01-23
| 20879 | Stanadyne

## Feb.-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments