## Installs
[5 empty] | INSTALLATIONS |  |  |  | 2014-03-31
[5 empty] | Requested | Confirmed | Quoted | Scheduled | Pending
Order Date | SO # | SO | Customer | Scope | Install Date | Delivery Date | Inst. Hrs | Install Date | Comments
Total
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets |  |  |  | confirm duct drawing with customer & order duct | 38 hose arms, arm stands at Avani,need to change fan to 208 volt,order duct/ po to contractor for pad 3/31
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10 |  | at broker |  | Abraham or John -Solo | everything shipped to Tuscon 2/21,take p-trap
2013-10-24 | 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40 |  | 2014-01-31 |  | Engineer on site wants to change layout | Fred is working with customer on intall date, duct is on order waiting on install date
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20 |  | (3) absolents on site |  | Discuss Install with Daniel re connection flanges | Jacobs duct not crossed over board per customs ,shipped 3 plenum boxes,mist pump boxes 3 WAITING ON DUCT TO CROSS 3/31 ordered connecting flanges
2013-12-11 | 20735 | 156500 | Wolf Tech-NY | grinding booth | 2/28/14 customer |  |  |  | waiting delivery from Taiwan
2013-12-16 | 20754 | 41076 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200 | multiple phases to project | continuing into 2015 |  | 4/8-4/10 Daniel | Matt to order Reducer and Isolater,silencer,fire dampers , pleneum recvd 3/14, jacobs tubing ship 4/3, KB ordered 3/12
2013-12-26 | 20799 | 55957 | General Distributing | SDC-30-16MD,duct,arms,silencer |  | 2/24/14 collector |  |  | ducct order Monday,silencer,collector shipped 2/24 in Wilmgton 4/9,
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan | 7/31/14 -customer |  |  | drug tests required | absolent ordered 1/16/14, fan, wiring,duct layout issues
2014-01-17 | 20894 | 44105 | (Magnum Engin )Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum | 2/28/14 not confirmed |  |  | Install April | booths/ table arrived 4/1 LAX/ vaccum delivered 3/27
2014-01-23 | 20903 | 11202 | Wolf Tech-NY | Paint Booths |  |  |  |  | electrical panels on order
2014-01-23 | 20904 | see above | Wolf Tech-NY | Paint Booths |  |  |  |  | Paint "custom" sample mailed to cust. 3/4/14
2014-02-11 | 20998 | 102178 | Curtis Niagara | A Smoke 40 Duct F. Dampers valves | Pickup ASMOKE 40 US Steel | dampers shipping to vendor 3/10 |  | Daniel - Duct ships 4/21 | A Smoke shipping from Tx 3/12/14, duct, plenum receivd 3 14/ connection/ F. dampers ordered 2/26 Duct to ship4/10 & 4/16 Fire Dampers complete 3/14
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel | Mid June 2014 |  |  | Bill, Jason June | System to ship 5/26, panel ship 4/1, duct , plenum, f. connector ordered 3/19, Riggers must be hired by Remele New location
2014-02-24 | 21059 | 6252 | Performance Contractors LA | 2030 arms, brackets, duct, install |  |  |  | 4/2-4/3 Jason Mike | Matt 3/4/14 Sprial ordered 3/6/14 ship 3/17
2014-02-24 | 21044 | 9640 | Herbalife Winston-Salem | Booth, blower, hood , arm, duct | 2014-03-17 |  |  | 4/8 ?? | 2/26 ordered booth ready 3/27? , arm and blower ship out 3/7, duct needed , K&B ordered ship 3/17, warehouse req for stock submitted 3/11
N/A | 20675 | 57487 | US Steel-PA | Baghouse | ASAP | Baghouse Installed 3 |  | Daniel Deliver Hoods-Pickup Unit on Return from Curtis Screw-ODR 3000 | 2 hoods arrived at Avani 3/24 in office for delivery
Follow-Up | 19854 | 248508 | LATTC | modify grinding table | ASAP |  |  |  | shorter arms delivered to customer, (3) grinding tables need modified
Follow-Up | 20274 | 41772 | Sirchie | Lexan tops,Filter Bag | ASAP | 1 |  | Ready to Finish it at anytime, waiting on Sirchie OK | need to install lexan AND duct
2014-03-17 | 21179 | 17290 | Global Precision Products-Rush NY | Mist 20 DEF 2000 | 2017-03-31 | 2 |  | Install Early April with Curtis Trip | U S duct 3/26 and pulled shipped , fabricate Throttle valves, bleed in box, fire dampers done, and hepa filters 3/20, plenum ordered 3/24
2014-03-19 | 21133 | 31729 | Granite Co Sch. Brockbank Jr. Hg,UT | Baghouse/ Shaker | 2014-06-03 |  |  |  | Baghouse/ Shaker ordered 3/19. 3/25 drawing to be confirmed sent to salesman for voltage
2014-03-19 | 21134 | 31729 | Granite Co.Sch Kearns Hg Office,UT | Baghouse/ Shaker | 2014-06-03 |  |  |  | Baghouse/ Shaker ordered 3/19, 3/25 drawing to salesman for voltage confirmation
2014-03-19 | 21136 | 29510 | Granite Co Sch Kearns Jr. Hg,UT | Baghouse/ Shaker/ Duct | 2014-06-03 |  |  |  | Baghouse/ Shacker ordered 3/19, 3/25 drawings confirmation to salesman for voltage
| 18566 |  | Trenholm |  |  |  |  | 4/3-4/4 ?? Jason Mike | phase 2 SO was closed, Bill to review originl order, Keen to view materials on site
| 21229 |  | QP Manufacturing-Ohio | Mist Stop, duct install |  | 4 |  | Install Early April with Curtis Trip-Deliver Mist Stop Ed to be on site | Duct on order duct in warehouse, Deliver Mist Stop Unit. Run flex hose, install duct
2014-03-21 | 19857 |  | Johnson Controls | RM-6000 |  |  |  |  | modify duct layout and order
|  | Punch List | Gaithersburg VA | Secure Duct, Install isolation pads |  |  |  | Daniel 4/3/14 | Isolation pads from Taiwan and saddle clamps from K&B
| 21222 | 37947 | Schaeffler Group FT. Mill SC | 2 A Mist 40 Duct | 2014-03-31 |  |  |  | Ordered (2) A Mist 3/27/14
2014-03-28 | 21232 | 42687 | Lakeshore Fittings, Grand Haven, MI | NO INSTALL-OUTSIDE CONTRACTOR (3 ODR300 & (1) Micro Air) |  |  |  |  | Matt to supply info to contractor

## Drop Ship Bill
[5 empty] | Drop-Ship-Bill |  |  | 2014-03-31
|  | SO |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Total | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct |  |  | Fred&Matt | matt sent drawing for approval, duct quote
2013-04-24 | 19838 | 25884 | Watterson-WA | (18) booths, arms, led lights | Deliver fall of 2014 | Monitor install date |  | Need to supply details for order already sent to Taiwan
2013-12-26 | 20802 | 3348 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2) | Mike C???? | MC to advise | Customer does not want for 1 year | sent fax, letters to store or ship
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains | Ken?? customer wants to hold for 60 days |  | cust wants no earlier than May | system & curtains in warehouse-
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055 | Ken?? | at Avani 1/7/14 |  | 3/18 customer doesn't want for at least 2 months
2014-01-07 | 20720 | 21948 | GE-Greenville SC | WB-6057G & TMC5-2 | Charles to confirm delivery |  |  | Customer wants to be called when system arrives GE will be shipping from Avaniwill arrive in May
2014-01-08 | 20840 | 25912 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump | 3/9/2014(MC advised not going to meet date) | color & texture critical | ab ships 3/10 | absolent to arrive 3/ 10 week , mist pump to build,pump ordered
2014-02-03 | 20956 | 8680 | Mid-America | (8) silencers |  | Trial silencer |  | Silencer shipped 2/24 in Wilmg 4/9
2014-02-04 | 20965 | 9029 | General Dist. MT | Dust Collector & Booths | 2014-03-05 |  |  | shipped 2/24 be in Wilmington 4/9
2014-02-21 | 20999 | 23946 | Hawkins | Wet Scrubber/ silencer/ duct | 2014-04-01 |  |  | Drawing sent by Fred to cust 3/4 for confirmation 3/14 revised order deleted duct
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm |  | Taiwan Booths |  | ordered all 2/26/14 3/31 customer confirmed
2013-03-13 | 21166 | 6331.65 | Hydromat Maryland | A Mist 20 and Mist Pump |  | absolent ordered 3/13 | ship 6/9/14 | mist pump box to be built
2014-03-18 | 21183 | 2995 | Sonic / GE Hitachi | Downdraft Tables | 2014-03-18 |  |  | Table in warehouse needs modified
2014-03-28 | 21236 | 8418 | Baldor | A mist 20/ p trap/ panel/ filter | 2014-03-28 |  |  | 3/31 P Trap order to warehouse, system ordered 3/31/ panel confirming voltage to order

## Open Orders12-31-13
Open Orders as of 12/31/13
Order Date | SO # | Customer | Scope
Installations
2013-09-16 | 20387 | NMCT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke
2013-12-20 | 20550 | Truform-Rightaway, IL | AB-A Smoke 40
2013-11-29 | 20675 | US Steel-PA | Baghouse
2013-05-29 | 19979 | Weatherford-LA | welding booths
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
| 19854 | LATTC | replace 26 mother boards install flex on sdt1400s
| 20851 | Curtis Screw | Run Duct to new machine
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
2013-12-19 | 20781 | CMS-Waco TX | Duct
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-11-06 | 20587 | NSK-Mexico | Jacobs Duct
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2013-10-02 | 19858 | Bernard Mechanical Contractors | Curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Case | 18869 | SunRight Disc | Lexan Top, exchange SDT-3 For SDT-1.5
Case | 20612 | Praxair Nipoma Hg School | left side welding booth damaged
Case | 20843 | Mustang | WB 1055
New | 20751 | US Engine-SC | Branch
New | 20720 | GE | WB-6057G & TMC5-2
2013-07-13 | 20131 | North Central Technical College | welding curtains

## Open Orders 1-31-13
Open Orders as of 1/31/13
Order Date | SO # | Customer | Scope
Installations
2013-06-21 | 20072 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | NCMT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200
2013-12-20 | 20786 | Truform-Rightaway, IL | AB-A Smoke 40
2013-12-26 | 20799 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-15 | 20880 | Stanadyne | Filters
2014-01-17 | 20894 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-01-23 | 20903 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | Wolf Tech-NY | Paint Booths
N/A | 20675 | US Steel-PA | Baghouse
Follow-Up | 19979 | Weatherford-LA | welding booths
Follow-Up | 19854 | LATTC | modify grinding table
Follow-Up | 20274 | Sirchie | Lexan tops,Filter Bag
Maintenance |  | Guilford Tech-Jamestown,NC | Filter change out
New |  | Altec | Filter change out
Courtesy Call |  | Accellent | Balance Absolents
| 20629 | Peterson | Welding Booths
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-19 | 20781 | CMS-Waco TX | Duct
| 20587 | NSK-Mexico | Jacobs Duct | closed 2/3
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | To ship per Sam Week of 2/3 designated truck
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Warranty | 18869 | SunRright Disc | Lexan Top, exchange SDT-3 For SDT-1.5
2014-01-07 | 20720 | GE | WB-6057G & TMC5-2
2014-01-08 | 20840 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump
2014-01-08 | 20837 | Wann Air Systems | Asmoke,Motor,Filters
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct | closed shipped 1/31
2014-01-13 | 20865 | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers | statx here 1/31 bill to work on next week
2014-01-23 | 20909 | Proveedora | US Duct | closed 2/4
2014-01-23 | 20910 | Proveedora | US Duct | closed 2/4
2014-01-27 | 20931 | Templeton | silencer, clamps, extension
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets | 1/28/14 shipped closed
2014-01-29 | 20563 | Fireaway - TRW Fuji Valve | wire & resistors
| 20738 | Curtis Screw | Absolent Filters (3)

## Open Orders2-28-14
Open Orders as of 2/28/13
Order Date | SO # | SO | Customer | Scope
Total
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10
2013-10-10 | 20674 | 12596 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | 43684 | Schaeffler Mexico | AB-Mist-20
| 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40
2013-11-22 | 20654 | 18299 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | 156500 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | 39629 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | 41076 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200
2013-12-20 | 20786 | 37462.95 | Truform-Rightaway, IL | AB-A Smoke 40
2013-12-26 | 20799 | 55957 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-17 | 20894 | 44105 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-01-23 | 20903 | 11202 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | see above | Wolf Tech-NY | Paint Booths
2014-02-11 | 20998 | 102178 | Curtis Niagara | A Smoke 40 Duct F. Dampers valves
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel
2014-02-24 | 21059 | 6252 | Performance Contractors LA | 2030 arms, brackets, duct, install
N/A | 20675 | 57487 | US Steel-PA | Baghouse
Follow-Up | 19979 | 224863 | Weatherford-LA | welding booths
Follow-Up | 19854 | 248508 | LATTC | modify grinding table
Follow-Up | 20274 | 41772 | Sirchie | Lexan tops,Filter Bag
Maintenance |  |  | Guilford Tech-Jamestown,NC | Filter change out
2014-02-24 | 21044 | 9640 | Herbalife Winston-Salem | Booth, blower, hood , arm, duct
SO
Order Date | SO # | Total | Customer | Scope
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct
2013-04-24 | 19838 | 25884 | Watterson-WA | WB1055-Arm-Light Kit
2013-10-30 | 20563 | 1434 | Fireaway - TRW Fuji Valve, TN | magnets & hoffman Box
2013-11-26 | 20325 | 19715 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | 3348 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055
2014-01-07 | 20720 | 21948 | GE | WB-6057G & TMC5-2
2014-01-08 | 20840 | 25912 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump
2014-02-03 | 20956 | 8680 | Mid-America | (8) silencers
2014-02-04 | 20965 | 9029 | General Dist. MT | Dust Collector & Booths
| 19668 | 5440 | Sundisc | Lexan Top, exchange SDT-3 For SDT-1.5
2014-02-04 | 20954 | 8830 | Thomas Linear | Use Mist duct, plenum, dampers
2014-02-07 | 20987 | 916 | Forge Shop | spark elminator
2014-02-06 | 20990 | 5872 | Paramount Die Co. MD | ODF 1000,1620 arm, stand
2014-02-14 | 21023 | 4391 | ACR Dayton Ohio | Duct Jacobs
2014-02-18 | 21034 | 5110.21 | Jernberg Il | Duct Jacobs
2014-02-21 | 20999 | 23946 | Hawkins | Wet Scrubber/ silencer/ duct
2014-02-25 | 21065 | 250 | Granite City VT | Manual Starter & Overload
2014-02-25 | 21066 | 483.86 | Stanadyne | Duct K & B
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm

## Jan-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Verbal-ED | 20851 | Curtis Screw | Run Duct to new machine | ASAP |  | 1/23-1/26 Dan & Abe | duct to ship 1/16/14-Daniel to install,Duct &gaskets at Avani to go
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-11-02 | 20621 | Oracle Winston Salem NC
2014-01-15 | 20880 | Stanadyne-NC | Stat-X Install | Drop-Ship-Bill |  |  | 2014-01-24
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
Case | 20843 | Mustang | WB 1055
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2014-01-09 | 20829 | Charter | K& B Duct |  |  | 2014-01-23
2014-01-06 | 20815 | Jernberg - IL | K&B Duct |  |  | 2014-01-23
| 20879 | Stanadyne
| 20587 | NSK-Mexico | Jacobs Duct |  |  | shipped 1/17/14 | Broker crossed over boarder 1/31/14 closed
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct |  |  | 1/30/2014 & 2/6/14 | closed shipped on 1/31/14
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets |  |  |  | shipped 1/28/14 closed

## Feb.-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500 |  |  | 1/26 - 2/3 Both Crews | completed 2/2/14
2013-12-18 | 20738 | Curtis Screw | Absolent Filters (3) |  |  | 2014-01-31 | shipped 2/6/14
| 20880 | Stanadyne | Filters |  |  |  | recd. 1/31/14
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10 |  | absolent on site | 2/9-2/13 Jason&Mike | completed 2/11/14
2013-07-03 | 20131 | North Central Tech College | welding curtains |  |  | 2014-02-05 | shipped 2/4/14
2014-01-27 | 20931 | Templeton | silencer, clamps, extension | asap |  |  | completed 2/4/14
2014-01-23 | 20909 | Proveedora | US Duct | ASAP |  | 2014-01-30 | completed 2/4/14
2014-01-23 | 20910 | Proveedora | US Duct | ASAP |  | 2014-01-30 | completed 2/4/14
2014-02-05 | 20855 | Proveedora De Seguriad | duct | missed pieces |  |  | shipped 2/5/14 close
2014-01-03 | 20824 | Hydromat St. Louise | Mist 20 s and Mist Pump |  |  |  | all shipped, and received closed 2/5
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | 2014-02-10 |  | shipping 1/31/14 | shipped out 2/7/14
New |  | Altec | Filter change out | 2014-02-08 |  | 2/8/14 Dan/Abraham/Josh
2014-02-05 | 20971 | Jernberg | 16" gaskets | overnight |  |  | ordered 2/5/14
2014-02-06 | 20975 | Muntz- Mundelein, IL | Damper, reducers , flg adaptors |  |  |  | ship damper 2/10 duct shipping 2/13
2014-01-22 | 20907 | Stanadyne | duct | 1/31/14 recd. Folder 2/3 |  | duct ships 2/11 | duct shipped 2/11 spark arrestor to shipping 2/10/14
2014-02-07 | 20993 | 1137 | Teel Plastics, WI | 1020 arm, bracket & duct |  |  |  | SHIPPED CLOSE
2014-02-11 | 21000 |  | Honda Canada Mfg | F.Damper ( fusable) Filter 6 | 2/11 recvd folder 2/11 |  |  | SHIPPED CLOSE
2014-01-13 | 20865 |  | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers |  | asmoke&fd delivered |  | SHIPPED CLOSE
Case | 1298 |  | Praxair Nipomo High School | panel PO sent in 2/5/14 |  |  |  | TO SHIPPING 2/19
2014-02-24 | 21038 | 235.6 | Howell Metal VA | 14"Elbow & Clamp |  |  |  | duct shipped 2/26 close
2014-01-08 | 20837 | 18352 | Wann Air Systems | Asmoke,Motor,Filters | 2014-01-31 |  |  | closed 2/27/14
2014-02-21 | 21052 | 250 | OZ Lifting Products MN | Manual Starter & Overload |  |  |  | shipped 2/25/14
2013-12-19 | 20781 | 36379 | CMS-Waco TX | Stainless KB Duct |  |  |  | shipped 2/26
2014-02-26 | 21069 | 900 | TRW Fuji | Fire Dampers 6 K&B |  |  |  | SHIPPED CLOSE
2013-11-15 | 20629 | Peterson | Welding Booths | CANCELLED ORDER |  |  | CUSTOMER CANCELLED VERBALLY PER ED 2/11/14
Courtesy Call |  |  | Accellent | Balance Absolents | 2/18 9AM |  | 2/18/2014 Bill

## Mar-Completed
2013-10-14 | 20513 | 43684 | Schaeffler Mexico | AB-Mist-20 | customer to advise | duct delivery 2/4/14 |  | completed 3/1/14
2013-11-22 | 20654 | 18299 | Schaeffler SC | AB-Mist-21 | duct on site | absolent on site | 3/5/14 Daniel & Mike | closed 3/5/14Mark to get additional PO
2013-12-20 | 20786 | 37462.95 | Truform-Rightway, IL | AB-A Smoke 40 | 2/1/14 per Fred | Duct ships 3/11 | 64.125 | completed 3/19/14 | 12" jacobs plenum&(4) 6"fire dampers take from Avani gripples ordered 3/10, install of 3/18
2013-10-10 | 20674 | 12596 | Magna Power, MI | AB-Mist -20 |  | Duct ship 2/4/14 | 41.25 | 3/20 Daniel Jason Mike | duct shipping 2/4/14, plenum & mist pump shipped,P Trap, install 3/21 to be confirmed by customer
2013-12-12 | 20744 | 39629 | Meigs Local School | Down Draft Table |  | SDCAT416 1/13/14 |  | Daniel Jason Mike 3/24 | downdraft table po to robbie2/26 , light kit here,portable filtration here/ duct revised 3/6, install 3/24 to be confirmed by customer
2014-03-05 | 21089 | 5153.13 | Starcon ( weldstar) | booth welding table top |  |  |  | install included with this | Estimated completion, ready to ship 3/26
2014-03-05 | 21090 | 3600 | Starcon ( weldstar) | Installation welding table top |  | Install 3/28/14 |  | John & Mike 3/27-3/29 | Fred to confirm install date, sometime after after 3/26
2014-03-14 | 21175 | 6785 | Eaton Roxboro-NC |  |  |  |  | Bill to be involved in install,confirm 3/28,Daniel & Jason | K&B received 3/21 , pulling from stock K&B, Fire dampers to warehouse 3/21,need ccover plates asap Matt to order
2014-02-25 | 21066 | 483.86 | Stanadyne | Duct K & B | 2014-02-24 |  |  | shipped 2/28/14 closed
2014-02-18 | 21034 | 5110.21 | Jernberg Il | Duct Jacobs | 2/20 recevd folder 12/18 afternoon |  |  | shipped in full no back order closed March2014
Maintenance |  |  | Guilford Tech-Jamestown,NC | Filter change out | 2014-03-05 | school shut 3/3 perfect time to install |  | completed 3/5/14
2014-02-14 | 21023 | 4391 | ACR Dayton Ohio | Duct Jacobs |  |  |  | closed 3/10/14
2014-03-03 | 21101 |  | Alcoa | filters/ track | 2014-03-03 | shipped 3/6 closed
2014-03-05 | 21117 | 416.88 | Munntz | 6 elbows K&B | 2014-03-07 | closed 3/7/14 |  | ordered to ship 3/6
2013-11-26 | 20325 | 19715 | Nucraft Metal - MI | Contactor-Relay |  |  |  | close per Fred 3/10/14
2014-02-25 | 21065 | 250 | Granite City VT | Manual Starter & Overload |  |  |  | closed 3/11/14
2014-02-06 | 20990 | 5872 | Paramount Die Co. MD | ODF 1000,1620 arm, stand | 2014-02-07 |  |  | closed 3/11/14
| 19668 | 5440 | Sundisc | Lexan Top, exchange SDT-3 For SDT-1.5 |  | work order issued to shipping 3/3 |  | Shipped 3/10/14-Closed
2014-03-12 | 21149 | 593.52 | Deutsche | Fire Dampers 3 |  |  |  | shipped 3/12 CLOSE
2014-02-04 | 20954 | 8830 | Thomas Linear | Use Mist duct, plenum, dampers | ( duct shipping 2/25) |  | customer to revise po | dampers/plenum to ship 2/20 duct ship 2/25 system moved per sam 2/20 Filters to shipping 2/21 final parts shipped 3/5 Closed
2014-03-17 | 21178 | 1014.2 | Proveedora | K & B Duct duplicate | CANCELLED ORDER | CANCELLED ORDER |  | CANCELLED ORDER 3/18/14
2014-03-20 | 21198 | 4213.6 | CMS | duct | 2014-03-20 |  |  | shipped 3/24 close
2014-03-24 | 21201 | 463.44 | US Engine Valve | Fire Damper/ Flange adaptors / clamps | 2014-03-20 |  |  | shipped 3/24 close
2014-03-18 | 21184 | 370.33 | Proveedora | K & B Duct clamps | 2014-03-18 |  |  | shipped 3/24 close
2014-03-11 | 21137 | 3601.03 | McClain Tool and Technology | Duct Jacobs | rush |  |  | shipping 3/18
2013-10-30 | 20563 | 1434 | Fireaway - TRW Fuji Valve, TN | magnets & hoffman Box | Bill or Matt to go train-Ken to get PO for training |  |  | parts at Avani, customer wants training
2014-03-25 | 21203 | 5932 | Alco Fastening System | Filters/ track/ Filters A Smoke 40 | 2014-03-20 |  |  | shipped 3/28
2014-03-06 | 21126 | 7028 | Alcoa Waco Tx | Filters/ duct mist stop | 2014-04-05 |  |  | Shipping 3/28/14 Close
2014-03-26 | 21219 | 1356 | P K / Swedish Match | dust/ reducer/ clamp | 2014-03-28 |  |  | duct shipped - system req to ship 3/26
2014-03-18 | 21182 | 1417 | Muntz IL | K&B duct/ Fire Damper | 2014-03-18 |  | Closed 3/31 | fire damper ship 3/18 K&B ship 3/26

## April-Completed
Follow-Up | 19979 | 224863 | Weatherford-LA | welding booths | ASAP | closed 4/1 | curtains ship3/24 To Weatherford, silencer at customers,vacuum branch recd 3/21 need 2 LED lights from taiwan