## Installs
INSTALLATIONS |  |  | 2014-05-31
Order Date | SO # | SO | Customer | Scope
Total
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10
2013-10-24 | 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | 156500 | Wolf Tech-NY | grinding booth
2014-01-23 | 20903 | 11202 | Wolf Tech-NY | Electrical Panel
2014-01-23 | 20904 | see above | Wolf Tech-NY | Paint
2013-12-26 | 20799 | 55957 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel
Follow-Up | 19854 | 248508 | LATTC | modify grinding table
2014-03-19 | 21133 | 31729 | Granite Co Sch. Brockbank Jr. Hg,UT | Baghouse/ Shaker
2014-03-19 | 21134 | 31729 | Granite Co.Sch Kearns Hg Office,UT | Baghouse/ Shaker
2014-03-19 | 21136 | 29510 | Granite Co Sch Kearns Jr. Hg,UT | Baghouse/ Shaker/ Duct
Modification |  | Modification | Gaithersburg VA | Replace Fan(s)
Warranty | 21377 |  | Gaithersburg VA | Fan
2014-04-21 | 21320 | 148236.7 | Truform Parker Fasteners, AZ | A Smoke 40, Arms, Duct
2014-04-30 | 21348 | 34417 | Curtis Niagara,NY | Absolent/ duct/
2014-04-30 | 21379 | 63869 | H B Construction/ Bernalillo H S NM | Dust Collector/ Duct/ Welding Booth
2014-04-30 | 21355 | 152966 | Amstead Rail | ABH-192-10 Baghouse,Fan, BM8005 Boom,Arm
2014-05-07 | 21385 | 152351 | Airgas Masscon, Westmoreland , PA | SDC-AT-4-48, 24 arms, Duct
2014-05-09 | 21391 | 63498 | Schaeffler SC | Absolent Mist 80 (2)
2014-05-21 | 21442 | 31050 | Kiffer Industeries/ CMC | Collector/ duct
2014-05-30 | 21468 | 32518 | Airgas/ Pa Rail Co | SDC EC 2000/ SDC EC 3000 arms, brackets
2014-05-29 | 21458 | 4000 | GE Greenville, SC | Added install to drop ship order
2014-05-30 | 21478 | 26384.65 | Keller Tech/ Great Lakes Mach | A Smoke 40, duct
2014-06-03 | 21487 | 2632.95 | Zeus Aiken SC | Duct Master and K&B

## Drop Ship Bill
Drop Ship Bill |  |  | 2014-05-31
SO
Order Date | SO # | Total | Customer | Scope
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct
2013-04-24 | 19838 | 25884 | Watterson-WA | (18) booths, arms, led lights
2013-12-26 | 20802 | 3348 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm
2013-03-13 | 21166 | 6331.65 | Hydromat Maryland | A Mist 20 and Mist Pump
2014-04-10 | 21288 | 7991 | Gosiger/ Tect Aerospace | AB A Mist 20/ Duct
2014-04-30 | 21357 | 8350 | Crown Battery/ Regency | Arms/ floor stand/
2014-05-01 | 21360 | 12225 | CareFusion | Abs. Mist 20/ filters/ training
2014-05-09 | 21394 | 39900 | Airgas/ T H Harris Campus | 40 red welding booths
2014-05-21 | 21443 | 21233 | Defense Fin and / Accounting | Booth/ down draft table/ portable
2014-05-22 | 21437 | 22392 | Haun/ Northern Catskills | 16 welding booths
2014-05-20 | 21439 | 3313.5 | Honda-Alliston, ON | Duct
2014-05-20 | 21440 | 6422.24 | Honda-Alliston, ON | Duct
2014-05-13 | 21418 | 52847.94 | JR Automation | SDC-20-16MD, RM6000N,duct, silencer
2014-05-30 | 21460 | 13637 | DENSO manufacturing | A Smoke 20 Control Panel P Trap
2014-06-03 | 21440 | 6422.24 | Honda of Canada | Duct 4 parts
2014-06-03 | 21439 | 3313.5 | Honda of Canada | Duct
2014-06-04 | 21491 | 21200 | Ecolotech / US Manufacturing | A Smoke 40 B , Contrl Panel, P-Trap, Stand

## Open Orders12-31-13
Open Orders as of 12/31/13
Order Date | SO # | Customer | Scope
Installations
2013-09-16 | 20387 | NMCT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke
2013-12-20 | 20550 | Truform-Rightaway, IL | AB-A Smoke 40
2013-11-29 | 20675 | US Steel-PA | Baghouse
2013-05-29 | 19979 | Weatherford-LA | welding booths
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
| 19854 | LATTC | replace 26 mother boards install flex on sdt1400s
| 20851 | Curtis Screw | Run Duct to new machine
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
2013-12-19 | 20781 | CMS-Waco TX | Duct
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-11-06 | 20587 | NSK-Mexico | Jacobs Duct
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2013-10-02 | 19858 | Bernard Mechanical Contractors | Curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Case | 18869 | SunRight Disc | Lexan Top, exchange SDT-3 For SDT-1.5
Case | 20612 | Praxair Nipoma Hg School | left side welding booth damaged
Case | 20843 | Mustang | WB 1055
New | 20751 | US Engine-SC | Branch
New | 20720 | GE | WB-6057G & TMC5-2
2013-07-13 | 20131 | North Central Technical College | welding curtains

## Open Orders 1-31-14
Open Orders as of 1/31/14
Order Date | SO # | Customer | Scope
Installations
2013-06-21 | 20072 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | NCMT Mexico | A-Mist 10
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500
2013-10-10 | 20674 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | Schaeffler Mexico | AB-Mist-20
2013-10-24 | 20550 | Truform- McClean Fog, IL | AB-Smoke 40
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10
2013-11-22 | 20654 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200
2013-12-20 | 20786 | Truform-Rightaway, IL | AB-A Smoke 40
2013-12-26 | 20799 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-15 | 20880 | Stanadyne | Filters
2014-01-17 | 20894 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-01-23 | 20903 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | Wolf Tech-NY | Paint Booths
N/A | 20675 | US Steel-PA | Baghouse
Follow-Up | 19979 | Weatherford-LA | welding booths
Follow-Up | 19854 | LATTC | modify grinding table
Follow-Up | 20274 | Sirchie | Lexan tops,Filter Bag
Maintenance |  | Guilford Tech-Jamestown,NC | Filter change out
New |  | Altec | Filter change out
Courtesy Call |  | Accellent | Balance Absolents
| 20629 | Peterson | Welding Booths
Order Date | SO # | Customer | Scope
Drop-Ship-Bill
2013-12-19 | 20781 | CMS-Waco TX | Duct
| 20587 | NSK-Mexico | Jacobs Duct | closed 2/3
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | To ship per Sam Week of 2/3 designated truck
2013-04-24 | 19838 | Watterson-WA | WB1055-Arm-Light Kit
2013-11-26 | 20325 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | Cooper & Company | WB-5055
Warranty | 18869 | SunRright Disc | Lexan Top, exchange SDT-3 For SDT-1.5
2014-01-07 | 20720 | GE | WB-6057G & TMC5-2
2014-01-08 | 20840 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump
2014-01-08 | 20837 | Wann Air Systems | Asmoke,Motor,Filters
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct | closed shipped 1/31
2014-01-13 | 20865 | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers | statx here 1/31 bill to work on next week
2014-01-23 | 20909 | Proveedora | US Duct | closed 2/4
2014-01-23 | 20910 | Proveedora | US Duct | closed 2/4
2014-01-27 | 20931 | Templeton | silencer, clamps, extension
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets | 1/28/14 shipped closed
2014-01-29 | 20563 | Fireaway - TRW Fuji Valve | wire & resistors
| 20738 | Curtis Screw | Absolent Filters (3)

## Open Orders2-28-14
Open Orders as of 2/28/14
Order Date | SO # | SO | Customer | Scope
Total
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10
2013-10-10 | 20674 | 12596 | Magna Power, MI | AB-Mist -20
2013-10-14 | 20513 | 43684 | Schaeffler Mexico | AB-Mist-20
| 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40
2013-11-22 | 20654 | 18299 | Schaeffler SC | AB-Mist-21
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | 156500 | Wolf Tech-NY | grinding booth
2013-12-12 | 20744 | 39629 | Meigs Local School | Down Draft Table
2013-12-16 | 20754 | 41076 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200
2013-12-20 | 20786 | 37462.95 | Truform-Rightaway, IL | AB-A Smoke 40
2013-12-26 | 20799 | 55957 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-17 | 20894 | 44105 | (Magnum)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-01-23 | 20903 | 11202 | Wolf Tech-NY | Paint Booths
2014-01-23 | 20904 | see above | Wolf Tech-NY | Paint Booths
2014-02-11 | 20998 | 102178 | Curtis Niagara | A Smoke 40 Duct F. Dampers valves
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel
2014-02-24 | 21059 | 6252 | Performance Contractors LA | 2030 arms, brackets, duct, install
N/A | 20675 | 57487 | US Steel-PA | Baghouse
Follow-Up | 19979 | 224863 | Weatherford-LA | welding booths
Follow-Up | 19854 | 248508 | LATTC | modify grinding table
Follow-Up | 20274 | 41772 | Sirchie | Lexan tops,Filter Bag
Maintenance |  |  | Guilford Tech-Jamestown,NC | Filter change out
2014-02-24 | 21044 | 9640 | Herbalife Winston-Salem | Booth, blower, hood , arm, duct
SO
Order Date | SO # | Total | Customer | Scope
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct
2013-04-24 | 19838 | 25884 | Watterson-WA | WB1055-Arm-Light Kit
2013-10-30 | 20563 | 1434 | Fireaway - TRW Fuji Valve, TN | magnets & hoffman Box
2013-11-26 | 20325 | 19715 | Nucraft Metal - MI | Contactor-Relay
2013-12-26 | 20802 | 3348 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055
2014-01-07 | 20720 | 21948 | GE | WB-6057G & TMC5-2
2014-01-08 | 20840 | 25912 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump
2014-02-03 | 20956 | 8680 | Mid-America | (8) silencers
2014-02-04 | 20965 | 9029 | General Dist. MT | Dust Collector & Booths
| 19668 | 5440 | Sundisc | Lexan Top, exchange SDT-3 For SDT-1.5
2014-02-04 | 20954 | 8830 | Thomas Linear | Use Mist duct, plenum, dampers
2014-02-07 | 20987 | 916 | Forge Shop | spark elminator
2014-02-06 | 20990 | 5872 | Paramount Die Co. MD | ODF 1000,1620 arm, stand
2014-02-14 | 21023 | 4391 | ACR Dayton Ohio | Duct Jacobs
2014-02-18 | 21034 | 5110.21 | Jernberg Il | Duct Jacobs
2014-02-21 | 20999 | 23946 | Hawkins | Wet Scrubber/ silencer/ duct
2014-02-25 | 21065 | 250 | Granite City VT | Manual Starter & Overload
2014-02-25 | 21066 | 483.86 | Stanadyne | Duct K & B
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm

## Open Orders 4-3-14
Open Orders as of 4/30/14
Installs
Order Date | SO # | SO | Customer | Scope
Total
2013-06-21 | 20072 | 74210 | SW Texas JC TX | Fan, Concete Pad, 38 arms, brackets
2013-09-16 | 20387 | 9234 | NCMT Mexico | A-Mist 10
2013-10-24 | 20550 | 39425.2 | Truform- McClean Fog, IL | AB-Smoke 40
2013-11-29 | 20497 | 37788 | Magna Power Mexico | AB-A Mist 20
2013-12-11 | 20735 | 156500 | Wolf Tech-NY | grinding booth
2014-01-23 | 20903 | 11202 | Wolf Tech-NY | Electrical Panel
2014-01-23 | 20904 | see above | Wolf Tech-NY | Paint
2013-12-26 | 20799 | 55957 | General Distributing | SDC-30-16MD,duct,arms,silencer
2013-12-27 | 20806 | 219088.34 | Honda-Tallapoosa, GA | A-SMoke40-160T,Spray,Fan
2014-01-17 | 20894 | 44105 | (Magnum Engin)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum
2014-02-20 | 21042 | 34675.4 | Hydromat Remmele Medical-MN | A Smoke, Filter, Duct, Ctrl Panel
Follow-Up | 19854 | 248508 | LATTC | modify grinding table
2014-03-19 | 21133 | 31729 | Granite Co Sch. Brockbank Jr. Hg,UT | Baghouse/ Shaker
2014-03-19 | 21134 | 31729 | Granite Co.Sch Kearns Hg Office,UT | Baghouse/ Shaker
2014-03-19 | 21136 | 29510 | Granite Co Sch Kearns Jr. Hg,UT | Baghouse/ Shaker/ Duct
| 18566 |  | Trenholm, AL
2014-03-21 | 19857 | Replacement | Johnson Controls | RM-6000
Modification |  | Modification | Gaithersburg VA | Replace Fan(s)
2014-03-26 | 21222 | 37947 | Schaeffler Group FT. Mill SC | 2 A Mist 40 Duct
2014-04-03 | 21251 | 540 | Altec | 60 + 8 Filters
Annual Maint. |  |  | Guilford
2014-04-30 | 21348 | 34417 | Curtis Niagara | Absolent/ duct/
Drop-Ship-Bill
Order Date | SO # | Total | Customer | Scope
2012-05-10 | 18573 | 14185 | Caterpillar IL | Jacobs Duct
2013-04-24 | 19838 | 25884 | Watterson-WA | (18) booths, arms, led lights
2013-12-26 | 20802 | 3348 | Mifflin HS-PA (Lobar Contractors) | WB-1055 (2)
2013-10-02 | 19858 | 62442 | Bernard Mechanical Contractors | system&curtains
2013-12-02 | 20535 | 49337.7 | Cooper & Company | WB-5055
2014-01-07 | 20720 | 21948 | GE-Greenville SC | WB-6057G & TMC5-2
2014-02-25 | 21058 | 105281 | Imperial Valley College | booths 22 / grinding table/ arm
2013-03-13 | 21166 | 6331.65 | Hydromat Maryland | A Mist 20 and Mist Pump
2014-04-04 | 21200 | 28028 | ELG Utica | Dust Collector
2014-04-10 | 21288 | 7991 | Gosiger/ Tect Aerospace | AB A Mist 20/ Duct
2014-04-22 | 21285 | 8275 | Petron | Duct/ plenum inlet/ fire dampers inline
2014-04-11 | 21297 | 6419 | Jarden | Duct Order-Diverter Valve
2014-04-11 | 21295 | 4668 | Airex | SPC 2000 Arm 2030 Expl proof motor
2014-04-23 | 21156 | 11479 | Hi Cone | After Filter Housing

## Jan-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-11-02 | 20621 | Oracle Winston Salem NC
2013-09-12 | 20381 | Stanadyne-NC | Install new motor
2013-08-19 | 20274 | Sirchie | Lexan tops,Filter Bag
Verbal-ED | 20851 | Curtis Screw | Run Duct to new machine | ASAP |  | 1/23-1/26 Dan & Abe | duct to ship 1/16/14-Daniel to install,Duct &gaskets at Avani to go
2013-10-18 | 20536 | Mid-America-IN | Install Vacuum
2013-11-02 | 20621 | Oracle Winston Salem NC
2014-01-15 | 20880 | Stanadyne-NC | Stat-X Install | Drop-Ship-Bill |  |  | 2014-01-24
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | DeliveryDate | Delivery/Receipt Date | Ship Date | Comments
2013-09-17 | 20393 | Weldstar-IL | Welding Booths
2013-12-26 | 20751 | US Engine-SC | US Duct Parts
Case | 20843 | Mustang | WB 1055
2014-01-06 | 20824 | Hydromat-MN | Amist 20S - Mist Pump
2013-10-01 | 20454 | Tennessee Tech-Comfort Systems-TN | SDC-30-16MD
2014-01-09 | 20829 | Charter | K& B Duct |  |  | 2014-01-23
2014-01-06 | 20815 | Jernberg - IL | K&B Duct |  |  | 2014-01-23
| 20879 | Stanadyne
| 20587 | NSK-Mexico | Jacobs Duct |  |  | shipped 1/17/14 | Broker crossed over boarder 1/31/14 closed
2014-01-10 | 20853 | ACR-Phoenix Metal Works | Jacobs Duct |  |  | 1/30/2014 & 2/6/14 | closed shipped on 1/31/14
2014-01-28 | 20936 | Jernberg - IL | Nordfab Gaskets |  |  |  | shipped 1/28/14 closed

## Feb.-Completed
|  |  |  | Requested | Confirmed | Scheduled | Pending
Order Date | SO # | Customer | Scope | Install Date | Delivery Date | Install Date | Comments
2013-10-04 | 20470 | Gaithersburg-VA | BH-5500 |  |  | 1/26 - 2/3 Both Crews | completed 2/2/14
2013-12-18 | 20738 | Curtis Screw | Absolent Filters (3) |  |  | 2014-01-31 | shipped 2/6/14
| 20880 | Stanadyne | Filters |  |  |  | recd. 1/31/14
2013-10-28 | 20558 | Wagstaff-WA | AB-A-Mist 10 |  | absolent on site | 2/9-2/13 Jason&Mike | completed 2/11/14
2013-07-03 | 20131 | North Central Tech College | welding curtains |  |  | 2014-02-05 | shipped 2/4/14
2014-01-27 | 20931 | Templeton | silencer, clamps, extension | asap |  |  | completed 2/4/14
2014-01-23 | 20909 | Proveedora | US Duct | ASAP |  | 2014-01-30 | completed 2/4/14
2014-01-23 | 20910 | Proveedora | US Duct | ASAP |  | 2014-01-30 | completed 2/4/14
2014-02-05 | 20855 | Proveedora De Seguriad | duct | missed pieces |  |  | shipped 2/5/14 close
2014-01-03 | 20824 | Hydromat St. Louise | Mist 20 s and Mist Pump |  |  |  | all shipped, and received closed 2/5
2013-09-09 | 20409 | Paul Jackson-Rite Hite CO.-IA | WB1055 & Curtains | 2014-02-10 |  | shipping 1/31/14 | shipped out 2/7/14
New |  | Altec | Filter change out | 2014-02-08 |  | 2/8/14 Dan/Abraham/Josh
2014-02-05 | 20971 | Jernberg | 16" gaskets | overnight |  |  | ordered 2/5/14
2014-02-06 | 20975 | Muntz- Mundelein, IL | Damper, reducers , flg adaptors |  |  |  | ship damper 2/10 duct shipping 2/13
2014-01-22 | 20907 | Stanadyne | duct | 1/31/14 recd. Folder 2/3 |  | duct ships 2/11 | duct shipped 2/11 spark arrestor to shipping 2/10/14
2014-02-07 | 20993 | 1137 | Teel Plastics, WI | 1020 arm, bracket & duct |  |  |  | SHIPPED CLOSE
2014-02-11 | 21000 |  | Honda Canada Mfg | F.Damper ( fusable) Filter 6 | 2/11 recvd folder 2/11 |  |  | SHIPPED CLOSE
2014-01-13 | 20865 |  | Industrial Air (Structure Medical) FL | ASmoke40,statx-Fire Dampers |  | asmoke&fd delivered |  | SHIPPED CLOSE
Case | 1298 |  | Praxair Nipomo High School | panel PO sent in 2/5/14 |  |  |  | TO SHIPPING 2/19
2014-02-24 | 21038 | 235.6 | Howell Metal VA | 14"Elbow & Clamp |  |  |  | duct shipped 2/26 close
2014-01-08 | 20837 | 18352 | Wann Air Systems | Asmoke,Motor,Filters | 2014-01-31 |  |  | closed 2/27/14
2014-02-21 | 21052 | 250 | OZ Lifting Products MN | Manual Starter & Overload |  |  |  | shipped 2/25/14
2013-12-19 | 20781 | 36379 | CMS-Waco TX | Stainless KB Duct |  |  |  | shipped 2/26
2014-02-26 | 21069 | 900 | TRW Fuji | Fire Dampers 6 K&B |  |  |  | SHIPPED CLOSE
2013-11-15 | 20629 | Peterson | Welding Booths | CANCELLED ORDER |  |  | CUSTOMER CANCELLED VERBALLY PER ED 2/11/14
Courtesy Call |  |  | Accellent | Balance Absolents | 2/18 9AM |  | 2/18/2014 Bill

## Mar-Completed
2013-10-14 | 20513 | 43684 | Schaeffler Mexico | AB-Mist-20 | customer to advise | duct delivery 2/4/14 |  | completed 3/1/14
2013-11-22 | 20654 | 18299 | Schaeffler SC | AB-Mist-21 | duct on site | absolent on site | 3/5/14 Daniel & Mike | closed 3/5/14Mark to get additional PO
2013-12-20 | 20786 | 37462.95 | Truform-Rightway, IL | AB-A Smoke 40 | 2/1/14 per Fred | Duct ships 3/11 | 64.125 | completed 3/19/14 | 12" jacobs plenum&(4) 6"fire dampers take from Avani gripples ordered 3/10, install of 3/18
2013-10-10 | 20674 | 12596 | Magna Power, MI | AB-Mist -20 |  | Duct ship 2/4/14 | 41.25 | 3/20 Daniel Jason Mike | duct shipping 2/4/14, plenum & mist pump shipped,P Trap, install 3/21 to be confirmed by customer
2013-12-12 | 20744 | 39629 | Meigs Local School | Down Draft Table |  | SDCAT416 1/13/14 |  | Daniel Jason Mike 3/24 | downdraft table po to robbie2/26 , light kit here,portable filtration here/ duct revised 3/6, install 3/24 to be confirmed by customer
2014-03-05 | 21089 | 5153.13 | Starcon ( weldstar) | booth welding table top |  |  |  | install included with this | Estimated completion, ready to ship 3/26
2014-03-05 | 21090 | 3600 | Starcon ( weldstar) | Installation welding table top |  | Install 3/28/14 |  | John & Mike 3/27-3/29 | Fred to confirm install date, sometime after after 3/26
2014-03-14 | 21175 | 6785 | Eaton Roxboro-NC |  |  |  |  | Bill to be involved in install,confirm 3/28,Daniel & Jason | K&B received 3/21 , pulling from stock K&B, Fire dampers to warehouse 3/21,need ccover plates asap Matt to order
2014-02-25 | 21066 | 483.86 | Stanadyne | Duct K & B | 2014-02-24 |  |  | shipped 2/28/14 closed
2014-02-18 | 21034 | 5110.21 | Jernberg Il | Duct Jacobs | 2/20 recevd folder 12/18 afternoon |  |  | shipped in full no back order closed March2014
Maintenance |  |  | Guilford Tech-Jamestown,NC | Filter change out | 2014-03-05 | school shut 3/3 perfect time to install |  | completed 3/5/14
2014-02-14 | 21023 | 4391 | ACR Dayton Ohio | Duct Jacobs |  |  |  | closed 3/10/14
2014-03-03 | 21101 |  | Alcoa | filters/ track | 2014-03-03 | shipped 3/6 closed
2014-03-05 | 21117 | 416.88 | Munntz | 6 elbows K&B | 2014-03-07 | closed 3/7/14 |  | ordered to ship 3/6
2013-11-26 | 20325 | 19715 | Nucraft Metal - MI | Contactor-Relay |  |  |  | close per Fred 3/10/14
2014-02-25 | 21065 | 250 | Granite City VT | Manual Starter & Overload |  |  |  | closed 3/11/14
2014-02-06 | 20990 | 5872 | Paramount Die Co. MD | ODF 1000,1620 arm, stand | 2014-02-07 |  |  | closed 3/11/14
| 19668 | 5440 | Sundisc | Lexan Top, exchange SDT-3 For SDT-1.5 |  | work order issued to shipping 3/3 |  | Shipped 3/10/14-Closed
2014-03-12 | 21149 | 593.52 | Deutsche | Fire Dampers 3 |  |  |  | shipped 3/12 CLOSE
2014-02-04 | 20954 | 8830 | Thomas Linear | Use Mist duct, plenum, dampers | ( duct shipping 2/25) |  | customer to revise po | dampers/plenum to ship 2/20 duct ship 2/25 system moved per sam 2/20 Filters to shipping 2/21 final parts shipped 3/5 Closed
2014-03-17 | 21178 | 1014.2 | Proveedora | K & B Duct duplicate | CANCELLED ORDER | CANCELLED ORDER |  | CANCELLED ORDER 3/18/14
2014-03-20 | 21198 | 4213.6 | CMS | duct | 2014-03-20 |  |  | shipped 3/24 close
2014-03-24 | 21201 | 463.44 | US Engine Valve | Fire Damper/ Flange adaptors / clamps | 2014-03-20 |  |  | shipped 3/24 close
2014-03-18 | 21184 | 370.33 | Proveedora | K & B Duct clamps | 2014-03-18 |  |  | shipped 3/24 close
2014-03-11 | 21137 | 3601.03 | McClain Tool and Technology | Duct Jacobs | rush |  |  | shipping 3/18
2013-10-30 | 20563 | 1434 | Fireaway - TRW Fuji Valve, TN | magnets & hoffman Box | Bill or Matt to go train-Ken to get PO for training |  |  | parts at Avani, customer wants training
2014-03-25 | 21203 | 5932 | Alco Fastening System | Filters/ track/ Filters A Smoke 40 | 2014-03-20 |  |  | shipped 3/28
2014-03-06 | 21126 | 7028 | Alcoa Waco Tx | Filters/ duct mist stop | 2014-04-05 |  |  | Shipping 3/28/14 Close
2014-03-26 | 21219 | 1356 | P K / Swedish Match | dust/ reducer/ clamp | 2014-03-28 |  |  | duct shipped - system req to ship 3/26
2014-03-18 | 21182 | 1417 | Muntz IL | K&B duct/ Fire Damper | 2014-03-18 |  | Closed 3/31 | fire damper ship 3/18 K&B ship 3/26

## April-Completed
Follow-Up | 19979 | 224863 | Weatherford-LA | welding booths | ASAP |  |  | closed 4/1 | curtains ship3/24 To Weatherford, silencer at customers,vacuum branch recd 3/21 need 2 LED lights from taiwan
2014-02-24 | 21059 | 6252 | Performance Contractors LA | 2030 arms, brackets, duct, install |  |  |  | 4/2-4/3 Jason Mike | Matt 3/4/14 Sprial ordered 3/6/14 ship 3/17
2013-12-16 | 20754 | 41076 | Eaton Roxboro-NC | A Smoke40 & Asmoke 1200 | multiple phases to project | continuing into 2015 | 46.66 | 4/8-4/10 Daniel & CJ | Matt to order Reducer and Isolater,silencer,fire dampers , pleneum recvd 3/14, jacobs tubing ship 4/3, KB ordered 3/12
Follow-Up | 20274 | 41772 | Sirchie | Lexan tops,Filter Bag | ASAP |  |  |  | installed lexan and duct
2014-02-24 | 21044 | 9640 | Herbalife Winston-Salem | Booth, blower, hood , arm, duct | 2014-03-17 |  | 20 | 4/14 Jason & Mike must be on site by 7:15 am | boothdelivered 4/4 , arm and blower ship out 3/7, duct needed , K&B ordered ship 3/17, warehouse req for stock submitted 3/11
2014-02-11 | 20998 | 102178 | Curtis Niagara | A Smoke 40 Duct F. Dampers valves |  | 1st stop | 131.11 | 4/22-4/27 Daniel - Duct arrives 4/22 | A Smoke shipping from Tx 3/12/14, duct, plenum receivd 3 14/ connection/ F. dampers ordered 2/26 Duct to ship4/10 & 4/16 Fire Dampers complete 3/14
N/A | 20675 | 57487 | US Steel-PA | Baghouse | Pickup ASMOKE 40 | 4th stop |  | 5/1-5/2 Daniel-Pickup Unit on Return from Curtis Screw-ODR 3000 | Mike Connors delivered hoods
2014-03-17 | 21179 | 17290 | Global Precision Products-Rush NY | Mist 20 DEF 2000 | 2017-03-31 | 2nd stop |  | 4/27-4/28 Daniel | U S duct 3/26 and pulled shipped , fabricate Throttle valves, bleed in box, fire dampers done, and hepa filters 3/20, plenum ordered 3/24
2014-03-27 | 21229 | 2319 | QP Manufacturing-Ohio | Mist Stop, duct install |  | 3rd stop |  | 4/30-5/1 | Duct on order duct in warehouse, Deliver Mist Stop Unit. Run flex hose, install duct
2014-04-03 | 21246 | 2400 | Amsted Rail | Stat X First Re. Canisters | 03/31/14 got folder 4/3/14 |  |  | all shipped 4/7 CLOSE
2014-03-28 | 21236 | 8418 | Baldor | A mist 20/ p trap/ panel/ filter | 2014-03-28 |  | closed 4/10/14 | 3/31 P Trap shipped , system shipped 4/4, panel shipped 4/8
2014-04-11 | 21299 | 4700 | DSSI (Johnson Controls) | Stat X | 2014-04-11 |  |  | shipped over night 4/17 CLOSE
2014-03-18 | 21183 | 2995 | Sonic / GE Hitachi | Downdraft Tables | 2014-03-18 |  |  | SHIPPED 4/14/14
2014-02-03 | 20956 | 8680 | Mid-America | (8) silencers |  | Trial silencer |  | shipped 4/17 returning 1
2014-04-11 | 21301 | 862.11 | Delta | Duct K/B or US DUCT | 2014-04-11 |  |  | duct shipped 4/17 close
2014-04-22 | 20962 | 15084 | General Distributing | TMC-3-2 WB-6055 |  |  |  | shipped 4/22/14
2014-02-04 | 20965 | 9029 | General Dist. MT | Dust Collector & Booths | 2014-03-05 |  |  | Shipped designated truck 4/21- close
2014-04-16 | 21314 | 6273 | Honda of Canada | Fire Damper/ Filter | 2014-04-16 |  |  | Shipped 4/22 Close
2014-01-08 | 20840 | 25912 | Gleason Total Gear | AB-Asmoke 20 & Mist Pump | 3/9/2014(MC advised not going to meet date) | color & texture critical | ab ships 3/10 | closed 4/24/14
2014-04-11 | 21296 | 97178.8 | Industrial Air Devices | A Smoke 3000 Statx | 2014-04-11 |  |  | all has shipped - close
2014-02-21 | 20999 | 23946 | Hawkins | Wet Scrubber/ silencer/ duct | 2014-04-01 |  |  | shipped 4/24
| 21310 |  | Stanadyne | Filter/ "Stat X/ Hepa | 2014-04-15 |  |  | stat x shipped 4/17/Hepa ordered/ Nano shipped 4/17
| 20921 | 2100 | Regency Sales | Hoods 6 |  |  |  | shipped 4/25/14

## May-Completed
Order Date | SO # | SO | Customer | Scope | Install Date | Delivery Date | Inst. Hrs | Install Date | Comments
Total
2014-01-17 | 20894 | 44105 | (Magnum Engin)Alcoa-Elmendorf,TX | WB601207C,SDC-10-6,DDT,Vacuum | 2/28/14 not confirmed |  | 72.16 | closed 5/1/14 | booths/ table shipping from LAX 4/8/ vacuum delivered 3/27
2014-03-21 | 19857 | Replacement | Johnson Controls | RM-6000 |  |  |  | Daniel & CJ leave 5/12 Install 5/13-5/14 | Bill Need to order duct
2014-03-26 | 21222 | 37947 | Schaeffler Group FT. Mill SC | 2 A Mist 40 Duct | 2014-03-31 |  |  | Jason -Mike 5/14-5/16 | Ordered (2) A Mist 3/27/14 to arrive 5/13 5p.m., US Duct ordered 5/6, plenum 5/6, work order 5/6 for inventory
2014-04-22 | 21285 | 8275 | Petron | Duct/ plenum inlet/ fire dampers inline | 2014-04-08 |  | need packing list for gripples 1 bag, | plenum bx 4/22 shipped / duct to pull from inventory 4/24/ fire dampers 4/24/ to ship , jacobs shipped 5/8/ CLOSE
2014-04-11 | 21232 | 42687 | Lakeshore Fittings-Grand Haven, MI | Duct & Install |  |  |  | Ecolo-Tech did the duct and install
| 18566 |  | Trenholm, AL |  |  | Duct to ship 5/6, all other supplies at location |  | closed 5/27/14 | phase 2 SO was closed, Bill to review original order, Ken to view materials on site/ duct ordered 4/15
Annual Maint. |  |  | Guilford | Filter Change | May 5 or 12 |  |  | Jason-Mike 5/12/2014
2014-05-05 | 21375 | 6511 | Truform | A Mist 20 , Panel | 2014-05-19 |  |  | All shipped CLOSE
2014-05-09 | 21401 | 125 | Winco | duct |  |  |  | shipped 5/13 CLOSE
2014-04-23 | 21156 | 11479 | Hi Cone | After Filter Housing |  |  | Scientific | shipped 5/15 CLOSE
| 21229 | 48.75 | Q P | Nema Housing |  |  |  | ordered 5/2/14
2014-04-03 | 21251 | 540 | Altec | 60 + 8 Filters | 2014-04-03 |  |  | John-Mark-David 5/17 | Filters ordered to ship to Avani est ship 4/16
2014-04-11 | 21297 | 6419 | Jarden | Duct Order-Diverter Valve | before 6/1/14 |  |  | all shipped- CLOSE
2014-04-04 | 21200 | 28028 | ELG Utica | Dust Collector |  |  | shipping 5/27 | shipped to customer 5/22
2014-05-13 | 21411 | 14950 | MarbleFall High School | 10 booths no tables hardware/ curtain rods |  |  |  | closed 5/23
2014-01-07 | 20720 | 21948 | GE-Greenville SC | WB-6057G & TMC5-2 | Charles to confirm delivery |  |  | closed 5/22
2014-05-22 | 21448 | 220.62 | Winco MFG | 2 Y branches/ 1 reducer |  |  |  | ordered pcs 5/22 to ship 5/28
2014-04-11 | 21295 | 4668 | Airex | SPC 2000 Arm 2030 Expl proof motor | 2014-04-11 |  | motor ship 5/19 | All Shipped 5/28 CLOSE
2014-05-09 | 21399 | 8453 | Thomson Linear LLC | A Mist 20 / Duct | 8453 | send plenum then close |  | All shipped 5/27 CLOSE
2014-05-19 | 21431 | 1684.34 | Ashland Chemical | Steel Duct |  |  |  | shipped 5/22 close
2014-05-23 | 21450 | 11177 | Salem Tools | Mist 20 ctrl panel, stat x | 2014-05-27 |  |  | all shipped 5/30 close

## June-Completed
2014-05-30 | 21460 | 13637 | DENSO manufacturing | A Smoke 20 Control Panel P Trap | ALL SHIPPED CLOSE