## Installs
2015-10-23
Order Date | Reps | SO # | SO Total | Customer | Contact | Scope | Rqustd Ins Date | Confirmed Delivery Date | Scheduled Install Date | Pending
2014-04-30 | KB | 21379 | 63869 | H B Construction/ Bernalillo H S NM | MikeH@hbconstruction.com (508) 377-3731 c-(505) 377-3731 | SDC-AT-5-20/ Duct/ WB-1044(9), ARM-1620(9) | 2016-06-01 | Need to Requote | 2015-11-01
2014-06-10 | KB |  | 92830 | Groathouse-Roosevelt High, WY | wkitchen@groathouse.com | Grinding Booth W/doors & rear mount collector (2) WB-1055 (18) 1620 Arms (18) | week of Dec 14th | Container due 8/27 | Sept. 2015 sheet metal specialties, 3/30 new contact is Wayne Kitchen | All equipmen in house
2014-12-02 | MH | 22233 | 126064 | Chevron-Richmond, CA |  | (8) WB 1066, (1) SDC-at-3-12, (8) 1020 arms, (8) custom hoods spiral duct | 2015-12-09 | No deposit required |  | 7/13 everything delivered waiting on date for install from cust. 8/10 follow up
2015-03-03 | RK | 22601 | 352442 | Lee College | [5 empty] | Training 11/30
2015-04-02 | ES | 22748 | 79019 | JC Tlaxcala |  |  | 2015-07-03 |  | 10/24/2015 Simex | Missing Shipment Simex Install
2015-04-14 | ES | 22714 | 257042 | Medtronic PR | edwin.marrero.nievs@medtronic.com | ab mist 80tf,(3)ab mist 40tf(2),mist stop(3)fire dampers(9) control panel(3) vfd frequency(3)drive, duct(4) | 2015-04-20 | Mid Nov Install | 4/29 rcvd adapters and VFS15 | 8/10 eric recevd email for the finish of install don’t know when we are sending someone out there 9/3 em alex for update on wall to finish install
2015-05-20 | ES | 22954 | 117373 | Schaeffler Mexico | 52-462-63600627 | AB-Smoke40 (2),AB-smoke 20 (1), duct,MP-400, stands, install | 2015-07-17 | Mid Nov Install |  | Additional Duct Ordered 10/16
2015-06-22 | ME | 23074 | 86859.25 | Spartanburg/Clayton con | Rick Ivester rick@claytonconstruction.net | Collector,control panel,fan,arm,duct,install | 2015-08-17 | container due 8/27 |  | 7/7 san mao 16 arms ordered 7/28 received quote and coi and w-9 Keller and Son act ship 8/10 US duct will ship 8/17, installation starts 8/20 9/9 left mess for charles at airgas on cell phone 864-809-3855 for update pend runoff. 9/25 em candi for track on ACT
2015-07-31 | mh | 23207 | 79365 | American castings | 831-637-5641 | WB-6066,Duct, SDC-at3-12 Duct Vaccuum | 2015-10-30 |  | December | taiwan ship date 11/19, plenum box ordered, ACT holding order till I tell her a date to ship 10/12 per eric to cust will receive in Dec. Client ok'd Approved drawing, need duct review and order
2015-08-10 | MH | 23227 | 215350.84 | APS Palo Verde | 623-393-6257 | Arm (3),duct,SDC-AT-4-16 (1),fan(1),wb-60118/6066 (2) sdt-5(2) down draft tables, avani install | 2015-11-05 | Install after 11/9 |  | Delivery all on 10/23, Duct Inc Install
2015-08-19 | ME | 23253 | 30956 | USCG training center |  | GB (2) w/ sliding door 5'5' AND 6'6', our install | 2015-12-12 |  |  | Taiwan Delivery 12/12 Mike asked jo to contact client, I emailed David Hargrave about new delivery date.
2015-09-04 | MC | 23329 | 133974 | Blast and Wash/Pace Industries | 585-384-9025 | SDC-AT-3-24,SDC-AT-4-32, duct, installation Avani | 2015-10-23 | ASAP | Install week of 11/9 | Hal doing drawings, Act units ship 11/6, need approved drawings and duct to be ordered
2015-09-09 | ES | 23332 | 80034 | JC Tlaxcala | 269-966-6426 | SDC-20-16MD, SRM-6000,control panel,silencer,custom duct, duct | 2015-11-30 |  |  | Need to order duct
2015-09-09 | FJ | 23338 | 3076 | Amsted |  | Stat X Monthly Inspections | 2015-09-09 |  |  | 10/07 per fred will make schedule
2015-09-17 | ME | 23356 | 8965 | Morris South | 704-523-6008 | AB-A Mist 10,install-avani, duct 62829 jacobs | 2016-01-12 |  |  | Absolent shipping 1/12/16, ME working on layout
| ME | 23404 | 42683 | Shaeffler Group Usa | 803-548-8926 | AB-A Smoke 40, jacobs duct, insatll avani | 2015-11-06 |  |  | 10/02 sent welcome letter 10/07 absolents ordered also need sight walk done Daniel 10/12 mark will let us know about walk through next week. Absolent ship date 11/06
2015-10-02 | ME | 23405 | 43370 | Shaeffler Group Usa | 803-548-8926 | AB-A Smoke 40, jacobs duct, insatll avani | 2015-11-06 |  |  | 10/02 sent welcome letter 10/07 absolents ordered also need sight walk done by Daniel 10/12 mark will let us know about walk through next week. Absolent ship date 11/06
2015-10-07 | MC | 23417 | 25590 | Bonney Forge | 800-345-7546 ext 2444 | AB-A smoke 20, jacobs duct, install avani | 2015-12-07 |  |  | absolent will ship 11/16 sent info to Thomas(contact)
2015-10-19 | ES | 23459 | 26440 | APIC-Angers & Salinas-TX | 956-726-1626 | A SMoke5 (3) Penguin stands (3) duct to connect |  |  |  | absolents ordered 10/21, need to discuss duct with ED
2015-10-27 | KB | 23482 | 113069 | Edgecombe CC Tarboro,NC |  | SDC-30-24MDF,(12 ,Curtains, (12) Custom Arm assembly brackets, (14) arms, (14) br-006, |  | 2016-02-09 |  | Collectorr order from Taiwan, need to order duct, curtains and assembly brackets from MC1
Total |  |  | 1978371.09
2014-07-25 |  | 21711 | 77077.3 | Boilermakers Spokan WA Local 242 | Mark Keffeler bm242@aol.com | local 242 | 2014-12-01 | not our install manage only | Waiting on Drawing approval before ordering duct. Connect to the existing square duct! 2/23/15 | 8/24 20 pallets in containers on property, 9/2 delivery for Rect duct eta 9/8. I em client
2014-07-25 | MH | 21712 | 249470 | Boilermakers Page, AZ Local 04 | Casey Tibbs, utahcasey79@hotmail.com | local 4 | 2014-12-01 | Customer wants full install |  | 9/18 the guys are all finished with the install.
2014-05-01 |  | 21360 | Invoiced | CareFusion |  | Training in Mexico-Bill
2015-04-01 | es | 21247 | 0 | National Machinery-Tiffin, OH |  | AB-smoke,duct | demo |  | 4/1 Per Ed no charge, eric got email that cust is supplying duct? | close
2015-02-12 | MC | 22531 |  | PPL/Airgas | Ron.downing@airgas.com, arthur.crochetiere | SDC-AT-3-12, WB10000, AE-1000 statX, contract statX install |  | Pending revised PO from airgas | 3/17 It was scheduled to ship 3/20 but it looks like now it will be ready on 3/18. per CB 8/26 per chaz taiwan container will port wilmington 8/27 | 6/22 will be in port july 30
2014-09-12 | ES | 21920 | 232099.8 | Doosan- Intl. Mexico |  | (28) A-mist 10s, (14) A-mist 20s | 2015-03-30 |  |  | 7/17 per ed do not send P-traps or clamps cust has already
2015-05-15 | KB | 22916 | 271334 | San Bernardino.Cal City |  | WB-3500 (26), WB-3500 (1), XA-WC-6(27) |  |  |  | 7/1 emailed jeff schlentz for install container coming in 7/7 and 7/14. install should be around 7/21. 7/13 eric sending me new contact for install

## Drop ships
Order Date | REP. | SO # | Total | Company Name | Scope | Requested | Ship Date | Pending
2015-06-23 | KB | 23067 | 86037 | Kelly Walsh/Sampson Const. | WB-1055(18) arms (18) customized curtains(18) br-006,grinding booth (2) | 2015-11-23
1963-03-21 | FJ | 23091 | 53700 | Amsted Rail | Stat-X | 2015-12-31 |  | Charge monthly 8/26 rcvd w-9 COI 10/04 po sent out for october inspection eric sent email to mike H for motnhly inspections not being done
2015-07-30 | es | 23176 | 9679.68 | Freeport McMoran | arm,2040p,br008,duct, | 2015-10-29 | 2015-11-25 | 10/2 Taiwan will ship of approx. 11-25 to cust
2015-08-27 | FJ | 23294 | 4981 | Dunkin Donuts/airgas | SBU-3 blower unit,230V,Clamp together duct,SDT-3 | 2015-11-12 | Duct Ordered | Kerry from Airgas would like to know a deliver date. Duct ordered 10/22, need to order flex hose
2015-08-27 | ES | 23296 | 4731 | Terrys Electric-PCSB Four corners K-8 School | WB-1055 (1),curtain 1620 arm Br006 | 2016-04-12
2015-08-31 | mc | 23310 | 9836 | Airgas/Lagonda | Fan TCBI-25,Duct clamp tpgether | 2015-08-31 |  | they have received the fan. New order for collector on the way, need to redo dwg and duct order
2015-09-02 | MC | 23311 | 16300 | Plumber and Pipefitters local 5 | acvs-24 Vacuum System | 2015-09-18 |  | all piping on order
2015-09-25 | ES | 23372 | 162579.06 | JR Automation-Holland MI | SDC-20-16MD,control panel,SRM-6000, Duct, Silencer | 2016-01-11 |  | Need to order Duct
2015-10-14 | ES | 23449 | 20030 | Nat Machinery | A Smoke 40B - Custom Paint | 2015-12-01 |  | Paint complete, Customer wants it shipped 12/1
2015-10-19 | MC | 23455 | 8048 | Accellent-Lake Region Medical | A Mist 20, Carbon Filter and MP-400 and stand | 2015-11-16 |  | all ordered, build mist pump box
2015-10-29 | ES | 23492 | 7993 | Automatic Products-Kent, WA | (2) Used A smoke 20, 8" pb | 2015-11-13 |  | ordered (1) plenum boxes, 4 legs
2015-10-29 | ES | 23493 | 15986 | Automatic Products-Kent, WA | (1) Used A smoke 20, 8" pb | 2015-11-13 |  | ordered (1) transition, (2) plenum boxes, 8 legs
2015-11-02 | FJ | 23503 | 13730 | BSI Engineering-Perkins-Jacksonville IN | (1) WB-1066 (1) TMC-3-2, (1) Welding Curtain |  |  | 11/2/15 6066 & TMC-3-2 ordered, curtain ordered
2015-11-04 | SS | 23506 | 344 | CMS - Waco, TX | Duct |  |  | ordered 11/4/15
2015-11-05 | SS | 23514 | 3454 | CMS - Waco, TX | Duct |  |  | ordered 11/5/15
2015-11-10 | FJ | 23510 | 22287 | Ecolo-Tech-MNP | A Smoke 40 std ,Control Panel, pre-filter |  |  | ordered 11/10/15
2015-11-09 | FJ | 23533 |  | Barnes | Duct |  |  | 11/9/15 Requested quote from Jacobs
Total |  |  | 347843.74
2015-02-05 | FJ | 22510 | 0 | Ecolo- Tech | 90 day demo unit |  | 2015-02-18 | delivered 2/25 revisit May 25th
2015-01-19 | FJ | 22417 |  | MacLean Fogg-Savanna, IL | Amist 6C,24 prefltrs w/frames,1 set flanges | closed 3/27 |  | 3/23 closed. Item delivered 3/5 60 day demo send invoice 5/5/15
2015-08-17 |  | 23192 |  | Southtec Show | AB-A Mist, mist pump mist stop prefilter SPC-2607
2015-09-17 | ES | 23358 | 37113 | Fabtech Show | AB-A mist 20, DD table 1.5hp, baby booth w/baby arm Arm SS2030, SPC-230, custom Duct
2015-05-13 | ES | 22906 | 10000 | San Bernardino | Grinding Booth 6'6' |  |  | cancelled until further notice, never received a PO
WB being shipped 9/8/15, per CB.per Chaz 8/20 del date on arms 9/16 for all. 8/24 WO done for arms and brackets. Emailed client on ship date. 9/15 emailed CB for definate date of tomrrow for shipping 9/16 CB made a mistake Jardine did not ship.he said hopefully tomorrow. I spoke with cust TIm. i will get the tracking and sent to Tim Malaska. Merchant 1 will be delivered 9/23 i notified customer also sent assembly instructions. 9/24 very unhappy customer, 9/28 curtains delivered curtain rod wrong size etc....told Kirk about it and Eric.. ORDER IS CLOSED HOWEVER THEY GAVE US A BILL FOR EXTRA COSTS DUE TO NO DELIVERY WHEN PROMISED

## Nov Close
Open Order 11/2/15
SO # | Total | Company Name
23067 | 86037 | Kelly Walsh/Sampson Const.
23091 | 53700 | Amsted Rail
23176 | 9679.68 | Freeport McMoran
23294 | 4981 | Dunkin Donuts/airgas
23296 | 4731 | Terrys Electric-PCSB Four corners K-8 School
23310 | 9836 | Airgas/Lagonda
23311 | 16300 | Plumber and Pipefitters local 5
23372 | 162579.06 | JR Automation-Holland MI
23449 | 20030 | Nat Machinery
23455 | 8048 | Accellent-Lake Region Medical
23469 | 1355 | Schaeffler MX
23492 | 7993 | Automatic Products-Kent, WA
23493 | 15986 | Automatic Products-Kent, WA
23503 | 13730 | BSI Engineering-Perkins-Jacksonville IN
21379 | 63869 | H B Construction/ Bernalillo H S NM
| 92830 | Groathouse-Roosevelt High, WY
22233 | 126064 | Chevron-Richmond, CA
22601 | 352442 | Lee College
22748 | 79019 | JC Tlaxcala
22714 | 257042 | Medtronic PR
22954 | 117373 | Schaeffler Mexico
23074 | 86859.25 | Spartanburg/Clayton con
23207 | 79365 | American castings
23227 | 215350.84 | APS Palo Verde
23253 | 30956 | USCG training center
23329 | 133974 | Blast and Wash/Pace Industries
23332 | 80034 | JC Tlaxcala
23338 | 3076 | Amsted
23356 | 8965 | Morris South
23404 | 42683 | Shaeffler Group Usa
23405 | 43370 | Shaeffler Group Usa
23417 | 25590 | Bonney Forge
23459 | 26440 | APIC-Angers & Salinas-TX
23482 | 113069 | Edgecombe CC Tarboro,NC
2393356.83
Nov Close |  |  |  |  | Closing Date
2015-10-22 | ES | 23469 | 1355 | Schaeffler MX | 2015-11-09

## Oct close
23167 | 9995 | ThyssenKrupp
23146 | 89100 | Thyssen Krupp
23197 | 21733.96 | Centrix | closed | install/cont
23167 | 9995 | ThyssenKrupp |  | install
22748 | 79019 | Johnson Controls |  | in
23128 | 73393 | JR Automation
22601 | 343532 | LEE college |  | install
23283 | 9907.7 | Eaton Corp |  | Install
23074 | 86859.25 | Spartanburg/Clayton construction |  | install
23311 | 16300 | Plumber and Pipefitters local 5
23199 | 9880 | Thomas Linear
23078 | 4536 | Duke University
23247 | 7615 | A Berger
23236 | 12805 | A Berger
761865.91
October Close | [8 empty] | closed
2015-09-11 | MC | 23340 | 3518.41 | CMS | 254-716-0312 | Credit Card | Duct | 2015-09-23 | 2015-10-14
2015-09-16 | FJ | 23351 | 9228 | Amstead Rail |  | net 30 | STAT-X Penetrator for 2500E | 2015-09-28 | 2015-10-14
2015-10-05 | FJ | 23406 | 49.56 | McGregor manu/mcclain tool | 314-432-3220 | net 30 | jacobs duct PN 11151110 slip tube 15 mm dia 1000mm 1.5 mm thick mild steel | 2015-10-23 | 2015-10-14
1905-07-07 | FJ | 23167 | 9995 | ThyssenKrupp | 217-444-5539 | net 60 | install, jacobs duct | 2015-08-11 |  | B&B? | 8/10 duct wll ship on 8/13
2015-07-31 | FJ | 23199 | 9880 | Thomas Linear | 815-568-4261 Randy | net 60 | AB-A Mist 20, jacobs duct, p-trap | 2015-08-28 |  | B&B? | 8/10 candi is placing order, jacobs esd 8/27, a mist esd 8/7
2015-09-17 | FL | 23360 | 567.28 | McGregor Manufactur/mclain tool | 314-432-3220 Laura Launius | net 30 | Jacobs Duct | 2015-10-02 |  | duct ordered 10/12 duct will ship today
2015-10-05 | SS | 23403 | 3418.63 | CMS | 254-716-0312 | credit card | Duct | 2015-10-16 |  | 10/12 order will ship 10/16 then close
2015-10-07 | FJ | 23412 |  | Barnes | 815-964-8661 | net 30 | duct K&B | 2015-10-13 |  | Bill -Quote from Jacobs 10/14
2015-10-14 | FJ | 23450 |  | Barnes |  |  | Duct-Jacobs
2015-08-12 | BS | 23236 | 12805 | A Berger | 905-840-8011 | net 75 | Duct, fire dampers 8" long6"dia, 8" long 8" diam,fire dampers 7",4", j120" | 2015-09-10 |  |  | 8/19/2015 duct and fire dampers ordered lloyd and jacobs 9/30 pack list for fire dampers and PVC trap done ship 10/2. Still need to ship 4",6"7" fire dampers waiting on pipe 10/07 pack ist done for b/o fire dampers delivered 10/08, 10/12 em bill for update
2015-08-20 | BS | 23247 | 7615 | A Berger | 905-840-8011 | no | Insall Av | 2015-09-21 |  |  | 8/20 and 9/3 Bill let me know that install should start in 2 weeks.
|  | 23240 | 11256.51 | A Berger
2015-10-22 | FJ | 23468 | 212 | Barnes |  |  | jacobs duct | 2015-10-26 |  | shipped 10/22
2013-04-21 | MH | 22832 | 16816.75 | Senior Aerospace | tclark@seniorssp.com | no | SDT-5,silencer,FM-20235,fm-s-30242, customised sdt-5 | 2015-06-15 |  | closed 10/26
2015-08-24 | me | 23283 | 9907.7 | Eaton Corp | 248-226-6796 | net 30 | Duct K&B pre0fabricated ductwork, custom machine connection, install avani | 2015-09-15 |  | call to sch on 10/26
2015-06-23 | ME | 23078 | 4536 | Duke University | 919-668-3207 | Arm 1620,BR006,Customized, install | 2015-08-21 |  | 10/26 Schedule it | 7/6 san mao ordered 6/24 7/13 8/10 customized c shaped hood arms are on boat 9/18 received a replacement green folder DO NOT DUPLICATE PO'S 10/07 pewr Carol with weather permitting, to be near this point the week of October 26th
2015-07-08 | ES | 23128 | 73393 | JC Matamoros | 616-820-3313 | Collector,control panel, silencer, duct, custom, install | 2015-09-15 |  |  | Cell 5, all at brokers 10/13
2015-07-24 | MC | 23180 | 3126 | Regency Sales/Mc Wane Pole | 216-901-9202 | net 30 | arm-2040, suction rail | 2015-10-19 |  | verify arm lines up with suction rail

## Completed Sept (hidden)
Sales Order | Total Due | Project
21709 | 195608.8 | Boilermakers 92 | closed | install | 195608.8
21711 | 77077.3 | 242 | closed | install | 77077.3
21712 | 249470 | 4 | closed | install | 249470
21714 | 121732.05 | 502 | closed | install | 121732.05
23146 | 89100 | ThyssenKrupp | closed | install | 89100
22932 | 13100 | 3m/ Airgas | closed | drop | 13100
23011 | 16538 | A Berger | closed | drop | 16538
22955 | 15378 | Construction Gely | closed | drop | 15378
22890 | 10773 | Airgas/Gala Industries | closed | drop | 10773
23153 | 628.1 | Honda Presision Parts of GA | closed | drop | 628.1
23225 | 1696 | Borg Warner | closed | drop | 1696
23243 | 30419 | Kodiak College/Univ of Alasaka | closed | drop | 30419
23248 | 3500 | Barnes | closed | drop | 3500
23267 | 11563.58 | CMS | closed | drop | 11563.58
23282 | 26834 | Peco Astronics | closed | drop | 26834
23181 | 44479 | Nueva vista | closed | drop | 44479
23337 | 3085 | ThyssenKrupp | closed | install | 3085
23339 | 716.25 | Hydromat | closed | drop | 716.25
23348 | 244.58 | Butler gas/Rosedale | closed | drop | 244.58
23344 | 2625.36 | Zeus | closed |  | 2625.36
23114 | 28967 | Jardine Malaska/Taylorsville HS | closed |  | 28967
23287 | 9530 | therm | closed | drop | 9530
| 953065.02 |  |  |  | 953065.02

## PONTUS
CASE # | DATE | UNDER WARRANTY | PRODUCT COST TO US | SHIPPING COST TO US
1608 | 2015-05-01 | YES/ABSOLENT | 0 | 0
1615 | 2015-05-11 | YES | 490 | 180
1616 | 2015-05-11 | yes | 70 | 12
1617 | 2015-05-11 | yes | 2467 | 286
1618 | 2015-05-11 | yes | 1898 | 10
1619 | 2015-05-11 | yes | 319.2 | 22
1620 | 2015-05-13 | yes | 25 | 11
1628 | 2015-05-18 | yes | 1392 | 0
1630 | 2015-05-18 | yes | 4503 | 341.4
1636 | 2015-05-19 | yes | 32 | 8.85
1638 | 2015-05-19 | yes | 385 | 141.66
1647 | 2015-06-15 | YES | 0 | 11
1657 | 6/2/215 | YES | 1983.6 | 458
1658 | 2015-06-02 | YES | 905 | 32
1659 | 2015-06-03 | yes | 1232.72 | 207.97
1663 | 2015-06-05 | yes | 59 | 6.96
1675 | 2015-06-18 | yes | 0 | 46
1678 | 2015-06-23 | yes | 840 | 22.79
1680 | 2015-06-23 | yes | 110 | 219.45
1681 | 2015-06-23 | yes | 250 | 18
1697 | 2015-07-02 | yes | 694 | 0
1698 | 2015-07-02 | yes | 345 | 32
1710 | 2015-08-09 | YES | 0 | 8.87
1716 | 2015-07-13 | YES | 25 | 9
1719 | 2015-07-13 | yes | 998.4 | 642
1720 | 2015-07-14 | yes | 4147.2 | 300
1730 | 2015-07-22 | yes | 0 | 141.11
1731 | 2015-07-22 | yes | 585 | 178.92
1732 | 2015-07-22 | yes | 0 | 32
1736 | 2015-07-24 | yes | 20 | 14.45
1751 | 2015-07-30 | yes | 20 | 14.45
1752 | 2015-07-30 | yes | 0 | 350
1756 | 2015-07-30 | yes | 0 | 46
1757 | 2015-08-04 | yes | 0 | 83.07
1764 | 2015-08-18 | yes | 1000 | 13.42
1770 | 2015-08-19 | yes | 1261.54 | 0
1771 | 2015-08-27 | yes | 65 | 44.79
Sub Total |  |  | 26122.66 | 3945.16
Total |  | 30067.82
September
CASE # | DATE | Warranty | Product cost | Freight
1779 | 2015-09-01 | YES | 3636 | 2269
1778 | 2015-09-01 | yes | 12 | 149.74

## Items to order
SO |  | Qty | Items | Order deadline | status
Boilermaker 04
Duct
Boilermaker 242
Light kits
duct
20550 | Truform- McClean Fog, IL |  | on hold
21379 | HB Construction
|  | 1 | ACC-5-20
|  | 9 | WB-1044
|  | 9 | ARM-1620
|  | 9 | BR006
|  |  | Duct | Need Sketch | Ed to assess in NM 8/10
21517 | Groathouse-Roosevelt High, WY
22748 | Johnson controls |  |  | 2015-06-22
22954 | Schaeffler mexico |  | duct, fire dampers, MP400, Mpstands | 6/15, 7/1 | 2015-06-23
22932 | 3M |  |  | 2015-08-10
|  | 6 | 5' X 8" flex
|  | 12 | clamps
duct
23128 | JR AUTO |  | 2015-09-15
|  | 1 | SDC-20-16MD |  | Ordered PO 11196
|  | 1 | Control panel |  | Ordered PO 11196
|  | 1 | Silencer |  | Ordered PO 11196
|  | 1 | Inlet plenum | 2015-08-24
|  |  | duct | 2015-08-24
23180 | Regency Sales/Mc Wane Pole
|  | 1 | Arm
|  | 1 | SSR8
23067 | Sampson/Kelly Walsh HS |  | 2015-11-23
|  | 18 | WB1055 ADJUSTIBLE SHELF
|  | 18 | BR006
|  | 18 | ARM1620
|  | 18 | XA-WC-6 curtains | 2015-10-19
|  |  | hooks | 2015-10-19
23207 | American casting
|  | 1 | wb6066C
|  | 1 | SDC-3-12
|  | 1 | 15HP TCBI
|  | 1 | Damper30 (ACT)
|  | 1 | Spark trap
|  | 1 | Cont panel (ACT)
|  | 1 | Custom table/cart
|  | 1 | AV-551BC vac system
23115 | ThyssenKrupp
|  | 2 | A mist 20 |  | PO 11170 7/8/2015
|  | 2 | P trap | stock | shipped 7/27/2015
|  | 2 | 34" legs | B&B
|  | 1 | Duct
23119 | ThyssenKrupp
|  | 1 | A smoke 40 |  | PO 11182 7/9/2015
|  | 1 | Install
23146 | ThyssenKrupp
|  | 5 | A smoke 20 |  | PO11213 7/15/2015
|  | 5 | High dense filter |  | PO11213 7/15/2015
|  | 5 | spray system |  | PO11213 7/15/2015
|  | 5 | P trap | 2015-08-14
|  | 3 | duct
|  | 1 | Install
23167 | ThyssenKrupp
|  | 1 | Jacobs duct |  | PO 11260 7/28/2015
|  | 1 | lift rental
|  | 1 | Install
23197 | Centrix |  |  | 2015-08-25
|  | 1 | Eco fire gate
|  | 1 | Install
23199 | Thomas Linear |  |  | 2015-08-28
22601 | Lee College
|  | 1 | SDC-AT-4-48
|  | 1 | SDC-AT-6-64
|  | 1 | SPC-2807
|  | 90 | WB-1056
|  | 90 | ARM-1620
90
90
90
90
|  | 1 | install
23197 | Centrix |  | 2015-08-25
gate system
Install evergreen
23199 | Thomas Linear |  | 2015-08-28
American castings
APS Pal Verde
USCG training center
Thomas Linear
Rosedale
| Bonney forge |  | duct
Kodiak College
Strayer Voight
Kennemetal/Industrial Dist
Kennemetal/extrude Hone Corp
Weldon Solutions
Barnes
Honda Presision Parts of GA
Barnes
Regency Sales/Mc Wane Pole
Nueva Vista Continuation HS
23176 | Freeport Mc moran |  | hoods from US duct
Borg Warner

## SO items in Shipping
SO # | Customer | Qty | Products in shipping | Location
22748 | Jonson Controls | 2 | KB Duct pallets
|  | 1 | cell transition
23180 | Regency Mcwayne pole | 1 | ARM2040

## CASES
|  | Current open warranty cases | Current pending cases |  | 2015 closed warranty cases |  |  | Total warranty cases for 2015
|  | 15 | 4 |  | 84 |  |  | 99
open case # | REP | Open Date | CASE # | SO # | Product | Serial # | Stopped production | Company Name | Issue | Warr | Status | Pending | Root cause | Short term resolution | Long term resolution | closed | Hours | Freight | Flight | Hotel | Outside contractor costs | parts | gas
10 | RK | 2015-03-03 | 1532 | 22056 |  |  |  | Airgas Torcsill | swap out arms and send duct | yes | Shipped, need to schedule install | 6/22 w/0 done for swaped out arms (3) | [9 empty] | 460.02
31 | BS | 2015-04-16 | 1565 | 20806 | control panel |  | no | honda |  | yes | per Chaz Problem with control panel may be under COMPLETE AUTOMATION RESOUCES WARRANTY. will now more 4/24/15 | Don and Brian Rode to visit 4/23. 5/11 per don Complete automation working on this 5/20 don emailed brody for update. 7/2 Jo emailed Brian R for update
33 | MC | 2015-04-27 | 1597 | 22531 | WB10000 |  | no | PPL | Paint booth | yes | We ordered/sent the wrong booth. PPL will use the booth they have now until we get new booth from taiwan, at which time we will also install. Container due 10/1 | New booth submittal approved 5/15, pending pricing (reqested 5/19) delivery expected early/mid Sept 9/14 per chaz ETS 9/27
52 |  | 2015-06-12 | 1665 | 21919 | (3)SRM 6000's |  | no | Johnson controls | install of 6? roll media (pending ed meeting with TY) in michigan, different transitions, from tiawan, change gears on prototype Customer claims 6 roll media | YES | 3 shipped, 4th at avani 7/2. 7/24 and 7/27 emailed ecolo tech for quote to install RM | 2/19 Drawings from Taiwan, approval, 12-15 weeks lead,3/2 per eric wll need to be installed (6) RM6000 in battle creek michigan | 9/9 talked with bob and doug. Doug wants to set up so it only needs to be connected. Need to order 15 calmps and 90 degree elbows thru K&B
63 | MC | 2015-07-22 | 1732 | 22889 | SPC-2810 |  | no | Architectural Brass | Mike Connors free light kit with purchase. It never shipped | Yes
77 | MC | 2015-08-20 | 1772 | 20894 | SPC-10-6 |  | no | Alcoa | SDC-10-6 not working properly sending bill B to texas | yes |  | 8/27 bill gathered all the info and sent to eric |  |  |  |  | 25 |  | hotel/car 485.54 | 121.42 |  | 895 | 5.6
74 | MC | 2015-08-19 | 1769 | 22152 | WB-6000 |  |  | plumbers and pipefitters | missing gussets (47),9/29 shipped gauges and Cortain rod brackets | yes | [7 empty] | 67 |  |  |  | 1150
75 | KB | 2015-08-19 | 1770 | 22916 | WB-3500 |  | yes | Cal City | all pipes need to be replaced/need light kit | yes |  | 8/27 job is done we have no pricing yet | 9-3 em Jim Dennis for ship tp address 9/8 shipped light kit em Jim L to let him know. Multiple rooms |  |  |  |  | 18 |  |  |  | 75
83 | ES | 2015-09-09 | 1783 | 23239 | a smoke |  | no | Eagle Mechanics | issue is more than the color being different unit was not prepped correctly it appears to be spray painted. peeling off and has scratches.It was determined this could have been a demo unit used taken from place to place.Sandy has already spoken to Ed about this in detail and was told a replacement would be sent and this bad unit picked up.arrange for pick up or provide me with your logistics carrier of choice and account# and I will set up pick up to you. | no | 9/9/ per Ed we have sold the unit to Eagle at a 20% discount. We will be eating the cost of the shipping this unit.
84 | KB |  | 1784 | 22934 | sid panel/springs |  | yes | CMS Alaska | kirk did not order the 2 separate panels also the wrong size spring was shipped. We are sending new springs with brackets | yes | 0
86 | FJ | 2015-09-10 | 1786 | 23166 | duct |  | no | barnes | wrong duct ordered | yes
94 | FJ | 2015-09-21 | 1792 | 23002 | filter &spray system |  |  | US Manufacturing and Ecolotech | 92110901 needs to ship asap to The filter cassette, fiber bed 1,ship directly to US Manufacturing in Warren, MI, 28201 Van Dyke Avenue. zip code 48093. Attention of Mutie Khatib. need to ship part number: 96103006 directly to Ecolo Tech | yes | [11 empty] | 2040.35
97 | CS | 2015-09-29 | 1796 | 22932/23385 | Duct |  | yes | 3M | We only shipped half the duct order | yes | K&B ship date 10/13 then close
99 | AV | 2015-09-24 | 1791 | 22919 | plasma cam 50% |  | no | KW Cages | SPC2000 does not fit, does not work | yes | ed handling?
100 | ES | 2015-10-01 | 1798 | 21709 | cotroller failure |  | yes | Local 92 | need new controller board | yes | sent rita serial numbers
101 | DJ | 2015-10-02 | 1799 | 22601 | taiwan ship error |  | yes | Lee College | See shortages in folder | yes | Eric Contacting Taiwan
PENDING
[8 empty] | Alcoa Waco | Holding SDC hostage | no | [11 empty] | 13783
[5 empty] | custom hood |  |  | Blast and wash | Hood too small, needs to be replaced | yes | pending cheryl info
65 | MC | 2015-07-24 | 1737 | 22884 | 18 booths |  | yes | Rosedale | all booths needed re-wiring, $9000 invoice | yes |  |  | 8/4 client has not paid per eric put aside | [8 empty] | 9000
72 |  | 2015-08-14 | 1767 | 22967 | FUME ARMS |  | YES | Parent kirkbride | we shipped two standing arms when the sales order called for all five to be hanging arms. Based on the way the brackets are bent they were hung upside down. | YES | everything has shipped and we can maybe close | 8/27 emailed brittany. We may owe the company money. 1460.00 dollars | [5 empty] | 19.23 |  |  | 52
| Done | Done | Done | Done |  |  |  | Done | Done | Done | Done | Done |  |  |  | Done
|  |  | n/a | 22344 |  |  |  | Clayton |  | not a case |  | We made a bagde. 2/18 don is taking care of |  |  |  | closed | 1
2 | ES | 2015-02-11 | 1514 | 21442 |  |  |  | CMC Alamo | SDC-15-16 no pulse control | yes | Ordered control from taiwan | 3/3 per chaz will ship 3/6 air. 3/9 shipping |  |  |  | Closed | 1 | 10.04 |  |  |  | 175
3 | MC | 2015-02-19 | n/a | 21468 |  |  |  | PA rail car | Master duct too small | yes | Closed | 3/6 delivered 9"flex 10' long close |  |  |  | Closed | 2
4 | MC | 2015-02-24 | 1518 | 21004 |  |  |  | Norfolk Southern | SPC- 1000 making a loud noise | yes | Where is the SPC? | delivered fed ex track#342823429-4 |  |  |  | Closed | 1
5 |  | 2015-02-25 | 1520 | 22527 |  |  |  | Welding alloys | RL Flange adapters hole pattern doesn't match his SBU-3 | yes |  | 3/19 sent email to adam to see if he was sending back to us? Per adam took of issue in house |  | Re-drill holes |  | closed | 1
7 | MC | 2015-02-18 | 1516 | 22192 |  |  |  | Brennan Environ/sig sauer | Worn brushes | yes |  | shipped 3/3 |  |  |  | closed | 2
8 | MC | 2015-02-19 | 1517 | 22170 |  |  |  | SIFCO ASC | needs replacement telescoping arm spring | yes |  | 2/5 don submitted packing list for spring. 2/25 don shipped sprng |  |  |  | closed | 1
9 | bill b | 2015-03-04 | 1531 | 3 s/o's |  |  |  | Barnes | transitions not welded that barnes fixed |  |  | gave to brittany to issue credit. |  |  |  | Closed
|  | 2015-02-26 | 1521 | 22319 |  |  |  | National Machinery | 2 sets of decals | yes |  | ups tracking 1Z82A9630492866250 |  |  |  | closed | 4
13 | MH | 2015-03-09 | n/a |  |  |  |  | Neumeier | Broken light on side wall of booth | yes | Only the tube, sending picture. |  |  | Pulled light tube from salvage and cut to fit | Keep inventory of 1 4' light tube | closed | 1
19 | KH | 2015-03-03 | 1527 | 22196 |  |  |  | Hagemeyer | cust. Rcvd 2 right booths from stock in our warehouse | yes | [5 empty] | Closed | 1
20 | ES | 2015-03-02 | 1528 | 22066 |  |  |  | Vegas Fasteners | Short SPC2k, ARM1630P, 2 manual starters, return duct Filter light on | yes | SPC-2000 del 3/10 | 3/10 ducts inc approved, given greenlight |  |  |  | Closed | 2 | n/a |  |  |  | 1800
21 | KB | 2015-02-05 | n/a | 22033 |  |  |  | Southern career institute | Control buttons damaged in shipping | yes | [5 empty] | closed | 5 | 11.85
22 | ES | 2015-02-12 | 1515 | 22319 |  |  |  | National Machinery | Damaged in shipping | Yes |  | 2/25 tom em painting himself |  |  |  | closed | 4 | 9.4 |  |  |  | 30
17 | AV | 2015-03-19 | 1543 | 22628 | FM-S116N1 |  | no | Harger Lightning and Grounding | Filter was sent without frame | yes | 3/19 Allana ordered wrong filter new one shipped | 3/23 filter will del 3/24 fedex 773174357658 |  |  |  | 2015-03-25 | 1 | 29 |  |  |  | 80
18 | MC | 2015-03-23 | 1544 | 21468 | ECO-2000 | 114506 | no | PA Rail car | ECO-2000 no gauge, eco 3ooos want gauges relocated | yes | eric got them to relocate gauges | 3/23 need to ship gauges and panels this week | 2 year old product shipped to customer without being updated to current | install gauge |  | 2015-03-26 | 1 | 10.92
11 |  | 2015-03-06 | 1534 | 22078 |  |  |  | Freeport Mcmoran | VFD tripping OVER HEAT, Jacobs duct leaking, Absolent gauge pegged | yes | Complete AR sent new VFD, contractor to fix duct. To be completed 3/23, need absolent serial # to issue warranty PO for new monitor | 3/23 Repair for leak done. 3/30 email for tracking on controller from absolent. No cost to us |  |  |  | 2015-03-31 | 1 | n/a |  |  | 1230.07
8 |  | 2015-03-03 | 1529 | 22316 |  |  |  | ELG Utica Alloys monroe NC | No spark trap on collector, shot blaster port left open. | yes | Quoting dampers and traps | closed 3/31 |  |  |  | 2015-03-31 | 3 | n/a |  |  | 252
n/a |  | 2015-02-11 | 1511 | 20894 |  |  | no | alcoa | hepa filter | yes | [5 empty] | 2015-04-01 | 4 | 711 |  |  |  | 2000
6 |  | 2015-03-04 | 1522 | 21930 |  |  |  | Airgas great lakes White Wave Food | customer claims item sent is wrong rec plenum vs round. | yes | plenum box del 3/16 track#773092693113 | 3/16 per Eric- daniel can contact cust to explain how this works.3/18 daniel call 2x cust did not call back |  |  |  | 2015-04-02 | 2 | 9.39 |  |  | 305 | 135
24 | AV | 2015-03-31 | 1549 | 22663 | FM-20252 |  | no | PCB Piezotronics NC | Return Damaged folter and send new one | yes |  | 3/31 packing list done |  |  |  | 2015-04-06 |  | 18.08 |  |  |  | 250
25 | MC | 2015-03-31 | 1551 | 22598 | 6" hood |  | no | Regency Sales | Hood damaged in shipping per chaz send another we pay for shipping | yes | [5 empty] | 2015-04-06 |  | 17.18 |  |  |  | 189
30 | BS | 2015-04-13 | 1559 | 22267 | lateral |  |  | honda of canada | wrong size | yes | [5 empty] | 2015-04-14 |  | 107.63 |  |  |  | 256
28 | BS | 2015-04-13 | 1558 | 19057 | starter |  |  | airgas | bad starter | yes | per don need case, shipping 4/13 |  |  |  |  | 2015-04-14 |  | 11.82 |  |  |  | 120
1 | ES | 2015-02-10 | 1512 | 18625 |  |  |  | JCC | Silencer leaking | yes | Robbie to modify, daniel to install Tuesday | silencer needs to br rework daniel will go 4/7 |  |  |  | 2015-04-22 | 6 |  |  |  |  | 60
23 | MH | 2015-03-30 | 1548 | Cata- logue | SPC-1000 |  |  | Fatigue | return 2 SPC-1000s for partial credit | NO | These were actually SPC-180s? not 1000s. | Not to arrive until Thursday 4/9 Fed Ex #3131661676
30 | CS | 2015-03-04 | 1556 | 22596 | A mist 40TF |  |  | Caldwell Sheanne | 2 filters had no frame | yes | delivered 4/10 |  |  |  |  | 2015-04-10 |  | 11.82 |  |  |  | 168
16 | ME | 2/18/12015 | 1542 | 20454 | SDC-30-16MDF | 134602 | no | Comfort systems TN Tech/Bristol | Vibration issues | Yes | Need replacement motor ? Going to try impeller only | Mike to install impeller 4/15 | Impeller imbalance | Replace Impeller |  | 2015-04-20 | 10 | 189 | 9 hours |  |  | 1443
14 | MC | 2015-02-11 | 1540 | 21683 |  |  |  | GE Grove city |  | no | getting outside contract for elec to be done |  |  |  |  | 2015-04-22 | [5 empty] | 2530
12 | MC | 2015-03-09 | 1537 | 20735 |  |  |  | Wolf-tec |  | yes | Taiwan recommends a earth leakage breaker, elec contractor determined transformer is leaking. Bonding center tap did not resolve. Recommends supplying house 120V | Local contractor to quote sub panel install.4/20 candi sending over quote to cust. 4/22 have quote for $5966.00. will be charged back to Taiwan |  | replace transformers with house main supplied sub panel |  | 2015-04-28 | 12 |  | 1 flight | 2 nights | 5846.68
29 | CS | 2015-04-13 | 1557 | 22142 | paint booths |  |  | airgas/portersville | naill sticking out of filters/hazard | yes | 4/13 I contact CB for insight4/14 Merchant 1 to replace nails with revised filter holder | Merch 1 to replace with revised filter holder. 4/22 Packing list done for filter holders |  |  |  | 2015-04-28 | [5 empty] | 1000
36 | DM | 2015-04-30 | 1606 | 22314 | switch |  | no | napotnik welding | broke in shipping | yes | shipping out the same day. This was stocked |  | shipping |  |  | 2015-05-05 | 1 | 12 |  |  |  | 175
| FJ | 2015-03-19 | Pend |  | Scientific collector |  |  | Sterling Spring | MANY Pulse valves stuck Working valves= 1,2,3,4,5,6,7,8,9,10, 11,12, 13,14,16,18,19,22,23. Valves not pulsing= 15,17,20,21,24,25,26,27,28,29,30,31,32 (some pulse a small amount, 3 or 4) | no | F. Johnson emailed mgerardi@scientificdust.com | 4/7 sent MC email for update |  |  |  | 2015-05-05
32 |  | 2015-04-17 | 1556 | 22364 | SPCmini | 150619 |  | Step PLUS | Brushes & commutator burned | yes | Don asked San Mao to send replacement brushes, customer wants new motors. | close |  |  |  | 5//11/2015
39 |  | 2015-05-11 | 1616 | 22310 | arms |  | no | SD Industries | 2 arms damaged in shipping | yes | 5/11 We are trying to ship 2030 arms cause we have them in stock per Diana she is checking with mike |  |  |  |  | 2015-05-13 |  | 12 |  |  |  | 70
41 |  | 2015-05-11 | 1618 | 22050 | motor starter |  | no | Spanda | we never ordered the starter | yes | 5/11 we are shipping today |  |  |  |  | 2015-05-19 |  | 9.67 |  |  |  | 1898
30 | mc | 2015-04-16 | 1561 | 22445 | wb,tables |  |  | Veritas | scratches on WB, shorted shipment 2 tables | yes | Cust. To quote repaint. Tables to ship 4/22, M1 to supply paint also | client painted booths himself | Vendors mistakes | issue partial credit, Merch 1 to supply paint. | Supplier quality discussions | 2015-05-19 |  | 0 |  |  | 0
43 |  | 2015-05-12 | 1620 | 21910 | wet collector, light tube |  | yes | Neumeier Engineering | wet collector trips overload, light tube to short | yes | Vender wants pictures form customer of panel, plate Eric in contact with both veder and customer. |  |  |  |  | 2015-05-19 |  | 10.62 |  |  |  | 25
34 | ES | 2015-04-27 | 1596 | 22759 | jacobs duct order | NA |  | National machinery | Duct painted wrong color, pant RAL 7035 per SO | yes |  |  | 5/1 check with marie for credit | issue credit |  | 2015-05-19 | [5 empty] | 218.68
35 | AV | 2015-04-28 | 1598/1612 | 22853 | filter order |  | no | Commercial metals | wrong filters sent, being returned sending new ones | yes |  | I need to do another case. Need to have these brought back and the remaining of the order cancelled. |  |  |  | 2015-05-19 | 1 | 125 |  |  |  | 800
48 | ES | 2015-05-18 | 1638 | 22140 | mp-400 |  | no | hydromat | 3rd mp-400 cust did not receive | [6 empty] | 2015-05-20 |  | 142 |  |  |  | 550
47 | MC | 2015-05-18 | 1636 | 21660 | gas shock | ` |  | William Lynch | customer has tried adjusting the bolts and the arm will stay in place but will not move. When they loosen the bolts so the arm moves, the arm falls to the ground. Sounds like the sock is not holding the arm in place. I spoke with Mike on Friday morning and he said the easiest thing would be to replace the shock. If you could send one to us, we | yes | [5 empty] | 2015-05-20 |  | 9 |  |  |  | 165
38 |  | 2015-05-11 | 1615 | 22685 | mist stop |  | no | Horizon | Mist stop plenum box damaged in shipping | yes | shipment rejected. Item should be enroute to avani | damaged mist stop was del back to avani 5/20 new mist stop tracking fed ex 773625784007 will be del 5/26 |  |  |  | 2015-05-20 |  | 180 |  |  |  | 490
40 |  | 2015-05-11 | 1617 | 22696 | transition/silencer |  | no | Regency Sales | customer not happy with items | yes | we are going to fix it ourself . 5/18 emailed eric for answer on this for diannas emaill | tansition and silencer shipped conway track 565-961126 |  |  |  | 2015-05-22 |  | 286 |  |  |  | 2467
48 | CMS | 2015-06-02 | 1657 | 22896 | SPC-2000 |  | no | Interroll/Airgas | SPC-2000 brand new doesn’t work | yes | ned ost of machine will ship 6/2 without arm which Is not needed | [6 empty] | 458 |  |  |  | 2300
45 | ME | 2015-05-15 | 1628 | 22316 | re-route duct | n/a | no | ELG Utica Alloys | Firewall issue re-route duct. Need elbows, unistrut,drawing | yes | We are sending Daniel next week. Need cost and hours worked | [5 empty] | 32 |  |  |  |  | 1392.59 | 350
51 | MC | 2015-06-05 | 1663 | 22093 | gas shock |  | no | LTS Services | no damage to arm shock absorber not working need a new one it will hold up arm. | yes | [6 empty] | 1 | 6.96 |  |  |  | 20
53 | MC | 2015-06-12 | 1666 | 22345 | booth lights |  | no | Rosedale/Butler Gas | items were not shipped | yes | Jason drove them up to facility 6/12 | Jim Riggs to release collector |  |  |  | 2015-06-12 | 1 | 0 |  |  |  | 0
27 | mc | 2015-04-07 | 1555 | 22345 | ARM-1620 |  | no | Rosedale/butler gas | 3 arms have wrong/weak flex hose and no avani decals | Yes | pend CS order from Taiwan to ship with Rosedale SDT180s | 4/20 Chaz ordering hose for 3 arms will be here from taiwan with SDT180. also need decals . Due at port 6/5 | Old inventory was not updated to current version | replace flex and decals | scrap any old stock |  | 6
26 | BS | 2015-04-07 | 1554 | 21948 |  |  |  | RB&W | Motor Is correct voltage (575) but display controller is 460/240V | Yes | 4/29 24 v will ship 5/4 | 5/11 2 shipped 2 pending for 6/26 |  |  |  |  | 4 |  |  |  |  | 455
47 |  | 2015-05-29 | 1647 | 19858 | 12 booth feet |  | no | bernard mechanical | missing 12 booth feet | yes | Pending air freight/ shipping 6/15 | san mao | shipping 6/15 |  |  |  | 1 | 15
42 |  | 2015-05-11 | 1619 | 21709 | curtains |  | no | local 92 | we sent the wrong size curtains | yes | shipped out the correct size. Close | 5/20 candi order correct size curtains 5/27 I emailed for tracking. Per eric we need other curtains back |  |  |  |  | 1 | 50 |  |  |  | 319
46 | ME | 2015-05-15 | 1630 | 21391 | filters |  | no | Schaeffler | 12 Filters need to be replace may be an absolent issue | yes | Installation week of 6/22 | 5/27 per eric wait to close |  |  |  |  | 8 | 341.4 |  |  |  | 3580
54 | KB | 2015-06-16 | 1674 | 26699 | SDT |  | no | Randolph CC | wrong motor starter sent (taiwan error) | yes | closed |  | Taiwan send wrong voltage starter | Replaced with 230V starter from avani stock |  |  | 2
56 | DM | 2015-06-23 | 1678 | 22579 | filters |  | no | Camfil | we shipped wrong filters | yes | Correct filters to ship 7/2 | [5 empty] | 2 | 22.79 |  |  |  | 0
55 | CMS | 2015-06-18 | 1675 | 22994 | arm |  | yes | Airgas Total access | we shipped SPC-230 without the arm | yes | [6 empty] | 1 |  |  |  |  | 400
44 | Eng | 2015-05-13 | 1621 | N/A | multi items | n/a | n/a | Jacobs | we used items for trade show | no | items returned, PO issued for unaccepted items. Close | PO for remaining items | [5 empty] | 0 |  |  |  | 631
57 | eng | 2015-07-02 | 1698 | 23017 |  |  | no | McClain Tool/LMI Aerospace | need 2 inlet plenum boxes and 1 “special” transition. Inlets are 6" and an 8" jt for A mist 20s |  | Shipped | [6 empty] | 32 |  |  |  | 345
58 | Christa | 2015-07-10 | 1710 | 21039 |  |  | yes | Airgas accrotool | 4 Carbon Filters for an SPC-3000; NONE of the units had the Carbon Filters (which need to be). They are unable to use the units as of now | yes | [7 empty] | 10 |  |  |  | 130
59 | Don | 2015-07-13 | 1716 | 22123 |  |  | no | Encore PKG | 2 swithches for SPC-230 | yes | Shipped | [6 empty] | 9 |  |  |  | 25
49 | ES | 2015-06-02 | 1658 | 21247 | VFS15-4075PL-W |  | yes | National Machine/Kamax | VFD "went up in smoke", may need to relocate VFD | yes | this is a demo unit. | closed |  | Sent PO for replacement
50 |  | 2015-06-03 | 1659 | 21920 | clamps,p traps, flex |  |  | Doosan | Forward company did not deliver 19 flex, clamps, 10 P traps, 4 8" KB clamps 7/1 items ordered | no | 7/15 sending p-traps and 4 8" clamps | flex, p-traps, flanges | ED SAID CANCEL
51 | av | 2015-06-10 | 1664 | 22869 | filter |  | no | Ferza | filter 23050 damaged in shipping | no | 7/2 per alanna told john he needs to open case for damaged goods with UPS. Customer has received new filters in june | [10 empty] | 272
61 |  | 2015-07-13 | 1719 | 22050 |  |  | YES | SPANDA | cartridge leak | yes | [7 empty] | 642
58 | DM | 2015-06-23 | 1680 | 22935 | SPC_1000 |  | yes | Genpak | possible shipping damage, item being sent back | yes | shipping to inspect returned SPC | 7/14 jon found base plate damaged 7/17 robbie sent replace ship next week
66 | MH | 2015-07-30 | 1751 | 21910 | light case |  | no | Neumeier | case for light (we were bot aware of 2nd light case) | yes | w/o done for light case
61 |  |  | 1730 | 22033 | assembly parts |  | yes | southern career | we never shipped the parts for the booth | yes | had to ship to us from taiwan and then shipped to southern career per Chaz | [6 empty] | mao/freight |  |  |  | 1200
64 |  | 2015-07-24 | 1736 | 22864 | missing plates |  | no | MCCowan Gordon | (2) 7x11 plates missing and need painting | yes | wo done for plates
62 | MC | 2015-07-24 | 1731 | 22839/ 23177 | transition |  | no | Alleghenay ATI |  |  | 7/23 ordered from Triangle metalworks transition | [6 empty] | mao/freight |  |  |  | 585
67 | MC | 2015-07-30 | 1752 | 20799 | assembly parts |  | no | General dist | brackets and stands (we forget them) | yes | pack list done shipping 7/30 2 day fedex
63 | MC | 2015-07-14 | 1720 | 21385 | Duct |  | no | Westmoreland college | SDC-AT-4-48 need filters and leak sealed | yes | 7/15 texted mike to see about finished job | 7/23,7/27 sent em candi for tracking | [5 empty] | mao/freight |  |  |  | 4147
70 | DM | 2015-08-04 | 1756 | 23059 | Bracket |  | no | Warner Cillcot | missing br004 | yes | John is sending out BR004 8/5/15 | [6 empty] | 46.73 |  |  |  | 24
69 | DM | 8/4/2015/ re-open 8/10 | 1757/1764 | 23173 | hardware |  | no | Kelso | the arms that were delivered to cust was missing hardware | yes | we are sending materials to cust 8/5 overnight | 8/13 Customer comlaning arms are incorrect | [5 empty] | 83.07 |  |  |  | 50
70 |  | 2015-08-10 | 1764 | 23173 | arms |  | yes | Kelso | Arms need to be cut down 7' to 5' | yes | Jason and Mark going to md this week | 8/13 em joe vass for conformation everything went ok. Arms have been cut and parts were delivered to him. 8/17 making new arm for client | [5 empty] | 13 |  |  |  | 120
62 |  | 2015-07-02 | 1697 | 20072 | Fan, arms, stands |  |  | SW TX Community college | Needs install completed, short starter & exhaust duct. SWTXCC lost arm stands and BR006s | yes | Kirke to quote stands and BR006s | Customer needs motor starter | [9 empty] | 694
59 | es | 2015-06-23 | 1681 | 23015 | Starter overlaod |  | yes | Cathedral Marble | damaged | yes | [7 empty] | 18 |  |  |  | 250
76 | MC | 2015-08-19 | 1771 | 20799 | moter and hose |  | yes | General dist | motor damaged need hose | yes |  | 8/18,8/19 em Jake Shrock per jason to send hose | [5 empty] | 44.79 |  |  |  | 65
79 |  | 2015-08-21 | 1774 | 20799 | hose |  | no | General dist | hose | yes |  | 8/27 per eric we will be adding to this case | [5 empty] | 44.79 |  |  |  | 60
83 | CS | 2015-09-01 | 1778 | 22688 | hose |  | yes | Lagonda Machine | hose is torn they are down shipping hose overnight | yes | [7 empty] | 149.74 OVERNIGHT |  |  |  | 10
84 | KB | 2015-09-01 | 1779 | 22810 | filters |  | NO | DTCC | 12 FM-20050 | yes |  | 9/1 Kirk ordered wrong filters did rga and sent to kirk to send to customer to get filters back. Filters del 9/2 | [5 empty] | 2269 |  |  |  | 3636
84 | cs | 2015-09-08 | 1781 | 22688 | hose |  | yes | Lagonda Machine | christa was going to order a hose under this warranty but its not covered | no
81 | MC | 2015-08-26 | 1776 | 23205 | SPC-230 |  | yes | Solak | 2 motors need to be replaced | yes |  | 8/26 pack list done | [5 empty] | 0 |  |  |  | 150
85 | es | 2015-09-10 | 1785 | 21920 | a mists, parts |  | yes | doosan |  | yes | Absolents have shipped parts ordered | [6 empty] | 0 |  |  |  | 0
78 | MC | 2015-08-20 | 1773 | 22152 | duct,curtains |  | no | plumbers and pipefitters | customer was promised 2 diverter valves | yes |  | 8/20 waiting on quote 8/27 em eric for update | 9/3 Airgas shipping 24 curtains and 530 hooks 9/9 | [8 empty] | 475
68 |  | 2015-08-03 | 1755 | 21468 | filters |  | no | PA Railcar | filters are not cleaning themselves | yes | per Christa need to order more filters. 8/3 per eric give to charles for quote on PTFE filters |  | 8/19 per chaz filters should be here in about 2 weeks 8/27 em chaz for update on filters 8/31 chaz going to follow up |  |  |  |  | 153.99 |  |  |  | 894
88 | DM | 2015-09-11 | 1787 | 22608 | BR-005 |  | yes | Kodiak Alaska watteson | We shipped the wrong item | yes | 9/14 per jon wrong address, will get back to me | [6 empty] | 548 |  |  |  | 648
91 | AV | 2015-09-15 | 1790 | 23309 | SPC-1610 |  | no | Murray | caster broke | yes | 9/15 made pack list | 1Z3899WY0393242087 | [5 empty] | 10.69 |  |  |  | 0
92 |  | 2015-09-17 | 1787 | 22608 | LK-200 |  | no | watterson | need light kits- DISCONTINUED | yes | 9/22 spoke with customer light kits will ship 9/23 | may be a taiwan case. Em chaz to check | 9/22 Taiwan needs to be billed for the light s and the shipping. |  |  |  |  | 58.19 |  |  |  | 225
82 | ME | 2015-08-26 | 1777 | 23203 | ? |  | yes | IDG Corp | Door damaged in shipping, 9/15 em cheryl for update after meeting with Pontus | yes |  | 8/26 I spoke with client sending unit back track number 543037095/ 9/1 unit sent back to us. | 9/7 Client says crate was not damaged but machine was. 5 diffente areas of damage. chaz said put it aside.9/14 emailed chaz for update on what he wants to do 9/22 per client they say they now want the machine pontus will advise of repairs 9/23 jon repairing and taking pictures |  |  |  | 5 | 179.14 |  |  |  | 0
95 | AV | 2015-09-23 | 1793 | 23330 | filters |  | yes | Hunter Engineering | alanna order wrong filters | yes | pack list done for fnew filters need RGA for wrong filters | [6 empty] | 43.88
96 | ME | 2015-09-24 | 1794 | 23168 | spc 2000/spc-807 |  | yes | Airgas schneider electric | Per Christa this customer ordered 3 SPC-2000s Client may want to go with the SPC-807. Per Christa she wants us to ship them 1 SPC-807 in A SPC-2000 box, so they can ship the SPC2000 back to us if they want to keep the SPC-807. if They keep the SPC-807 we will pay for shipping if they don't keep it they will pay for shipping. | yes | 9/28 pack list done RGA form done we r paying for shipping ok per Pontus | [6 empty] | 200.77 |  |  |  | 600
98 | DM | 2015-09-29 | 1797 | 23205 | brushes |  | yes | Solak | brushes burnt | yes | 9/29 pack list done for 8 brushes per chaz
90 | KB | 2015-09-14 | 1789 | 22033 | SPC-5000 | 141402 | yes | Southern Career | was told by Angie unit is making noise | yes | 9/28 angie sent video of broken SPC-5000. gave to chaz and eric. Sounds like impeller broke off. Steveis going to see whats up 10/6 | [5 empty] | 2
80 | MC | 2015-08-26 | 1775 | 23032 | arm1025 |  | yes | Nederman | 24 arms need to be re-worked | yes |  | 8/26 contacted MC for contact at nederman | 8/26 sent em to contact for shipping arms back to us.9/2 sent RGA to nederman. 10/5 other 24 arms shipping 10/7 |  |  |  | 12 | 0 |  |  |  | 532
69 |  | 2015-08-05 | 1761 | 22479 | GB-6000 |  | no | ap wyoming | dent | yes |  | will be shippin from taiwan 9/27 | 10/05 Door will ship 10/06 let jon haas know |  |  |  |  | 309.64 |  |  |  | 500
87 | cs | 2015-09-11 | 1782 | 20799 | motor |  | yes | General Distributing | 30Hp motor failed on dust colletor | yes | 9/11 san mao ordered 9/21 will ship the 25th should delivery around the 30th. 9/21 E`m jeff to see if I can get a forklift 9/23 will need a fork lift | QW`QWHK+9C | [5 empty] | 260.62 |  |  |  | 2200

## Completed Aug
Sales Order | Total Due | Project | Status | ESD
install
23022 | 43335 | Delaware CC | closed | install
22934 | 12638 | Custom Mechanical Alaska | closed | drop
22974 | 22480 | Stackpole International | closed | drop
22984 | 28171 | Georgia Power/RCN | closed | drop
| 3396 | Boilermakers south l37 | closed | drop
23077 | 11804 | Little ELM HS | closed | drop
23136 | 2437.71 | Petron Automation | closed | drop
22916 | 271334 | Cal City/san Bernardino | closed | cont
23166 | 12860 | Barnes | closed | drop
23195 | 244.8 | hennessy | closed | drop
23202 | 74.82 | Pure Power | closed | drop
23115 | 16000 | Thyssen Krupp | closed
23119 | 27456.5 | Thyssen Krupp | closed
23221 | 297.5 | McClain Tool | closed
20799 | 55958 | General Distributors | closed | install
23196 | 4167.65 | dubose | closed | drop
23238 | 408 | Butler gas | closed
23251 | 1273.16 | Kennemetal/Industrial Dist
23246 | 6959 | Kennemetal/extrude Hone Corp | closed
23256 | 7810 | Weldon Solutions
23199 | 9880 | Thomas Linear
23267 | 11563.58 | CMS waco tx
23280 | 7995 | Harbor Freight | closed
23239 | 23058 | Strayer Voight |  | drop
581601.72

## Completed July close
Sales Order | Total Due | Project |  |  | status
22152 | 366183 | Plumbers local 05 | dan/cj, jason |  | closed
22684 | 114000 | San Bernardino | Dust Coll Svc? | conractor | closed
22839 | 38221 | Allegheny/Airgas/ATI | Dan/CJ |  | closed
23008 | 28830 | American Truetzschler | B&B? | conractor | closed
22864 | 123396 | McCown Gordon | Seaman and Schuske Metal Works | conractor | closed
22800 | 127040 | Metform,mcclean fogg | drop |  | closed
22720 | 73440 | Pearson | drop |  | closed
23097 | 7123 | Kadon Precision Machining | drop |  | closed
23100 | 19057 | East Penn/Wann | dorp |  | closed
23072 | 1050 | TRW Fuji Valve | drop |  | closed
22983 | 44289 | Baldor/Narion MFG Plant | drop |  | closed
22828 | 11234 | Bristol/Truform Equipment | drop |  | closed
23073 | 1536 | Hoffman & Hoffman/Baldor | drop |  | closed
22531 | 43077 | ppl |  |  | closed
23148 | 12896 | US Manufacturing/Ecolo Tech | drop |  | closed
23139 | 8262 | Timkin |  |  | closed
23066 | 28202 | thysenn krupp |  |  | closed
23043 | 2816 | thysenn krupp |  |  | closed
23017 | 13078 | Mclain tool |  |  | closed
21920 | 232099.8 | Doosan- Intl. Mexico | closed |  | closed
22152 | 366183 | Plumbers local 05 | closed |  | closed
Total | 1662012.8

## completed june closings
Sales Order | Total Due | Project | Due
22578 | 74420 | South Louisianna Comm Coll | Closed
22345 | 39145 | Butler- Rosedale pittsburg PA | Closed
22884 | 2924 | Rosedale Technical/Butler gas | Closed
22669 | 10025.9 | Randolph Comm College | Closed
22737 | 271.34 | Randolph Comm College | Closed
22283 | 221040 | Alcoa-Waco TX | Closed
22518 | 11876 | Praxair | Closed
22401 | 28048 | Coll of Charleston-Charleston,SC | Closed
21986 21418 | 52847.94 | JR Automation | Closed
22696 | 14000 | Regency Sales | Closed
22685 | 19390 | Horizon | Closed
23010 | 1805 | ACT | Closed
22927 | 40059 | NATIONAL MACHINERY | Closed
22935 | 4903 | GENPAK | Closed
23021 | 3890 | THOMAS LINEAR | Closed
22941 | 14900 | Southside VA Comm College | 2015-06-22
22845 | 13129 | Regency Sales | Closed
23041 | 19157 | Wann Air
22800 | 108880 | Maclean Fogg
23017 | 16152 | Mclain Tool/LMI Aero Washington | Closed
Total | 696863.18