## Status
Order the following items | Action | ship date | delivered | notes
Ductwork cradles and bases
Ductwork
Terostat / elastic adhesive | ordered
Curbs (25 pcs) | ordered | 2006-04-27 |  | Altec providing
Unistrut
Hardware
3/8 nuts, bolts and washers
Self tapping screws
Anchor bolts
Regulator for dust collectors
Cordless Impact Gun
Cart to move ductwork
Items shipping to Altec | Shipping
Robo Vent dust collectors | week of May 1st
Return air Louvers | week of May 1st
Items provided by Altec
Crane to lift duct onto roof
Boom lift for inside work
Run air line to dust collectors
just outside of wall

## Schedule
Description | ship date | Performed by | Date | Notes
Dust Collectors | week of 5/1 | Great Lakes
Set dust collectors |  | IAQ | 2006-05-07
Schedule crane |  | Altec
Run air line to dust collectors |  | Altec | 2006-05-08
Run electrical to collectors |  | Altec | week of 5/7
Roof Curbs | 2006-04-27 | Altec
Attach curbs to roof and cut hole |  | IAQ
Flash curbs and cover |  | Baker Roofing
Ductwork for project |  | IAQ

## Cost breakdown
Description | IAQ Cost
Duct work
From Nordfab | 32827
From Associated Metals | 88825
Elastic adhesive
Henkle Adhesive | 1127.52
Ductwork supports
Chessom machine | 23634
Materials
Unistrut
Hardware
Cordless impact gun
Regulators for DC
Air line piping
Total Costs: | 146413.52
Revenue for Project: | 215000
Profit for Project: | 68586.48
Labor:
IAQ Salaried hours
Hired wages
Don and temp help