## Status
Order the following items | Action | ship date | delivered | notes
Ductwork cradles and bases
Ductwork
Terostat / elastic adhesive | ordered
Curbs (25 pcs) | ordered | 2006-04-27 |  | Altec providing
Unistrut
Hardware
3/8 nuts, bolts and washers
Self tapping screws
Anchor bolts
Regulator for dust collectors
Cordless Impact Gun
Cart to move ductwork
Items shipping to Altec | Shipping
Robo Vent dust collectors | week of May 1st
Return air Louvers | week of May 1st
Items provided by Altec
Crane to lift duct onto roof
Boom lift for inside work
Run air line to dust collectors
just outside of wall

## Schedule
Description | ship date | Performed by | Date | Notes
Dust Collectors | week of 5/1 | Great Lakes
Set dust collectors |  | IAQ | 2006-05-07
Schedule crane |  | Altec
Run air line to dust collectors |  | Altec | 2006-05-08
Run electrical to collectors |  | Altec | week of 5/7
Roof Curbs | 2006-04-27 | Altec
Attach curbs to roof and cut hole |  | IAQ
Flash curbs and cover |  | Baker Roofing
Ductwork for project | 2006-05-07 | IAQ
Collector #1 |  | IAQ | 2006-05-14
Collector #2 |  | IAQ | 2006-05-21
Collector #3 |  | IAQ | 2006-05-28
Collector #4 |  | IAQ | 2006-06-04
Collector #5 |  | IAQ | 2006-06-11
Please note that the installation of the ductwork will vary depending upon the wether.
Note: When installing the ductwork, Baker roofing will be present to flash the duct
supports as they are installed.