QUOTE NUMBER		: 	06-?????

PROJECT DESCRIPTION			: 	EV14 Serial Line 7 Central Vac

ORIGIN DATE		:	02/07/2006

FACILITY			:	Robert Bosch, Charleston, SC

REVISION			:	Orig.

| Contact | Phone | Fax | Email |
| --- | --- | --- | --- |
| ChP/MFE3.3 Bottler | 001 843 760 8634 | 001 843 760 7685 | Rainer.Bottler@us.bosch.com |
| ChP/PUR4 Marano | 001 843 760 7819 | 001 843 760 7815 | helen.marano@us.bosch.com |
| Clean Air Sales Engineer Patrik Newell | (706) 346-5835 | (706) 291- 1747 | patrick.newell@clean-air.com |

1	PROJECT

2	REQUIRMENTS

2.1	TIMING

2.2	TECHNICAL REQUIRMENTS

2.3	DEFINITION OF VACCUUM UNIT AND DROP LOCATIONS

3	QUOTATION INFORMATION

4	ATTACHMENTS

# PROJECT SCOPE

This project includes the central vacuum system and all required duct work for Bosch Charleston EV14 serial line 7 laser welding and general station vacuum requirements.

# REQUIREMENTS

## TIMING

- The listed timings are estimates for the  vacuum system, based on current line 7 installation:

- Submit RQF: 02/17/2006

- Quote due: 03/01/2006

- Order date: 03/15/2006

- Estimated installation window: 05/01/2006 through 05/13/2006

## TECHNICAL REQUIRMENTS

- Supplier will be responsible for all vacuum equipment and duct work

- Favorite Supplier: 	Clean Air

7 Superior Blvd SE

Rome, GA 30161

Sales Engineer: Patrik Newell

- ChP/TEF8 is responsible for the transportation (inside the plant) and the electrical

Installation

- Vacuum requirements are similar to the current EV14 serial line 6 in Charleston

capable of: 6,000 cfm @ 4-6” external static pressure

- Vacuum unit location: between the ceiling and the roof  (above the assembly room)

- Available Space:

Height (Gap between ceiling and roof): 	95 inches

Width:					50 inches

Length:					175 inches

 Clean Air vacuum unit DFC8 does not meet the space requirements!

 Use two smaller vacuum units like line 1\3: DFC4

 In case of a technical fault: install a bypass between unit 1 and 2

- Duct work will be from the vacuum unit to the top frame of the specified stations

- 3” drops can be used only up to the top frame of station

- ATMO (production equipment supplier) is responsible for vacuum lines inside the station to the point of use

- 1.5” lines will be used inside the station due to space limitations

## DEFINITION OF VACCUUM UNIT AND DROP LOCATION

- A layout (an electronic file) has been provided to the supplier defining exact locations of the production equipment

- This file also contains the data for the exact locations of the vacuum unit and all drops to the required stations

- Drop locations for serial line 7 include:

| Station | Amount | Drop Dimension | Comments |
| --- | --- | --- | --- |
| 10 | 1 | 1.5” | Exhaust air laser |
|  | 1 | 2x 32 mm | WT blow off |
| 70 | 1 | 1.5” | Exhaust air laser |
|  | 1 | 80 mm | Housing feeding |
|  | 1 | 80 mm | Coil feeding |
| 80 | 2 | 1.5” | Exhaust air laser |
| 180 | 1 | 1.5” | Exhaust air laser |
| 170 | 1 | 1.5” | Exhaust air laser |
|  | 1 | 80 mm | Filter feeding |
| 210 | 2 | 1.5” | Exhaust air laser |
|  | 1 | 80 mm | Exhaust air laser cabinet |
| 260 | 1 | 2x32 mm | WT blow off |
| 280 | 1 | 80 mm | Exhaust air laser |

# QUOTATION INFORMATION

- The equipment must meet the latest revision (at receipt) of RFQ BOSCH GENERAL DELIVERY SPECIFICATIONS – RBUO DIVISION. A statement confirming this must be in the quote.

- The Bosch Charleston RFQ # must be referenced on the quote.

# Attachments

- Bosch Charleston EV14 Serial Line 7 Installation Timeline

- Serial Line 7 Central Vacuum System Layout