Date: 	11/29/07	  	     PO#: 	 	            IAQ Crew: Bill & David

Customer:	Delta Faucet 					Installation:  X

1425 West Main St.				Service:

Greensburg, IN 47240				Warranty:

Tim Nelson					Repair:

# Scope Of Project

- 11-05-07

  - Arrived on site at 1:30pm with following personnel

    - Bill Boisvert

    - David Frederickson

    - Jason Simons

  - Inspected duct work and move all to out building

  - Reviewed job

  - Started installing plenum boxes

- 11-06-07

  - Continued with plenum box installation

  - Started installing duct header for Area 1

- 11-07-07

  - Bill Lewis arrived on site

  - Continued with duct header installation Area 2

  - Connected machines in Area 1

- 11-08-07

  - Continued with duct header installation Area 3

  - Connected Machines in Area 2

- 11-09-07

  - Jason Simons left site

  - Ran header and connected machines in Building 26

- 11-10-07

  - Ran header in Area 5

- 11-11-07

  - Minor clean up work in Area 5

- 11-12-07

  - Ran header in Area 6

- 11-13-07

  - Ran header in Area 7

  - Completed installation of plenum boxes

- 11-14-07

  - Completed all duct headers

  - Completed machine connections in Area 4

- 11-15-07

  - Cleaned up work Area

  - Moved duct back to outbuilding

- 11-27-07

  - Completed machine connections in Area 7

  - Stared machine connections in Area 6

- 11-28-07

  - Completed Machine connections in Area 6

  - Completed Machine connections in Area 3

- 11-29-07

  - Reworked one connection in Building 26

  - Connected all machines in Area 5

  - Cleaned work area

  - Boxed all remaining duct work (six boxes)

  - Recorded filter pressure reading on Area 1, Area 2, Area 3, Area 4, Area 6, Area 7, and Building 26.

  - Above system all had correct fan rotation.

Please review; make comments, sign and fax page 2 to IAQ office attention Bob Venezia.

CUSTOMER REMARKS:

CUSTOMER SIGNATURE:						DATE:

TITLE OR DEPARTMENT: