## Data
Customer Info
Company Name | Billing Address | City | StateOrProvince | Postal Code
DEUTSCHE PRECISION | 11600 ADIE ROAD | MARYLAND HEIGHTS | MO | 63043
Customer ID | Customer PO
HYDROMAT
Contact #1 | Position | Phone | Mobile
ROB PAYNE | PROJECT ENGINEER | 314-810-3973
Contact #2 | Position | Phone | Mobile
ROB LUTH | ENGINEER | 314-810-3979
Contact #3 | Position | Phone | Mobile
MARVIN | FACILITY MANAGER | 314-576-6291
Avani Envir.
SO#: | Sales Rep. | Start Date | Start Time
19330 | ED | 2013-03-12 | 12:00
Crew Leader | Crew | Crew | Crew
RODNEY | CREW 1

## Project Expeses
Avani Environmental - PROJECT EXPENSES
CUSTOMER: | DEUTSCHE PRECISION |  |  | CITY: | MARYLAND HEIGHTS |  | ST: | MO | SO #: | 19330
|  |  | CREW MEMBERS: |  |  | RODNEY |  | CREW 1
ITEMIZED EXPENSES FOR PROJECT
Date | Travel | Time | Work | Time |  | Auto | Hotel |  | Food | Hardware
| Start | Stop | Start | Stop |  | Expenses |  |  |  | Materials
2013-03-11 | 6:00AM | 11:00AM | 11:00AM | 4:15PM |  |  | 81.89 |  | L14.16/D36.70 | 150.00 SW AIR
2013-03-12 |  |  | 8:00AM | 5:15PM |  |  | 161.24 |  | L16.70 | FASTENAL
2013-03-13 |  |  | 9:36AM | 3:53PM |  | 25.50/25/50 |  |  | L37.06/D25.28
2013-03-13 | 3:53 | 10:32 |  |  |  | 325.04 ENTR
TOTALS: |  |  |  | 31.54HRS. |  | 376.04 | 243.13 |  | 129.9 | 300
Comments & Expense Justification
MATERIAL FROM FASTENAL PRICES WILL SHOW WHEN GET BILLED

## Project Information
Avani Environmental - PROJECT INFORMATION
CUSTOMER: |  | DEUTSCHE PRECISION |  |  | SO#: | 19330
ADDRESS: |  | 11600 ADIE ROAD
CITY: |  | MARYLAND HEIGHTS |  | ST: | MO | ZIP CODE: | 63043
SALES REP: |  | ED |  |  |  | Project #: | 19330
[6 empty] | Crew #: | ONE
[6 empty] | Job Leader: | RODNEY
Time Expected At Job Site: |  |  | 2013-03-12 |  | 12:00 | Actual Time:
Job Site: |  | same as above
Contact: |  | ROB PAYNE |  |  |  | Phone: | 314-810-3973
Position: |  | PROJECT ENGINEER |  |  |  | Mobile:
Contact: |  | ROB LUTH |  |  |  | Phone: | 314-810-3979
Position: |  | ENGINEER |  |  |  | Mobile:
Contact: |  | MARVIN |  |  |  | Phone: | 314-576-6291
Position: |  | FACILITY MANAGER |  |  |  | Mobile:
Other Contact(s):
DIRECTIONS TO JOB SITE (Map Included): | [5 empty] | yes | USE GPS WILL GET
YOU TO JOB AND HOTEL
Local Hotels: |  | DRURY HOTELS |  |  |  | Phone: | 314-576-9966
|  | HYDROMAT CORPORATE RATE |  |  |  | FAX | 888-368-3449
|  | 12220 DORSETT ROAD MARYLAND HEIGHTS |  |  |  | Phone:
SPECIAL INSTRUCTIONS
YES | Fork Lift Required |  |  | Provided by customer
Yes | Scissor / Boom Lift Required |  |  | Provided by customer
NO | Crane Required
NO | Rigging or Special Mechanical Contractors Required
SPECIAL INSTALLATION HOUR IF REQUIRED: | [5 empty] | 7:00AM-4:30PM
SCOPE OF WORK:
SET AND INSTALL ABSOLENT ODR 3000
INSTALL 12" PLENUM WITH JACOBS CONNECTION.
INSTALL JACOB DUCT TO 3 MACH AND 3 FUTURE MACHINES |  |  | 3 MACHINES AND 3 FUTURE MACHINES-CAP OFF DROPS
TO 3 FUTURE MACHINES

## Project Checklist
Avani Environmental - PROJECT CHECKLIST
SO#: | 19330 |  |  |  | CREW #:
PROJECT NAME: |  | DEUTSCHE PRECISION |  |  | JOB | RODNEY
|  | MARYLAND HEIGHTS | MO |  | LEADER
START DATE: |  | 2013-03-12 |  | END DATE:
Y | Called Customer To Set Installation Date
N/A | Attended Customer Safety Meeting (If Required)
Y | Inspected Equipment Being Installed
Y | Inspected Ducting Being Installed
N/A | Called To Have Rental Equipment Picked Up |  |  |  | Date:
| Confirmation #: |  |  | Contact:
Y | Completed Field Report
Y | Filled Out Parts Used Sheet For Project
Y | Cleaned Work Area (Tools, Trash, Materials, Etc.
Y | Reviewed Project (Level & Professional)
NO | Brought Back Additional Ducting, Materials, Parts, Etc.
Additional Ducting, Fitting, Hoods, Etc. Required to Complete Project
TO COMPLETE JOB AVANI WILL HAVE TO SEND FIRE DAMPERS AND
THROTTLE VALVES FOR SIX MACHS.
Customer Comments, Requests or Concerns
CUSTOMER WANTED TO KNOW IF COULD HOOK TO 7 MACH.
** ADVISE CUSTOMER THAT 7 MACH. WOULD BE TO MUCH FOR ODR 3000
CUSTOMER ASKED IF COULD ADJUST TO CONTROL FLOW ** MADE CUSTOMER
AWARE THAT THEY OPTED OUT OF THROTTLE VALVES. CUSTOMER REVISED
Recommended Improvements For Project Efficiency
PLANS NEED TO MATCH THE ORDER PIPE -THIS CAUSES INSTALL CONFUSSION
NEED TO CONTACT CUSTOMER FOR HOTEL RECOMMADATION
NEED TO MAKE SURE PAINT IS SENT FROM JACOBS WHEN ORDER
ASK INSTALLERS TO LOOK AT DRAWINGS AND TALK ABOUT TO RESOLVE
CUFUSION IN THE FIELD
Customer Called for Installation Follow-up (Office Staff)
1 2 3 4 5 6 7 8 9 10 (Comments Below)

## Safety Checklist
Avani Environmental - Safety Checklist
DATE: | 2013-03-12
PROJECT NAME: |  | DEUTSCHE PRECISION |  | SO:# | 19330
CONTACT: |  | ROB PAYNE |  | PHONE: | 314-810-3973
CONTACT: |  | ROB LUTH |  | PHONE: | 314-810-3979
CONTACT: |  | MARVIN |  | PHONE: | 314-576-6291
SAFETY ITEMS REQUIRED (CHECK APPROPRIATE)
YES | SAFETY GLASSES
YES | STEEL TOE SHOES
NO | HARD HAT
YES | SAFETY HARNESS |  | SPECIFY HEIGHT:
YES | HEARING PROTECTION / EAR PLUGS
NO | HAIR NET / FACIAL NET
NO | RESPIRATOR / BREATHING EQUIPMENT
NO | BACK BRACE
SPECIAL PERMITS REQUIRED (CHECK APPROPRIATE)
NO | HOT WORK PERMIT (Welding, Burning, Grinding)
NO | FORKLIFT PERMIT
NO | SCISSOR LIFT / JLG PERMIT
NO | CONFINED SPACE PERMIT
ARE THERE ANY HAZARDOUS CONDITIONS? IF YES EXPLAIN
NO
IS SAFETY TRAINING REQUIRED (IF YES, HOW & WHO MUST ATTEND)
NO

## Machinery Data Sheet
Avani Environmental - Machinery Data
MANUFACTURER: |  | Absolent
MODEL NO: |  |  |  | S/N:
Unit |  | DEUTSCHE PRECISION
Installed |  | 11600 ADIE ROAD
At: |  | MARYLAND HEIGHTS | MO | 63043
Contact: | ROB PAYNE |  |  |  | Installed Date:
Unit | Machine Make/Model |  | ABSOLENT ODR 3000
Installed | Cust. Reference # |  | MIST COLLECTOR
On: | Basic Location |  | EAST BUILDING
Frequency Drive: |  | Yes/No/NA | NO | Oil Pump |  | Yes/No/NA | YES
Electrical Controls |  | Yes/No | YES | Unit Color |  | ABSOLENT GREY
Notes: | ABSOLENT IS CONNECTED TO SIX MACHINES WITH FIRE DAMPERS
AND THROTTLE VALVES. THE DROPS ARE FIVE INCH FROM BRANCHES TO SIX
INCH FIRE DAMPERS,THROTTLE VALVES AND SIX INCH JACOBS CONNECTING
FLANGES. ******THE CONNECTING FLANGS DO NOT MATCH HYDROMATS BOLT
PATTERN, SUGGESTED THAT THEY USE SELF TAPPING SCREWS OR TAP AND
BOLT IN BECAUSE OF VERTICAL POSITION OF DROP
Any Damaged Parts or Problems With The Unit:
JACOBS TUBBING CAME IN WITH SOME SCRATCHES AND DENTS. PAINTED
WHAT COULD GET TO
Unit Gauge Readings
Date | 1st | 2nd | HEPA |  | Gage Units: (INWC, Pa, PSI, Etc.)

## Parts Used Table
Avani Environmental - PARTS RETURNED TABLE
Project # |  | 19330
Date: | 2013-03-12 |  |  |  |  | PROJECT NAME: |  |  | DEUTSCHE PRECISION |  |  | MARYLAND HEIGHTS |  | MO
|  | 4" | 5" | 6" | 7" | 8" | 9" | 10" | 12" | 14" | 16" | 18" | 20" | 22' | Other
Pipe
Nipple
Clamp
30 Deg Elbow
45 Deg Elbow
60 Deg Elbow
90 Deg Elbow
Blast Gate
Angle Ring
Hose Adaptor
End Cap
Screen Cap
|  | A | B | C |  | A | B | C |  | A | B | C
Branch
Y- Branch
|  | A | B | QF |  | A | B | QF |  | A | B | QF
Rect to Round
|  | A | B |  | A | B |  | A | B |  | A | B |  | A | B
Reducer
Custom Hoods, Stands, Etc.
|  | ****************** |  | NO PIPE RETURNED, JOB IS NOT COMPLETE. CUSTOMER TO RECEIVE NEW
|  |  |  | MACHINES TO FINISH JOB. |  |  |  | ************

## Order Form
ORDER FORM |  |  | REP:
DATE: |  |  | ORDERED:
CUSTOMER: |  |  | SO#:
Ship To Address: |  |  | Bill to Address:
TAG:
Shipping Instructions:
Manufacturer:
| PART NUMBER | DESCRIPTION |  | QUANTITY | PRICE | EXTENDED
REQUESTED BY: |  |  |  |  | DATE: