## Sheet1
Equipment shipped to Fillauer
Mfg | Description | Status
Dustex | Dust collector model 3339-6-6 | At Fillauer
| multiple pieces for assembly | as of 7/17
cages and bags
support braces
hopper section
bag house section
Drum lid kits
ladder and rails
IAQ | 36"x 24" Downdraft table | Shipped
| For Dust collector project | 2007-07-18
1pc Aluminum mesh filter shipped
install in the Wet collector
25' of 4" Urethane flex duct.
For Dust collector Project
AT Products | Wet Collector model C5-1800 | At Fillauer
as of 7/17
Conveyability | Electrical contro panel for the | At Fillauer
| dust collector project | as of 7/17
Mount inside in room. See Patti
for exact location
Hutchco | Twin City exhaust fan model | At Fillauer
| BCS300 20Hp for dust project | as of 7/17
American | Vertical hoods for the Trautman | Shipped
Blower | Grinders (5 pcs) for Dust project | 2007-07-09
Nordfab | Nordfab ductwork for Wet collector | Shipped
295603 |  | 2007-07-11
Nordfab | Nordfab ductwork for Dust | Shipped
295602 | Collector Project | 2007-07-11