## Sheet1
Installation Schedule Honda Power Equipment Swepsonville NC
Available to Commence Hood Installation |  |  | April | May | June | July | Aug
Crankshaft Finishing |  | Avail Date
| Crank 1 | 2004-06-12
| Crank 2 | Now
Barrel Transfer
| Barrel 1 | 2004-05-02
| Barrel 2 | Now
Oil Pan/Conn Rod
| Oil Pan | Now
| Conn Rod | 2004-06-03
IAQ Installation Notes
1. IAQ will install the capture hoods and other collection devices as the production machines are put into place
2. Hood layout and design can be done during production time but installations will be done on weekends.
Honda must approve installations that will take palce during production periods.
3. Absolent machines will be assembled on the overhead platforms during one installation period if possible
4. Connection between main trunk line and installed hoods will be completed during weekends
unless alternative installation time is approved by Honda
5. Absolent delivery schedule yet to be determined.
Honda Installation Notes
1. Honda will provide the platforms/drawings to support the Absolent installation schedule
2. Honda personnel will be available for weekend support (general questions/approvals)
3. Electrical installation schedule responsibility of Honda