## Case Schedule
Honda
Tallapoosa, GA
Case Line Absolent Installation schedule
Absolent equipment
Once ordered it takes about 8 to 9 weeks for delivery
Installation of Absolents and ductwork
2 to 3 weeks for all units after delivery date
Completion of install for Case line will vary with delivery
Final walk through
One week after installation has been completed
Please note installation times may vary with early arrvial of
equipment and can install certain machines sooner
as well.
Note:
Will need to make an engineering site visit to determine
the exact location of each Absolent unit and ductwork
layout.