## Sheet1
Honda power / Tallapoosa, GA
Installation Schedule |  |  | Scheduled | Completed Date
|  |  | Install | Absolent |  | Drain
Valve Body Line: |  |  | Date | or Amtech | Ductwork | Line | Notes
1 | Transfer Machine | ODF 6000 | 2007-03-19
2 | P-Type Module | ODF 4000T | 2007-03-19
3 | Fine Bore Machine | ODF 4000T | 2007-02-26
4 | Oil Hole NC Machine | ODF 4000T | 2007-03-19
5 | Washer | ODF 4000T | 2007-03-19
6 | Grinder | ODF 6000 | 2007-03-19
7 | Vertical Mill | ODF 2000 | 2007-03-19
M Case Line
8 | Rotary Mill | AT - 4 | 2007-02-26
9 | NC Machines #1 | ODF 4000T | 2007-02-26
10 | NC Machines #2 | ODF 6000 | 2007-02-26
11 | NC Machines #3 | ODF 6000 | 2007-02-26
12 | TH Machine | ODF 4000T | 2007-02-26
13 | Pack Machine #1 | ODF 6000 | 2007-03-19
14 | Pack Machine #2 | ODF 6000 | 2007-03-19
TC Case Line
15 | VM5 Machine | ODF 2000 | 2007-02-26
16 | Rotary Mill | AT - 4 | 2007-02-26
17 | NC Machines #4 | ODF 6000 | 2007-03-19
18 | NC Machines #5 | ODF 4000T | 2007-02-26
19 | NC Machines #6 | ODF 6000 | 2007-03-19
20 | Pack Machine #3 | ODF 6000 | 2007-03-19
21 | Pack Machine #4 | ODF 6000 | 2007-03-19