## Schedule
Honda
Tallapoosa, GA
Valve Body Maching Line Absolent Installation schedule
Absolent equipment ordered
November 10th, 2006
Delivery of Absolents (8 to 9 weeks)
Week of January 15th, 2007
Installation of Absolents and ductwork
2 to 3 weeks for all units
Completion of install for Valve Body Line Feb 9th, 2007
Final walk through
February 15th, 2007
Please note installation times may vary with early arrvial of
equipment and can install certain machines sooner
as well.
Note:
Will need to make an engineering site visit to determine
the exact location of each Absolent unit and ductwork
layout.