Date: 	4/9/08	  	     Project#: Absolents           IAQ Crew Leader:  Bill Boisvert

Customer:	Kennametal					Installation:  X

100 Kennametal Drive			Service:

Weldon, NC 27890				Warranty:

Dan Kline					Repair:

# Scope Of Project

- 03/31/08 – 04/02/08

  - Installed Plenum Boxes on Absolents for machine groups 5 & 6

  - Installed Connection flanges on machines in group 6

  - Ran duct from ODF-4000TF to Machines in group 6

  - Ran drain lines for Absolents in machine groups 5 & 6

  - Assessed tubing needs

  - Cleaned Area

- 04/4/08 – 04/05/08

  - Ran duct from ODF-4000TF to machines in group 5

  - Removed temporary duct installation groups 3 & 4

  - Ran duct from ODF-4000TF to machines in group 3

  - Removed ODF-2000 from machine in group 3

  - Ran duct from ODF-4000TF to machines in group 3

  - Removed flex duct from machines in groups 1 & 2

  - Installed connection flanges on machines in groups 1 & 2

  - Moved ODF-4000TF’s for machine groups 1 & 2

  - Ran duct from ODF-4000TF to machines in group 1

  - Ran duct from ODF-4000TF to machines in group 2

  - Ran drain lines for Absolents in machine groups 1 & 2

  - Reworked drain line on ODF-4000TF in machine group 7

  - Cleaned area

- 04/08/08

  - Uncrated ODF-4000TF for Machine Group 9

  - Set ODF in place

  - Removed ODF-2000

  - Attached connection flanges to machines

  - Ran duct to three of four drops in machine group 9

    - Missing 1, 200mm to 100mm cone and 1, 100mm clamp.

  - Inventoried all remaining tubing, placed in two boxes

  - Removed all empty boxes and pallets, cleaned area.

I have all the parts for the last drop at our shop (except two missing parts) so that when we get the last two parts we 2will know where they are.  All remaining Jacob Tubing needs to be returned to Jacob (or Proeco) for credit.  (Inventory sheets attached)

Will return to complete the last drop as soon as we get the parts.

Please sign the last page and fax to IAQ

Thanks,

Bill Boisvert, Field Supervisor IAQ

CUSTOMER REMARKS:

CUSTOMER SIGNATURE:						DATE:

TITLE OR DEPARTMENT: