## Sheet1
| Sales Order #: | 18570 |  |  |  | Rep: | Mark
| Project Name: | RBC Bearings |  |  |  | PO# | 2205979
Brief Description:
install 3 odf 1000s and 1 odf 2000
| Duct Drawings Submitted: |  | yes | Customized Products: |  | no
| Contractors Needed: |  | no
EQUIPMENT Commissions | Manufacturer | Product | PO | AVI Cost | Quantity | Total | Customer PO $ | Margin
| Absolent |  | 4573 | 12736.1 | 1 | 12736.1 | 19594 | 35%
0
0
0
0
| TOTAL |  |  |  |  | 12736.1 | 19594 | 35%
| Project Start / Finish Dates: |  |  | 6/15/2012-6/19/12
| Location: | Hartsville, SC
| Crew Leader: | Rodney
LABOR / DUCT Commissions | Manufacturer/Supplier | Product | PO | Avani Costs | Quantity | Total | Quoted | Margin
| Triangle Metal | Misc Duct | 4576 | 600 | 1 | 600 | 15216 | 33.33%
| K&B | Duct | 4575 | 1716.13 | 1 | 1716.13
| Triangle Metal | Misc Duct | 4712 | 215 | 1 | 215
| Fastenal | Gripples | 4806 | 160.92 | 1 | 160.92
| K&B | Duct | 4804 | 6164.03 | 1 | 6164.03
| Triangle Metal | Misc Duct | 4805 | 80 | 1 | 80
|  | Hardware | CC | 414.37 | 1 | 414.37
| Avani | Duct | - | 794.19 | 1 | 794.19
| Labor-Travel |  |  | 62 | 30.5 | 1891 | 7200 | 4.847%
| Labor - On-site |  |  | 62 | 80 | 4960
Labor - Other
AirFare
Over Night Stays
Other:
| TOTALS |  |  |  |  | 16995.64 | 22416 | 24.18%
| JOB TOTAL |  |  |  |  | 29731.74 | 42010 | 29.23%
Note on E9: Cynthia: Add 15% for container shipments

## Sheet2
28 | 90 | 2520
2 | 165 | 330
5 | 18.315 | 91.575
1 | 36.33 | 36.33
17 | 15.6375 | 265.8375
2 | 31.7775 | 63.555
2 | 25.6425 | 51.285
3358.5825