## Sheet1
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Nov 28th | Nov 29th | Nov 30th | Dec 1st | Dec 2nd | Dec 3rd | Dec 4th
IAQ/PMS
| Move A/C | Build Pad
Demo work
Dec 5th | Dec 6th | Dec 7th | Dec 8th | Dec 9th | Dec 10th | Dec 11th
Install
ODR 18000, Sheldon's Exhaust Fan and ductwork inside
Install Pre-Inlet box and pumps
Ductwork delivered on 12/6
Dec 12th | Dec 13th | Dec 14th | Dec 15th | Dec 16th | Dec 17th | Dec 18th
| Take out 2 | Install new cyclone, ductwork on roof, blast gates, access doors
| fans. | Install rotary airlock
Demo on roof
RJR shutdown
Dec 19th | Dec 20th | Dec 21st | Dec 22nd | Dec 23rd | Dec 24th | Dec 25th
|  |  | Finish Project |  | X-mas eve | X-Mas