## Outage
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  | None, b/u rate |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 12 | 0 | 2 | 42 | 14.4 | 604.8
Cert/Prec/ | 2 | 12 | 0 | 2 | 40 | 16.8 | 672
Craft | 0 | 12 | 0 | 2 | 37 | 12 | 444
Helpers |  |  |  |  | 34 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 2 | 14 |  |  | 4.5 |  | 126
Avg Cost $/hr w/pd | 42.75 |  |  |  |  | 43.2 | 1846.8
Equipment
Cosumeables |  |  |  | 43.2 | 1 |  | 43.2
Small Tools |  |  |  | 43.2 | 0.5 |  | 21.6
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 2 |  |  | 7 | 4 |  | 56
Forkifts | 0.5 |  |  | 7 | 6 |  | 21
Torches | 2 |  |  | 7 | 1 |  | 14
Rigging | 1 |  |  | 7 | 1 |  | 7
Manlift | 1 |  |  | 7 | 14 |  | 98
Total | [6 empty] | 3736.8
Demo Roof
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  | None, b/u rate |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 |  | 0 | 0 | 33 |  | 0
WF/GF | 1 | 25 | 0 | 2 | 42 | 30 | 1260
Cert/Prec/ | 2 | 25 | 0 | 2 | 40 | 35 | 1400
Craft | 2 | 25 | 0 | 2 | 37 | 35 | 1295
Helpers |  |  |  |  | 34 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 4 | 27 |  |  | 4.5 |  | 486
Avg Cost $/hr w/pd | 44.41 |  |  |  |  | 100 | 4441
Equipment
Cosumeables |  |  |  | 100 | 1 |  | 100
Small Tools |  |  |  | 100 | 1 |  | 100
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 2 |  |  | 13.5 | 4 |  | 108
Forkifts | 0.5 |  |  | 13.5 | 6 |  | 40.5
Torches | 2 |  |  | 13.5 | 1.5 |  | 40.5
Rigging | 1 |  |  | 13.5 | 1 |  | 13.5
Manlift | 0 |  |  | 13.5 | 14 |  | 0
Total | [6 empty] | 8982
Install frame & collector
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  | None, b/u rate |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 20 | 0 | 2 | 42 | 24 | 1008
Cert/Prec/ | 2 | 20 | 0 | 2 | 40 | 28 | 1120
Craft | 1 | 20 | 0 | 2 | 37 | 24 | 888
Helpers |  |  |  |  | 34 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 3 | 22 |  |  | 4.5 |  | 297
Avg Cost $/hr w/pd | 43.5921 |  |  |  |  | 76 | 3313
Equipment
Cosumeables |  |  |  | 76 | 1 |  | 76
Small Tools |  |  |  | 76 | 0.5 |  | 38
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 2 |  |  | 11 | 4 |  | 88
Forkifts | 0.5 |  |  | 11 | 6 |  | 33
Torches | 2 |  |  | 11 | 1 |  | 22
Rigging | 1 |  |  | 11 | 1 |  | 11
Manlift | 1 |  |  | 11 | 14 |  | 154
Total | [6 empty] | 6702
Demo fans
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  | None, b/u rate |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 10 | 0 | 2 | 42 | 12 | 504
Cert/Prec/ | 2 | 10 | 0 | 2 | 40 | 14 | 560
Craft | 0 | 10 | 0 | 2 | 37 | 10 | 370
Helpers |  |  |  |  | 34 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 2 | 12 |  |  | 4.5 |  | 108
Avg Cost $/hr w/pd | 42.8333 |  |  |  |  | 36 | 1542
Equipment
Cosumeables |  |  |  | 36 | 1 |  | 36
Small Tools |  |  |  | 36 | 0.5 |  | 18
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 2 |  |  | 6 | 4 |  | 48
Forkifts | 0.5 |  |  | 6 | 6 |  | 18
Torches | 2 |  |  | 6 | 1 |  | 12
Rigging | 1 |  |  | 6 | 1 |  | 6
Manlift | 1 |  |  | 6 | 14 |  | 84
Total | [6 empty] | 3120
Duct tie ins
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  | None, b/u rate |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 10 | 0 | 2 | 42 | 12 | 504
Cert/Prec/ | 2 | 10 | 0 | 2 | 40 | 14 | 560
Craft | 1 | 10 | 0 | 2 | 37 | 12 | 444
Helpers |  |  |  |  | 34 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 3 | 12 |  |  | 4.5 |  | 162
Avg Cost $/hr w/pd | 43.9474 |  |  |  |  | 38 | 1670
Equipment
Cosumeables |  |  |  | 38 | 1 |  | 38
Small Tools |  |  |  | 38 | 0.5 |  | 19
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 2 |  |  | 6 | 4 |  | 48
Forkifts | 0.5 |  |  | 6 | 6 |  | 18
Torches | 2 |  |  | 6 | 1 |  | 12
Rigging | 1 |  |  | 6 | 1 |  | 6
Manlift | 1 |  |  | 6 | 14 |  | 84
Total | [6 empty] | 3378
A Comp relocate
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  | None, b/u rate |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 6 | 0 | 2 | 42 | 7.2 | 302.4
Cert/Prec/ | 2 | 6 | 0 | 2 | 40 | 8.4 | 336
Craft | 0 | 6 | 0 | 2 | 37 | 6 | 222
Helpers |  |  |  |  | 34 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 2 | 8 |  |  | 4.5 |  | 72
Avg Cost $/hr w/pd | 43.1667 |  |  |  |  | 21.6 | 932.4
Equipment
Cosumeables |  |  |  | 21.6 | 1 |  | 21.6
Small Tools |  |  |  | 21.6 | 0.5 |  | 10.8
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 2 |  |  | 4 | 4 |  | 32
Forkifts | 0.5 |  |  | 4 | 6 |  | 12
Torches | 2 |  |  | 4 | 1 |  | 8
Rigging | 1 |  |  | 4 | 1 |  | 4
Manlift | 1 |  |  | 4 | 14 |  | 56
Total | [6 empty] | 1886.4
ABS Start up
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  | None, b/u rate |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 12 | 0 | 2 | 42 | 14.4 | 604.8
Cert/Prec/ | 2 | 12 | 0 | 2 | 40 | 16.8 | 672
Craft | 0 | 12 | 0 | 2 | 37 | 12 | 444
Helpers |  |  |  |  | 34 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 2 | 14 |  |  | 4.5 |  | 126
Avg Cost $/hr w/pd | 42.75 |  |  |  |  | 43.2 | 1846.8
Equipment
Cosumeables |  |  |  | 43.2 | 1 |  | 43.2
Small Tools |  |  |  | 43.2 | 0.5 |  | 21.6
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 2 |  |  | 7 | 4 |  | 56
Forkifts | 0.5 |  |  | 7 | 6 |  | 21
Torches | 2 |  |  | 7 | 1 |  | 14
Rigging | 1 |  |  | 7 | 1 |  | 7
Manlift | 1 |  |  | 7 | 14 |  | 98
Total | [6 empty] | 3736.8

## Total Work sheet
Description | cost | Labor Included for ST or Outage | Notes |  | demo | inst
Demo Roof & equipment | 10500 | O |  | * | 7800
Install Roof Frame & cyclone | 7450 | O |  |  |  | 7250
Fabricate Platform & deliver | 16400 | S | galvanized 1" grating, yellow Hrails/2 coats paint |  |  | 16000
Install Platform | 12000 | O | no crane, no roofing, |  | 9800
Demo Fans | 3120 | O | leave platforms | * | 3000
Install IAQ duct at fans | 1250 | O | duct and up to 2 loose flanges to be installed |  |  | 1000
Housekeeping Pads | 2650 | S | as required by drawings |  |  | 2650
Install IAQ Duct | 8150 | S&O |  |  |  | 6000
Install ABS Equip | 6258 | S | includes piping & tye in & bollard demo | *1/2 | 2800 | 2250
Relocate Acomp | 1245 | O | stored on site at your location | * | 1000
Hanger mat | 2110 | N/A | threaded rods & other needs
Start up labor | 2900 | O | one day 2 folks at ot with equip |  |  | 1200
Crane 70t (10 days at 10-12 hrs) | 17500 | Both | outage will require ot with crane |  |  | 12800
Total | 91533 |  |  |  | 24400 | 49150
Complete Total project as required by drawings no discussions |  |  |  |  | 73550
General Notes:
No hazardous material demo allowed for
All parts other than structural steel, hanger rods, concrete and rebar by IAQ
All Steel is primed and painted
Minimal OT allowed for during shutdown, need plant access 12/20-23 &12/27-31 with start up on Monday 1/2/05
All support/hanger material is removed
All other items from proposal remain the same

## Preoutage
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  |  |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 20 | 0 | 2 | 31 | 24 | 744
Cert/Prec/ | 2 | 20 | 0 | 2 | 30 | 28 | 840
Craft | 1 | 20 | 0 | 2 | 26 | 24 | 624
Helpers |  |  |  | 2 | 21 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 4 | 22 |  |  | 4.5 |  | 396
Avg Cost $/hr w/pd | 34.2632 |  |  |  |  | 76 | 2604
35 or less
Equipment
Cosumeables |  |  |  | 76 | 1 |  | 76
Small Tools |  |  |  | 76 | 0.5 |  | 38
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 4 |  |  | 11 | 4 |  | 176
Forkifts | 1 |  |  | 11 | 6 |  | 66
Torches | 2 |  |  | 11 | 1 |  | 22
Rigging | 1 |  |  | 11 | 1 |  | 11
Manlift | 1 |  |  | 11 | 14 |  | 154
Total | [6 empty] | 5284
Duct Install
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  |  |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 35 | 0 | 2 | 31 | 42 | 1302
Cert/Prec/ | 1 | 35 | 0 | 2 | 30 | 42 | 1260
Craft | 2 | 35 | 0 | 2 | 26 | 49 | 1274
Helpers |  |  |  | 2 | 21 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 4 | 37 |  |  | 4.5 |  | 666
Avg Cost $/hr w/pd | 33.8496 |  |  |  |  | 133 | 4502
35 or less
Equipment
Cosumeables |  |  |  | 133 | 1 |  | 133
Small Tools |  |  |  | 133 | 0.5 |  | 66.5
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 4 |  |  | 18.5 | 4 |  | 296
Forkifts | 1 |  |  | 18.5 | 6 |  | 111
Torches | 2 |  |  | 18.5 | 1 |  | 37
Rigging | 1 |  |  | 18.5 | 1 |  | 18.5
Manlift | 1 |  |  | 18.5 | 14 |  | 259
Total | [6 empty] | 9137
Abso Install
Perdiem Rate-S-WF | 60
Perdiem Rate-all others | 45
Hours/day | 10 |  |  |  |  | Total | Total
Description | Total Crew | Hours/ST | Hours/OT | Travel | Rate | Equiv. Hrs | Dollars
Super | 0 | 0 | 0 | 0 | 33 | 0 | 0
WF/GF | 1 | 20 | 0 | 2 | 31 | 24 | 744
Cert/Prec/ | 2 | 20 | 0 | 2 | 30 | 28 | 840
Craft | 1 | 20 | 0 | 2 | 26 | 24 | 624
Helpers |  |  |  | 2 | 21 | 0 | 0
Perdiem
S-WF | 1 | 0 |  |  | 6 |  | 0
All Others | 4 | 22 |  |  | 4.5 |  | 396
Avg Cost $/hr w/pd | 34.2632 |  |  |  |  | 76 | 2604
35 or less
Equipment
Cosumeables |  |  |  | 76 | 1 |  | 76
Small Tools |  |  |  | 76 | 0.5 |  | 38
Trucks | 2 |  | milage,1 way | 200 | 0.35 |  | 140
welders | 4 |  |  | 11 | 4 |  | 176
Forkifts | 1 |  |  | 11 | 6 |  | 66
Torches | 2 |  |  | 11 | 1 |  | 22
Rigging | 1 |  |  | 11 | 1 |  | 11
Manlift | 1 |  |  | 11 | 14 |  | 154
Total | [6 empty] | 5284