## Sheet1
| Sales Order #: | 18672 |  |  |  | Rep: | Ken
| Project Name: | THK Rhythm |  |  |  | PO# | 11682
Brief Description:
Install ODR-3000 & ductwork
|  | Duct Drawings Submitted: |  |  |  | NO
|  | Customized Products: |  |  |  | NO
|  | Contractors Needed: |  |  |  | NO
EQUIPMENT | Manufacturer | Product | PO | AVI Cost | Quantity | Total | Quoted by Sales | Margin
| Absolent | ODR-3000 | 4732 | 16011.45 | 1 | 16011.45 | 23402 | 31.58%
| K&B | Duct | 4746 | 1482.86 | 1 | 1482.86 | 2300 | 27.12%
| Triangle Metal | Duct | 4745 | 125 | 1 | 125
| Fastenal | Gripples | 4747 | 68.34 | 1 | 68.34
0
Freight
| Materials - Duct From Vendor |  |  |  |  | 0
| Materials - on the job |  |  | 92.48 | 1 | 92.48
| Material - Other |  |  |  |  | 0
| Duct Returned |  |  | 303.87 |  | 303.87
| TOTALS |  |  |  |  | 17476.26 | 25702 | 32%
| Project Start / Finish Dates: |  | 6/20-6/22/12
| Location: | Sparta, TN
| Crew Leader: | Rodney
LABOR | Tasks |  |  | Avani Costs | Quantity | Total | Quoted | Margin
| Labor - Travel Cost / Man Hour |  |  | 62 | 21 | 1302 | 2400 | 19.92%
| Labor - On-site / Man Hour |  |  | 62 | 10 | 620
| Labor - Other Costs |  |  |  |  | 0
| Airfare: No |  |  |  |  | 0
Total Overnight Stays:
Other -
| TOTALS |  |  |  |  | 1922 | 2400 | 19.92%
| JOB TOTAL |  |  |  |  | 19398.26 | 28102 | 30.97%
Note on E10: Cynthia: Add 15% for container shipments
Note on F27: Cynthia: x2 men
Note on E28: Cynthia: use 75 for 1 man crew
Note on F28: Cynthia: x2 men

## Sheet2
28 | 90 | 2520
2 | 165 | 330
5 | 18.315 | 91.575
1 | 36.33 | 36.33
17 | 15.6375 | 265.8375
2 | 31.7775 | 63.555
2 | 25.6425 | 51.285
3358.5825