## Sheet1
| Name | Phone Number | Contact | Location | Site Visit
| Local 242 | (509) 489-1891 | Mark Keffeler | 6404 Pittsburg Spokane WA | 7/28/14 at 8:00 AM
| Local 502 | (253) 435-0330 | Tracy Eixenberger | 16621 110 Ave Puyallup, WA | 7/28/14 at 3:00 PM
| Local 242 | (360) 904-1400 | Steve Burger | 2515 NE Columbia Blvd Portland, OR | 7/29/14 at 8:00 AM
| Local 92 |  |  | 2260 Riverside Ave Bloomington, CA | 7/30/14 at lunch
| Local 04 |  |  | 294 Cowboy Ray Road Page, AZ | 7/31/14 at 8:00 AM
Name | Drawing/Layout Complete | Drawing/Layout Approved | Equipment/ Duct Ordered | Equipment/ Duct On Site | Install Start | Install Complete
Local 242 | 2014-08-15 | 2014-08-20 | 2014-08-25 | 2014-11-03 | 2014-11-03 | 2014-11-10
Local 502 | 2014-08-15 | 2014-08-20 | 2014-08-25 | 2014-11-03 | 2014-11-03 | 2014-11-10
Local 242 | 2014-08-15 | 2014-08-20 | 2014-08-25 | 2014-11-10 | 2014-11-10 | 2014-11-17
Local 92 | 2014-08-15 | 2014-08-20 | 2014-08-25 | 2014-11-10 | 2014-11-10 | 2014-11-17
Local 04 | 2014-08-15 | 2014-08-20 | 2014-08-25 | 2014-11-03 | 2014-11-03 | 2014-11-10