## Sheet1
| Sales Order #: | 18582 |  |  |  | Rep: | Ed
| Project Name: | Curtis Niagra |  |  |  | PO# | B9724
Brief Description:
Install ODR3000 and Jacob Duct
| Duct Drawings Submitted: |  | yes | Customized Products: |  | no
| Contractors Needed: |  | no
EQUIPMENT Commissions | Manufacturer | Product | PO | AVI Cost | Quantity | Total | Customer PO $ | Margin
| Absolent | ODR3000 | 4590 | 18778.5 | 1 | 18778.5 | 28924 | 35.08%
0
0
| TOTAL |  |  |  |  | 18778.5 | 28924 | 35.08%
| Project Start / Finish Dates: |  | 6/8/12-6/11/12
| Location: | Buffalo, MY
| Crew Leader: | Daniel
LABOR / DUCT Commissions | Manufacturer/Supplier | Product | PO | Avani Costs | Quantity | Total | Quoted | Margin
| Triangle Metal | Plenum | 4627 | 125 | 1 | 125 | 5806 | 12.73%
| Jacob Tube | Duct | 4626 | 5480.07 | 1 | 5480.07
| Jacob Tube | Duct | 4635 | 8.91 | 8 | 71.28
| LR Gorrell | Fire Dampers | 4634 | 26 | 8 | 208
| Jacob Tube | Duct | 4728 | 106.42 | 1 | 106.42
| Other: | Hardware | - | 199.03 | 1 | 199.03
| RETURNED | Duct | - | 1122.77 | -1 | -1122.77
| Labor-Travel |  |  | 62 | 56.5 | 3503 | 6250 | -7.136%
| Labor - On-site |  |  | 62 | 51.5 | 3193
Labor - Other
AirFare
Over Night Stays
Other:
| TOTALS |  |  |  |  | 11763.03 | 12056 | 2.43%
| JOB TOTAL |  |  |  |  | 30541.53 | 40980 | 25.47%
Note on E9: Cynthia: Add 15% for container shipments

## Sheet2
28 | 90 | 2520
2 | 165 | 330
5 | 18.315 | 91.575
1 | 36.33 | 36.33
17 | 15.6375 | 265.8375
2 | 31.7775 | 63.555
2 | 25.6425 | 51.285
3358.5825