**Delaware Tech Change Order Items**

1. $450.00 Labor Delay on 2/17/11

 Delay onsite due to booth layout change because they did not fit where approved.

2. $985.00 Modification to end panel and shelf

The back panel and shelf for the last booth had to be cut and rewelded about 2” to fit.

3. $76.00 14”dia ductwork

1pc 14” diameter ductwork and 1pc 14” clamp. Needed to complete the main trunkline. We were short due to the booth layout on the wall changed from approved drawing.

4. $1920.00 Adjustable welding stand for overhead welding

10pcs at $192 each. Was not part of our original quote. This cost would be lower but I had to pay a rush charge to get them done by today for Monday delivery.

5. $779.00 Electrical work for the downdraft tables

This to run electrical drops from the electrical panels to each downdraft table. We have hired Nickle Electric to perform the work. Completed on 2/23/11

6. $3250.00 Labor to install items 2, 3 and 4.

Also, Urie and Blanton is providing new welding curtains that slide onto our rods. We will hang install the curtains provided (ie we will slide them onto our rods).

Items to be completed by Avani Environmental:

1. Provide and install portable fume arms for each welding table

2. Provide and install 6” Wall mount bracket for the last booth and run the 6” diameter ductwork from the bracket to the main trunkline.

3. Flash the hole in the wall where the ductwork penetrates. Avani has hired Breslin Contracting to flash the hole. They are trying to complete this week depending on weather.

4. Avani to make final electrical connections in our control panels from the collector.

5. Avani to take air flow readings at the arms and perform startup of the collector on Tuesday March 1st.

Optional items:

1. Clean out doors are not needed since the ductwork is clamp together. You can unclamp sections of the ductwork to access the inside of the ductwork to clean it.

If you want a clean out door, they are $200.00 each. We will not be able to install on this trip. If you want to install we will have to charge for travel and labor.

2. If Urie and Blanton can not provide the slide on welding curtains, we can quote you them.

5’ wide by 6’ long with grommets and hanging hardware $82.00 each plus freight