## Sheet1
| Sales Order #: | 18312 |  |  |  | Rep: | Mike
| Project Name: | GENDCO/Bear Paw |  |  |  | PO# | 174326
Brief Description:
Install Dust Collector and Arms
|  | Duct Drawings Submitted: |  |  |  | NO
|  | Customized Products: |  |  |  | NO
|  | Contractors Needed: |  |  |  | NO
EQUIPMENT | Manufacturer | Product | PO | AVI Cost | Quantity | Total | Quoted by Sales | Margin
| San Mao | Arms, Booms | 4313 | 13380 | 1 | 13380 | 28350 | 52.8%
| San Mao | SDC | 4313 |  | 1 | 0 | 29025 | 100%
0
| K&B | Duct | 4506 | 14349.73 | 1 | 14349.73 | 15216 | 18.8%
| Ferguson | Beam Clamp | 4552 | 1.848 | 40 | 73.92
| Fastenal | Flashing | 4505 | 632 | 1 | 632
| Materials - Duct From Avani |  | 0 | 242.11 | 1 | 242.11
| Material - Other |  | 0 | 228.21 | 1 | 228.21
| Duct Returned |  |  | 3170.04 |  | 3170.04
| TOTALS |  |  |  |  | 25735.93 | 72591 | 64.55%
| Project Start / Finish Dates: |  |  | 6/5/12-6/10/12
| Location: | Sidney, MT
| Crew Leader: | Rodney
LABOR | Tasks |  |  | Avani Costs | Quantity | Total | Quoted | Margin
| Labor - Travel Cost / Man Hour |  |  | 62 | 59 | 3658 | 12600 | 3.802%
| Labor - On-site / Man Hour |  |  | 62 | 136.5 | 8463
| Labor - Other Costs |  |  |  |  | 0
| Airfare: yes |  |  | 980 | 1 | 980
Total Overnight Stays:
Other -
| TOTALS |  |  |  |  | 13101 | 12600 | -3.976%
| JOB TOTAL |  |  |  |  | 38836.93 | 85191 | 54.41%
Note on E10: Cynthia: Add 15% for container shipments
Note on E28: Cynthia: use 75 for 1 man crew
Note on F27: Cynthia: x2 men
Note on F28: Cynthia: x2 men

## Sheet2
28 | 90 | 2520
2 | 165 | 330
5 | 18.315 | 91.575
1 | 36.33 | 36.33
17 | 15.6375 | 265.8375
2 | 31.7775 | 63.555
2 | 25.6425 | 51.285
3358.5825