## Sheet1
| Sales Order #: | 18125 |  |  | Rep: | Ken
| Project Name: | Horn Equipment
Brief Description:
Install Collector, Arrestor, Arms and Silencer
|  | Duct Drawings Submitted: |  |  | YES
|  | Customized Products: |  |  | NO
|  | Contractors Needed: |  |  | NO
EQUIPMENT | Manufacturer | Product | AVI Cost | Quantity | Total | Quoted by Sales | Margin
| ACT | Collector | 24696.76 | 1 | 24696.76 | 43057 | 42.64%
| Fastenal | Varies | 1790.93 | 1 | 1790.93
| SmartVent |  | 15690 | 1 | 15690 | 32500 | 51.72%
| Quality Air | Arrestor | 3093 | 1 | 3093 | 0
| Tutco | Silencer | 376 | 1 | 376 | 1473 | 74.47%
| Triangle Metal | Varies | 775 | 1 | 775
| Freight |  |  |  | 0
| Materials - Duct From Vendor |  | 13818.71 | 1 | 13818.71 | 17869 | 34.28%
| Materials - Duct From Avani |  | 4877.46 | 1 | 4877.46
| Material - Other |  | 1684.5 | 1 | 1684.5
| Duct Returned |  | 2075.68 |  | 2075.68
| TOTALS |  |  |  | 64726.68 | 94899 | 31.79%
| Project Start / Finish Dates: |  | 4/9/12-4/17/12
| Location: | Moore, OK
| Crew Leader: | Rodney
LABOR | Tasks |  | Avani Costs | Quantity | Total | Quoted | Margin
| Labor - Travel Cost / Man Hour |  | 55.5 | 26.5 | 1470.75 | 15100 | 26.15%
| Labor - On-site / Man Hour |  | 55.5 | 167 | 9268.5
| Labor - Other Costs |  |  | 0 | 0
| Airfare: Yes (MSY-OKC-RDU) |  | 1229.48 | 1
| Total Overnight Stays: |  | 412.82 | 1 | 412.82
| Rental |  | 524.65 | 1
| Luggage |  | 75 | 1 | 75
Other -
| TOTALS |  |  |  | 11227.07 | 15100 | 25.65%
| JOB TOTAL |  |  |  | 75953.75 | 109999 | 30.95%
Note on E27: Cynthia: x2 men
Note on D28: Cynthia: use 75 for 1 man crew
Note on E28: Cynthia: x2 men

## Sheet2
28 | 90 | 2520
2 | 165 | 330
5 | 18.315 | 91.575
1 | 36.33 | 36.33
17 | 15.6375 | 265.8375
2 | 31.7775 | 63.555
2 | 25.6425 | 51.285
3358.5825