## Sheet1
Change Order Form
Customer: |  | Spartanburg CC |  |  |  | Avani Environmental Intl, Inc
Sales Order Number: |  | 23074 |  |  |  | 95 Cypress Drive
Date: |  | 2015-09-10 |  |  |  | Youngsville, NC
Change Order: |  | 20150910
Change Required: | Customer requests two additional pieces of duct (24"), remote start switch,
and collector pad
Reason For Change: |  | Customer is requesting to moving collector
Materials Required: | (Details/Cost) |  |  | (2) 24" x 5' Pipe | 425
|  |  |  | Concrete pad | 495
|  |  |  | Remote start switch | 100
Freight Costs : (Details / Cost) |  |  |  | (2) Day delivery | 250
Return Trip Required |  | Yes |  | No
Cost of Change: Materials & Labor) |  |  |  |  | 1270
Approval required over $250 in total cost
Signataure: Customer / Project Manager (based on reason for change)
Customer PO Required: |  | Yes
Details/Comments:
Doc: AV-CO-01 |  |  | Rev.0 |  | Rev. Date 10/21/14